## Worksheet
Control No | Requested by | Date Needed | MIS in Charge | Details | Status | Remarks
CSR-1202-19 | Roner B. Paguirigan | 2019-12-18 21:00:00 | admin.Joe Nico T. Geronimo | SSD (Solid State Drive) to speed up NX work stations QTY 4 | Work in Progress | Delay
CSR-1371-19 | Joan M. Fortuna | 2019-10-29 21:00:00 | admin.Joe Nico T. Geronimo | CD. To free some space in CTD server. Location of folders X:\CE REQUESTING AFFILIATES\03 LOW VOLTAGE\0A FOR DVD Please save files according to customer. Do not mix different BU. | Work in Progress | Delay
CSR-1378-19 | Jovielet B. Caintoy | 2019-11-29 08:06:00 | admin.Joe Nico T. Geronimo | 1.Limit saving of files/folders outside the declared folder in 10.49.1.97-WH. (see attached file) 2.Limit saving of files/folders outside the declared folder in 10.49.1.97-WH-COMMON. (see attached file) | Work in Progress | Delay
CSR-0978-20 | Donn M. Carlos | 2020-11-20 21:00:00 | admin.Joe Nico T. Geronimo | WHD1 transfer of PC location, this is due to transfer of members to other group and no PC to be use. | Assigned | Delay
CSR-1045-20 | Patrick James R. Garcia | 2020-12-08 21:00:00 | admin.Joe Nico T. Geronimo | Transfer Lync from 10.49.3.96 to 10.49.1.234. | Assigned | Delay