## Worksheet
Control No | Requested by | Date Needed | MIS in Charge | Details | Status | Remarks
CSR-0335-20 | Jathniel I. Lopez | 2020-03-06 21:00:00 | admin.Joel Eduardo D. Ocampo | Request for automatic back-up of job's folder inside the PC 10.49.4.199 drive into PETSVRTSE(NAS DS918) inside the satellite room. | Assigned | Delay
CSR-0400-20 | Cindy S. Antonillas | 2020-06-24 21:00:00 | admin.Joel Eduardo D. Ocampo | Cannot create work order due to error occured in WO management | Work in Progress | Delay
CSR-0401-20 | Cindy S. Antonillas | 2020-06-24 21:00:00 | admin.Joel Eduardo D. Ocampo | Cannot search work order, re-open closed WO due to error in Common Administration- Project Management | Assigned | Delay
CPR-0044-20 | Raffy P. Ubaldo | 2020-07-03 08:32:00 | admin.Joel Eduardo D. Ocampo | PC not continuing to open. | Work in Progress | Delay
CSR-0563-20 | May Angely A. Ramos | 2020-07-16 21:00:00 | admin.Joel Eduardo D. Ocampo | Install Gimp in 10.49.2.2 | Assigned | Delay
CSR-0560-20 | Kaiser Ralph H. Roca | 2020-07-27 21:00:00 | admin.Joel Eduardo D. Ocampo | The following computers attached does not have a license to run the programs needed. | Assigned | Delay
CSR-0557-20 | Manuel Louie M. Soriano | 2020-07-30 21:00:00 | admin.Joel Eduardo D. Ocampo | Light-up license key doesn't work. | Work in Progress | Delay
CSR-0595-20 | Maria Teresa C. Valentin | 2020-08-06 21:00:00 | admin.Joel Eduardo D. Ocampo | In-line with the plan of changing the Microsoft office 2010 to office 365, the email address are affected. We would like to request for additional email address, to be deleted address and for existing email address but will be assigned to shared mailbox for WHD2 (HO and BO). Please receive attached for your reference of the file and its location. | Assigned | Delay
CSR-0620-20 | Belinda C. Cabico | 2020-08-14 08:00:00 | admin.Joel Eduardo D. Ocampo | Nissan Hotfix need to be installed to NX software so that the Environment of NX will become Nissan Environment. IP below needs update of NX Environment 10.49.2.180 10.49.2.93 10.49.2.210 10.49.2.56 10.49.2.190 10.49.2.91 | Work in Progress | Delay
CSR-0619-20 | Ma. Joelette L. Montemar | 2020-08-05 21:00:00 | admin.Joel Eduardo D. Ocampo | request to activate microsoft lync application for the following GM-HO & Subaru IP address | Work in Progress | Delay
CSR-0606-20 | Donn M. Carlos | 2020-08-13 21:00:00 | admin.Joel Eduardo D. Ocampo | Please activate Microsoft Lync of the following IP (10.49.5.194 / 10.49.5.40 / 10.49.1.86 / 10.49.5.38 / 10.49.5.190 / 10.49.3.145 / 10.49.3.84 / 10.49.2.158 / 10.49.5.202 / 10.49.2.234 / 10.49.2.181 / 10.49.2.191 | Work in Progress | Delay
CSR-0743-20 | Willem R. Leonardo | 2020-08-20 21:00:00 | admin.Joel Eduardo D. Ocampo | need virtual machine to load VHD file of DMS to avoid downtime during OS upgrade of DMS physical server. | Assigned | Delay
CSR-0833-20 | Danevie Alvarez | 2020-10-07 21:00:00 | admin.Joel Eduardo D. Ocampo | No report generated on call accounting system | Work in Progress | Delay
CPR-0090-20 | Emmanuel Jr. C. Jimenez | 2020-10-09 10:41:00 | admin.Joel Eduardo D. Ocampo | PC running slow after upgrading from Windows 7 to Windows 10 | Work in Progress | Delay
CSR-0866-20 | Ma. Reina Monserrat A. Abalos | 2020-10-13 21:00:00 | admin.Joel Eduardo D. Ocampo | transfer VCAD from 10.49.1.115 to 10.49.2.248 | Assigned | Delay
CSR-0846-20 | Alvin O. Ramirez | 2020-10-14 21:00:00 | admin.Joel Eduardo D. Ocampo | need to install menseki and initial cross-section camera set-up CS05W | Work in Progress | Delay
CPR-0095-20 | Patrick B. Martinez | 2020-10-19 13:28:00 | admin.Joel Eduardo D. Ocampo | PC failed to Boot up. MIS used remote access to test earlier today. | Work in Progress | Delay
CPR-0100-20 | Nerissa S. Bugaoan | 2020-10-19 10:05:00 | admin.Joel Eduardo D. Ocampo | Slow PDF-TIFF/TIFF-PDF conversion on Acrobat 2017 tool. Can affect our process if we have many drawings to convert. | Work in Progress | Delay
CSR-0961-20 | Alexander A. Robles | 2020-11-19 21:00:00 | admin.Joel Eduardo D. Ocampo | 1. Please configure EV Laptop to be used for Work from Home set-up 2. We will have an online meeting through Web Ex access point, please configure the laptop to enable this function if needed. | Assigned | Delay
CSR-0964-20 | Joseph H. Pauly | 2020-11-20 21:00:00 | admin.Joel Eduardo D. Ocampo | Installation of Adobe Acrobat DC | Assigned | Delay
CSR-0963-20 | Anthony N. Boado | 2020-12-01 21:00:00 | admin.Joel Eduardo D. Ocampo | To restict other users to access the folder in Local drive of 10.49.2.243(ARCHIVES DATA),10.49.1.127(STC ARCHIVES 2020),10.49.1.34(STC ARCHIVES 2019),10.492.194(ARCHIVES DATA) | Work in Progress | Delay
CSR-1001-20 | Ma. Reina Monserrat A. Abalos | 2020-11-24 21:00:00 | admin.Joel Eduardo D. Ocampo | back-up from 10.49.2.244\c\1.For_back_up_and_others | Assigned | Delay
CSR-1012-20 | Annabelle L. Malonda | 2020-11-27 21:00:00 | admin.Joel Eduardo D. Ocampo | Download video manuals from https://www.prism-arts.co.jp/en/support/video/ and save in \\10.49.1.97\ei\24 SOFTWARE\14 COMMON\14 REFERENCE\02 Manuals\Prism Video Manuals Please see attached file for details. | Assigned | Delay
CSR-1026-20 | Patrick B. Martinez | 2020-12-08 21:00:00 | admin.Joel Eduardo D. Ocampo | We wish to have our ev_home folder in \\10.49.1.97\ev_home Access list double checked as it was reported to us that there are other department members able to access our folders. Please make its restriction same with our \\10.49.1.97\ev | Assigned | Delay
CSR-0983-20 | Lorenie M. Maullon | 2020-12-10 21:00:00 | admin.Joel Eduardo D. Ocampo | Log-in/ server access,Email address, and Lync of new Parts member use for communication, and Job processing Ms. Wendy Lyn C. Agnote PET ID: 2025 (IP 10.49.3.140) | Work in Progress | Delay
CSR-0989-20 | Marcelo Jr. P. Santillan | 2020-12-10 21:00:00 | admin.Joel Eduardo D. Ocampo | Need to access EED hardisk for new members | Assigned | Delay
CPR-0112-20 | Mark Donne O. Opinio | 2020-12-01 15:51:00 | admin.Joel Eduardo D. Ocampo | Mouse scroll wheel defective. | Assigned | Delay
CPR-0114-20 | Rodney L. Estacion | 2020-12-09 08:12:00 | admin.Joel Eduardo D. Ocampo | No display appear on monitor after power on or even restart. | Work in Progress | Delay
CSR-0007-21 | Karmalou Sasaki | 2020-12-14 21:00:00 | admin.Joel Eduardo D. Ocampo | Internet Connection for External Auditor in 1 week starting December 14-18, 2020 | Work in Progress | Delay
CSR-1029-20 | Gilbert G. Velasquez | 2021-01-04 13:07:00 | admin.Joel Eduardo D. Ocampo | Creation new folder for the MT Dept. please see attached file for the details, METER document inside EI server will be move to the new folder(MT server) | Work in Progress | Delay
CSR-1041-20 | Rommel E. Aguilon | 2020-12-21 21:00:00 | admin.Joel Eduardo D. Ocampo | We would like to make a request to have the powerpoint file in the link below to be converted into a screensaver that will be installed to all computers in PET. This is one way to keep all PET employees reminded of their safety during these pandemic season specially in the coming holidays. \\Petsvr1097\common\ADMIN\for MIS\From_ADM_COVID-19\COVID-19 PRESENTATION.pptx\ | Assigned | Delay
CSR-0032-21 | Maria Josefa G. Samson | 2021-01-04 21:00:00 | admin.Joel Eduardo D. Ocampo | Update lync to skype | Work in Progress | Delay
CSR-0030-21 | John Hennsy C. Gamboa | 2021-01-13 21:00:00 | admin.Joel Eduardo D. Ocampo | EVC requested access to the following location, \\10.49.1.97\EVD-EVC Shared The purpose is for sharing data/information regarding SOC(substance of concern)/environment related jobs. | Work in Progress | Delay
CSR-0035-21 | Jovielet B. Caintoy | 2021-01-13 21:00:00 | admin.Joel Eduardo D. Ocampo | Request for additional folder access right of Mary Kathlene Brotonel in Hino Folder. | Work in Progress | Delay
CSR-0011-21 | Glenn L. Fabian | 2021-01-15 12:00:00 | admin.Joel Eduardo D. Ocampo | Add additional 100GB capacity to \\10.49.1.97\EI Archive\Hardware | Work in Progress | Delay
CSR-0010-21 | admin.Emiliano P. Mendoza | 2021-01-06 21:00:00 | admin.Joel Eduardo D. Ocampo | Folder access request for new MIS member - Ms Ruby Maghilum MIS folder ( \\10.49.1.97\mis ) MIS Utilities folder ( \\10.49.1.97\MIS Utilities ) | Work in Progress | Delay
CPR-0004-21 | Ernesto L. Basbas | 2021-01-11 14:34:00 | admin.Joel Eduardo D. Ocampo | Alert popped up on my screen whenever I open my PC. | Work in Progress | Delay
CPR-0007-21 | Clarice L. Jandayan | 2021-01-04 12:49:00 | admin.Joel Eduardo D. Ocampo | Problem encountered on LAN outlet.(no connection) | Assigned | Delay
CSR-0085-21 | Leen Mark R. Fulgencio | 2021-01-18 21:00:00 | admin.Joel Eduardo D. Ocampo | Requesting Internet access for our work CE20-PK-0392 (extraction of connector) finding part number of NON-yazaki connector. 6 members are in-charge. please see the following members that requesting internet access. (per user not per IP) Period starts on 01/18/21 - 02/15/21 1. pet1690 (aubrey) 2. pet1502 (RJ) 3. pet1704 (Leen) 4. pet1873 (MJ) 5. pet1902 (Otep) 6. pet1027 (Yel) | Assigned | Delay
DRR-0013-21 | Marielle B. Esula | 2021-01-25 08:37:00 | admin.Joel Eduardo D. Ocampo | (1)はめ合い(MALE,FEMALE);\\10.49.1.97\cdd\CDE\01CDC Start 16 June\SCT\202102\SCT20-PK-C079(210111)\⑧WORKING DATA;Original Directory;No;System Error | Assigned | Delay