## Worksheet
Control No | Requested by | Date Needed | MIS in Charge | Details | Status | Remarks
CSR-0335-20 | Jathniel I. Lopez | 2020-03-06 21:00:00 | admin.Joel Eduardo D. Ocampo | Request for automatic back-up of job's folder inside the PC 10.49.4.199 drive into PETSVRTSE(NAS DS918) inside the satellite room. | Assigned | Delay
CSR-0400-20 | Cindy S. Antonillas | 2020-06-24 21:00:00 | admin.Joel Eduardo D. Ocampo | Cannot create work order due to error occured in WO management | Work in Progress | Delay
CSR-0401-20 | Cindy S. Antonillas | 2020-06-24 21:00:00 | admin.Joel Eduardo D. Ocampo | Cannot search work order, re-open closed WO due to error in Common Administration- Project Management | Assigned | Delay
CPR-0044-20 | Raffy P. Ubaldo | 2020-07-03 08:32:00 | admin.Joel Eduardo D. Ocampo | PC not continuing to open. | Work in Progress | Delay
CSR-0563-20 | May Angely A. Ramos | 2020-07-16 21:00:00 | admin.Joel Eduardo D. Ocampo | Install Gimp in 10.49.2.2 | Assigned | Delay
CSR-0560-20 | Kaiser Ralph H. Roca | 2020-07-27 21:00:00 | admin.Joel Eduardo D. Ocampo | The following computers attached does not have a license to run the programs needed. | Assigned | Delay
CSR-0557-20 | Manuel Louie M. Soriano | 2020-07-30 21:00:00 | admin.Joel Eduardo D. Ocampo | Light-up license key doesn't work. | Work in Progress | Delay
CSR-0595-20 | Maria Teresa C. Valentin | 2020-08-06 21:00:00 | admin.Joel Eduardo D. Ocampo | In-line with the plan of changing the Microsoft office 2010 to office 365, the email address are affected. We would like to request for additional email address, to be deleted address and for existing email address but will be assigned to shared mailbox for WHD2 (HO and BO). Please receive attached for your reference of the file and its location. | Assigned | Delay
CSR-0620-20 | Belinda C. Cabico | 2020-08-14 08:00:00 | admin.Joel Eduardo D. Ocampo | Nissan Hotfix need to be installed to NX software so that the Environment of NX will become Nissan Environment. IP below needs update of NX Environment 10.49.2.180 10.49.2.93 10.49.2.210 10.49.2.56 10.49.2.190 10.49.2.91 | Work in Progress | Delay
CSR-0619-20 | Ma. Joelette L. Montemar | 2020-08-05 21:00:00 | admin.Joel Eduardo D. Ocampo | request to activate microsoft lync application for the following GM-HO & Subaru IP address | Work in Progress | Delay
CSR-0606-20 | Donn M. Carlos | 2020-08-13 21:00:00 | admin.Joel Eduardo D. Ocampo | Please activate Microsoft Lync of the following IP (10.49.5.194 / 10.49.5.40 / 10.49.1.86 / 10.49.5.38 / 10.49.5.190 / 10.49.3.145 / 10.49.3.84 / 10.49.2.158 / 10.49.5.202 / 10.49.2.234 / 10.49.2.181 / 10.49.2.191 | Work in Progress | Delay
CSR-0743-20 | Willem R. Leonardo | 2020-08-20 21:00:00 | admin.Joel Eduardo D. Ocampo | need virtual machine to load VHD file of DMS to avoid downtime during OS upgrade of DMS physical server. | Assigned | Delay
CSR-0833-20 | Danevie Alvarez | 2020-10-07 21:00:00 | admin.Joel Eduardo D. Ocampo | No report generated on call accounting system | Work in Progress | Delay
CPR-0090-20 | Emmanuel Jr. C. Jimenez | 2020-10-09 10:41:00 | admin.Joel Eduardo D. Ocampo | PC running slow after upgrading from Windows 7 to Windows 10 | Work in Progress | Delay
CSR-0866-20 | Ma. Reina Monserrat A. Abalos | 2020-10-13 21:00:00 | admin.Joel Eduardo D. Ocampo | transfer VCAD from 10.49.1.115 to 10.49.2.248 | Assigned | Delay
CSR-0846-20 | Alvin O. Ramirez | 2020-10-14 21:00:00 | admin.Joel Eduardo D. Ocampo | need to install menseki and initial cross-section camera set-up CS05W | Work in Progress | Delay
CPR-0095-20 | Patrick B. Martinez | 2020-10-19 13:28:00 | admin.Joel Eduardo D. Ocampo | PC failed to Boot up. MIS used remote access to test earlier today. | Work in Progress | Delay
CPR-0100-20 | Nerissa S. Bugaoan | 2020-10-19 10:05:00 | admin.Joel Eduardo D. Ocampo | Slow PDF-TIFF/TIFF-PDF conversion on Acrobat 2017 tool. Can affect our process if we have many drawings to convert. | Work in Progress | Delay
CSR-0964-20 | Joseph H. Pauly | 2020-11-20 21:00:00 | admin.Joel Eduardo D. Ocampo | Installation of Adobe Acrobat DC | Assigned | Delay
CSR-0963-20 | Anthony N. Boado | 2020-12-01 21:00:00 | admin.Joel Eduardo D. Ocampo | To restict other users to access the folder in Local drive of 10.49.2.243(ARCHIVES DATA),10.49.1.127(STC ARCHIVES 2020),10.49.1.34(STC ARCHIVES 2019),10.492.194(ARCHIVES DATA) | Work in Progress | Delay
CSR-1001-20 | Ma. Reina Monserrat A. Abalos | 2020-11-24 21:00:00 | admin.Joel Eduardo D. Ocampo | back-up from 10.49.2.244\c\1.For_back_up_and_others | Assigned | Delay
CSR-1012-20 | Annabelle L. Malonda | 2020-11-27 21:00:00 | admin.Joel Eduardo D. Ocampo | Download video manuals from https://www.prism-arts.co.jp/en/support/video/ and save in \\10.49.1.97\ei\24 SOFTWARE\14 COMMON\14 REFERENCE\02 Manuals\Prism Video Manuals Please see attached file for details. | Assigned | Delay
CSR-1026-20 | Patrick B. Martinez | 2020-12-08 21:00:00 | admin.Joel Eduardo D. Ocampo | We wish to have our ev_home folder in \\10.49.1.97\ev_home Access list double checked as it was reported to us that there are other department members able to access our folders. Please make its restriction same with our \\10.49.1.97\ev | Assigned | Delay
CSR-0983-20 | Lorenie M. Maullon | 2020-12-10 21:00:00 | admin.Joel Eduardo D. Ocampo | Log-in/ server access,Email address, and Lync of new Parts member use for communication, and Job processing Ms. Wendy Lyn C. Agnote PET ID: 2025 (IP 10.49.3.140) | Work in Progress | Delay
CSR-0989-20 | Marcelo Jr. P. Santillan | 2020-12-10 21:00:00 | admin.Joel Eduardo D. Ocampo | Need to access EED hardisk for new members | Assigned | Delay
CPR-0112-20 | Mark Donne O. Opinio | 2020-12-01 15:51:00 | admin.Joel Eduardo D. Ocampo | Mouse scroll wheel defective. | Assigned | Delay
CSR-0007-21 | Karmalou Sasaki | 2020-12-14 21:00:00 | admin.Joel Eduardo D. Ocampo | Internet Connection for External Auditor in 1 week starting December 14-18, 2020 | Work in Progress | Delay
CSR-1029-20 | Gilbert G. Velasquez | 2021-01-04 13:07:00 | admin.Joel Eduardo D. Ocampo | Creation new folder for the MT Dept. please see attached file for the details, METER document inside EI server will be move to the new folder(MT server) | Work in Progress | Delay
CSR-1041-20 | Rommel E. Aguilon | 2020-12-21 21:00:00 | admin.Joel Eduardo D. Ocampo | We would like to make a request to have the powerpoint file in the link below to be converted into a screensaver that will be installed to all computers in PET. This is one way to keep all PET employees reminded of their safety during these pandemic season specially in the coming holidays. \\Petsvr1097\common\ADMIN\for MIS\From_ADM_COVID-19\COVID-19 PRESENTATION.pptx\ | Assigned | Delay
CSR-0011-21 | Glenn L. Fabian | 2021-01-15 12:00:00 | admin.Joel Eduardo D. Ocampo | Add additional 100GB capacity to \\10.49.1.97\EI Archive\Hardware | Work in Progress | Delay
CSR-0049-21 | Mark Joseph H. Nocon | 2021-01-12 21:00:00 | admin.Joel Eduardo D. Ocampo | moritex shott application msx-500di viewer | Work in Progress | Delay
CPR-0004-21 | Ernesto L. Basbas | 2021-01-11 14:34:00 | admin.Joel Eduardo D. Ocampo | Alert popped up on my screen whenever I open my PC. | Work in Progress | Delay
CSR-0085-21 | Leen Mark R. Fulgencio | 2021-01-18 21:00:00 | admin.Joel Eduardo D. Ocampo | Requesting Internet access for our work CE20-PK-0392 (extraction of connector) finding part number of NON-yazaki connector. 6 members are in-charge. please see the following members that requesting internet access. (per user not per IP) Period starts on 01/18/21 - 02/15/21 1. pet1690 (aubrey) 2. pet1502 (RJ) 3. pet1704 (Leen) 4. pet1873 (MJ) 5. pet1902 (Otep) 6. pet1027 (Yel) | Assigned | Delay
DRR-0013-21 | Marielle B. Esula | 2021-01-25 08:37:00 | admin.Joel Eduardo D. Ocampo | (1)はめ合い(MALE,FEMALE);\\10.49.1.97\cdd\CDE\01CDC Start 16 June\SCT\202102\SCT20-PK-C079(210111)\⑧WORKING DATA;Original Directory;No;System Error | Work in Progress | Delay
CSR-0136-21 | Redemptor C. Batiduan | 2021-02-02 21:00:00 | admin.Joel Eduardo D. Ocampo | Request of MTF Reader account for 4 members of PRT. Please see attached file for details. | Work in Progress | Delay
CSR-0138-21 | Ronalyn G. Imana | 2021-02-05 21:00:00 | admin.Joel Eduardo D. Ocampo | FOR HARDWARE, SOFTWARE AND METER Request to configure the ISMS wallpaper to all PC of HW, SW, Meter. Please include PC of Ronalyn Imana (pet1531) Location \\10.49.1.97\ei\11 Common\03 ISMS\ISMS wallpaper | Work in Progress | Delay
DRR-0020-21 | Ma. Kristela T. Meomeo | 2021-02-04 07:14:00 | admin.Joel Eduardo D. Ocampo | 004 Nihongo;\\10.49.1.97\emd\emd1102;\\10.49.1.97\tqm\006 Training;No;missing folder_overlooked due to transfer of files from emd to TQM | Work in Progress | Delay
CSR-0183-21 | Belinda C. Cabico | 2021-02-15 17:00:00 | admin.Joel Eduardo D. Ocampo | Need for Work from Home from February16, 2021 to March 02, 2021 for Ms Marilou Aquino Model Name Lenovo Thinkpad X230 232582A Serial Number R9YNYGZ | Work in Progress | Delay
DRR-0022-21 | Donalene M. Lipana | 2021-02-09 16:57:00 | admin.Joel Eduardo D. Ocampo | 82199-60201;\\10.49.1.97\wh\TOYOTA\★CAE Related Documents\01. PROGRESS LIST\15=B5\702W\W20-257;Original Directory;No;FILE CORRUPTED | Assigned | Delay
DRR-0027-21 | Jaime Jr. P. Tan | 2021-02-11 10:27:00 | admin.Joel Eduardo D. Ocampo | 20170303_Hayasaka-san 20170411_Maruno-san 20170607_Machida-san;\\10.49.1.97\common\Common_Data\EV\recovered;Original Directory;Yes;We need the data for further reference. | Assigned | Delay
CSR-0263-21 | Cyrus John V. Ibea | 2021-02-26 21:00:00 | admin.Joel Eduardo D. Ocampo | Transfer of WHE Members Bryan Dave Navarro 1. Add access to \\10.49.1.97\eed\EED_Hardisk 5S\TBU-JPN for 2. Delete access to \10.49.1.97\eed\EED_Hardisk 5S\MSBU 3. Delete access to \10.49.1.97\eed\EED_Hardisk 5S\IVS Noel Sonny Sosa 1. Delete access to \\10.49.1.97\eed\EED_Hardisk 5S\TBU-JPN 2. Add access to \10.49.1.97\eed\EED_Hardisk 5S\MSBU 3. Add access to \10.49.1.97\eed\EED_Hardisk 5S\IVS | Assigned | Delay
CSR-0204-21 | Ma. Filipina G. Del Rosario | 2021-02-26 21:00:00 | admin.Joel Eduardo D. Ocampo | Grant access/permission to create & save file in common TQM folder. | Assigned | Delay
CSR-0249-21 | Williard D. Go | 2021-02-19 21:00:00 | admin.Joel Eduardo D. Ocampo | Increase storage capacity of \\10.49.1.97\TCED | Assigned | Delay
CSR-0261-21 | Jovielet B. Caintoy | 2021-03-02 21:00:00 | admin.Joel Eduardo D. Ocampo | Request for additional folder access right in \\10.49.1.97\wh\COMMON\QUALITY\COUNTERMEASURE\CONTROL LISTS Purpose- Input/update External mistake 1.Ibarrientos, Nikee M. 2. Ramos , May Angely A. | Assigned | Delay
DRR-0029-21 | Brian M. Sarmiento | 2021-02-18 06:30:00 | admin.Joel Eduardo D. Ocampo | ISMS-CPAR-HW-HO-20201125-01.pdf ISMS-CPAR-HW-HO-20201125-02.pdf;\\10.49.1.97\common\TDCD\ISMS-Internal_Audit\ISMS Corrective-Preventive Action Report 202011\HW\ForAuditorChecking\ISMS-CPAR-HW-HO-20201125-01 \\10.49.1.97\common\TDCD\ISMS-Internal_Audit\ISMS Corrective-Preventive Action Report 202011\HW\ForAuditorChecking\ISMS-CPAR-HW-HO-20201125-02;Original Directory;No;Corrupted file | Assigned | Delay
DRR-0030-21 | Johansson L. Binalla | 2021-02-23 09:22:00 | admin.Joel Eduardo D. Ocampo | (61)異品番端子の挿入検知検討【4.8_F_HLC】;\\10.49.128.7\cdd_(branch)\CDE\01CDC Start 16 June\11T\CE21-PK-0012(210128)検討\⑧WORKING DATA\① 7198-4980 (4.8_F_HLC);Original Directory;No;the file was deleted yesterday around 4pm | Assigned | Delay
CSR-0227-21 | Ernesto L. Basbas | 2021-02-26 21:00:00 | admin.Joel Eduardo D. Ocampo | Increase storage capacity of \\10.49.1.97\common\TDCD from 1GB to 2GB, This is for ISMS documentation. | Assigned | Delay
DRR-0032-21 | Janser K. Del-isen | 2021-02-26 17:00:00 | admin.Joel Eduardo D. Ocampo | RR CASE ASSY;\\10.49.1.97\ev\⑤ JOB ORDERS\EV BOX\2021\03月\OTHERS\EVB1-2101004(KATAOKA SAN)\3D MODEL;Original Directory;No;I accidentally deleted some file to be send to customer | Work in Progress | Delay
CSR-0254-21 | Vicente Z. Nieto | 2021-03-04 21:00:00 | admin.Joel Eduardo D. Ocampo | Always experienced disk full in this computer and affect the current deadline. We would to request to reformat the hardisk and don't forget to re-install all the current software and application like MTF-Reader, microsoft office etc. | Assigned | Delay
CSR-0253-21 | Vicente Z. Nieto | 2021-03-04 21:00:00 | admin.Joel Eduardo D. Ocampo | Install Microsoft Teams for GPMS meetings with TBU counterpart | Assigned | Delay