## Worksheet
Control No | Requested by | Date Needed | MIS in Charge | Details | Status | Remarks
CSR-0990-20 | Rommel E. Aguilon | 2020-12-31 21:00:00 | admin.Reymark B. Evangelista | Please replace PC with IP 10.49.2.215 (Marissa's PC) | Assigned | Delay
CSR-0829-20 | John Elly C. Javier | 2021-01-01 21:00:00 | admin.Reymark B. Evangelista | Requesting to purchase 2 CPU, CE have budget for 2 for the month of July Requirements. Intel R Core i5-9500, 1TB SSD M.2 NVME PCIe, 12GB DDR4 2666DIMM, Win 10 Pro 64 and with MS Office. | Work in Progress | Delay
CSR-0809-20 | Reymark B. Evangelista | 2021-01-04 21:00:00 | admin.Reymark B. Evangelista | ORICO 6629US3-C-V1-US-BK USB3.0 to SATA Dual Bay External Hard Drive Docking Station for 2.5 or 3.5 inch HDD, SSD with Hard Drive. For Troubleshooting Purposes and for file transfer peer to peer HDD/SSD | Work in Progress | Delay
CPR-0092-20 | Brandon Alan N. Docdocil | 2020-10-06 15:12:00 | admin.Reymark B. Evangelista | Unable to start windows 10 due to maybe power supply problem or others. countermeasure reformat or replace CPU(if defective) | Work in Progress | Delay
CSR-0899-20 | Karmalou Sasaki | 2021-01-08 21:00:00 | admin.Reymark B. Evangelista | Purchase of Laptop HP IDS DSC MX250 2GB i5-10210U440G7BNBPC | Work in Progress | Delay
CSR-1046-20 | Belinda C. Cabico | 2020-12-15 21:00:00 | admin.Reymark B. Evangelista | Transfer VISIO2003 from PC10.49.2.29 to PC10.49.3.52. PC10.49.2.29 is currently being used by TBU member but visio is needed for RNBU and HBU Jobs. Need to transfer VISIO to a PC accessible by RNBU/HBU member. | Work in Progress | Delay
CSR-0006-21 | Gene Rigor Quintos | 2020-12-18 21:00:00 | admin.Reymark B. Evangelista | What need - Identify user ID "Pet123" from what division and department he/she belongs. Why need - To improve work productivity on monthly paper consumption report. | Work in Progress | Delay
CSR-0015-21 | Ma. Cecilia B. Bermejo | 2020-12-31 21:00:00 | admin.Reymark B. Evangelista | Request for access right due to policy report requirement- \\Petsvr1097\iso\KPM\1. PET POLICY\03 EA\80th\TQM | Work in Progress | Delay
CSR-0024-21 | Rosano A. Buerano | 2021-01-08 21:00:00 | admin.Reymark B. Evangelista | Install Mentor Graphic Softwares and LP Wizard on Laptops with the following IP addresses -10.49.2.91 -10.49.5.250 -10.49.3.42 | Assigned | Delay
CSR-0033-21 | John Elly C. Javier | 2021-01-07 21:00:00 | admin.Reymark B. Evangelista | Requesting to install the imaging software of newly purchase stereo microscope. | Assigned | Delay