## Worksheet
HO October 2020
Response | Count |  |  |  | Status | Request
Ahead of Time | 54 |  |  |  | New Request | 0
On Time | 0 |  |  |  | Assigned | 8
Delay | 59 |  |  |  | Work in Progress | 18
[5 empty] | Done | 80
Ave. Response Time | 3692.42 |  |  |  | Endorse to Checker | 0
[5 empty] | Closed | 19
[5 empty] | Total Received Request | 125
Process | Count | Hours | Delay |  | Purchase | Count
CSR | 92 | 3072.64 | 43 |  | Software | 2
CPR | 12 | 441.97 | 8 |  | Hardware | 10
DRR | 9 | 66.76 | 8 |  | Renewal | 11
QA | 12 | 21.05
Members with Request and Status count info
Name | Assigned | Work in Progress | Done | Closed | Total
admin.Aaron Jet N. Sarreal | 0 | 0 | 1 | 0 | 1
admin.admin.Aaron Jet N. Sarreal | 0 | 0 | 0 | 9 | 9
admin.Christ John M. Dela Cruz | 0 | 1 | 1 | 0 | 2
admin.Emiliano P. Mendoza | 2 | 0 | 1 | 0 | 3
admin.Greg Daniel E. Mojica | 0 | 0 | 4 | 1 | 5
admin.Jasper Labenia | 0 | 4 | 10 | 0 | 14
admin.Joe Nico T. Geronimo | 0 | 0 | 4 | 0 | 4
admin.Joel Eduardo D. Ocampo | 0 | 3 | 18 | 0 | 21
admin.John Christian Lovitos | 0 | 0 | 1 | 0 | 1
admin.Kaiser Ralph H. Roca | 0 | 1 | 0 | 0 | 1
admin.Kiel S. Antaran | 0 | 2 | 2 | 6 | 10
admin.Nancy O. Gendive | 4 | 2 | 13 | 0 | 19
admin.Reymark B. Evangelista | 1 | 5 | 25 | 0 | 31
admin.Willem R. Leonardo | 0 | 0 | 0 | 3 | 3
Total |  |  |  |  | 124
Request Details
IC No. | Reference No. | Requestor | Department | Site | Request date | Request needed/occur | Status | Request | Details | Acknowledge Date | Date Receive | Date Done | In Charge | Man Hour | Response
IC-1426-20 | CSR-0737-20 | Reyna Marie I. Sarra | WHE | HO | 2020-09-16 09:28:00 | 2020-09-17 21:00:00 | Done | Install Software | Global Protect Installation to Connect in YAZAKI network. | 2020-10-06 08:47:00 | 2020-09-21 00:00:00 | 2020-10-06 09:07:00 | admin.Joel Eduardo D. Ocampo | 0.33 | Ahead of Time
IC-1427-20 | CSR | Reyna Marie I. Sarra | WHE | HO | 2020-09-16 09:34:00 | 2020-10-28 21:00:00 | Assigned | Software Purchase | Global Protect Installation to connect in YAZAKI network | 0000-00-00 00:00:00 | 0000-00-00 00:00:00 | 0000-00-00 00:00:00
IC-1429-20 | CSR-0738-20 | Reyna Marie I. Sarra | WHE | HO | 2020-09-16 12:25:00 | 2020-09-17 21:00:00 | Done | Install Software | Global Protect Installation to connect with YAZAKI network | 2020-09-28 13:04:00 | 2020-09-21 00:00:00 | 2020-10-02 12:52:00 | admin.Joel Eduardo D. Ocampo | 59.8 | Delay
IC-1430-20 | CSR-0729-20 | Ma. Kristela T. Meomeo | EA | HO | 2020-09-16 12:44:00 | 2020-09-17 21:00:00 | Done | Install Software | Install the Tableau Tool in 10.49.2.185 | 2020-09-17 13:46:00 | 2020-09-17 00:00:00 | 2020-11-17 07:16:00 | admin.Aaron Jet N. Sarreal | 638.5 | Delay
IC-1432-20 | CSR-0744-20 | Jayson L. Toding | WHD2 | HO | 2020-09-16 16:09:00 | 2020-09-18 21:00:00 | Done | Install Software | Please install Microsoft Lync in IP 10.49.3.24. The PC will be used for the KD viewer training of Branch office members. | 2020-09-22 08:26:00 | 2020-09-22 00:00:00 | 2020-09-23 06:59:00 | admin.Joel Eduardo D. Ocampo | 13.55 | Delay
IC-1433-20 | CSR-0770-20 | Marcelo Jr. P. Santillan | WHE | HO | 2020-09-17 08:33:00 | 2020-09-18 21:00:00 | Done | Modify Software | Request for computer reformat due to slow work performance | 2020-10-09 21:26:00 | 2020-09-28 00:00:00 | 2020-10-09 21:26:00 | admin.Jasper Labenia | 0 | Ahead of Time
IC-1438-20 | DRR-0092-20 | Marron C. De Guzman | JBRB | HO | 2020-09-17 12:10:00 | 2020-09-17 12:04:00 | Done | Cae | Parts;Z:\01_JBRB Design\00 JOB ORDERS\ECI-41T\SUZUKI\2020\10-OCTOBER\EKIK-20090XX (YFG) FURUSAWA SAN\03 OUTPUT\NEW LAYOUT_0917;Original Directory;Yes;Date deleted | 2020-09-30 12:38:00 | 2020-09-28 00:00:00 | 2020-09-30 12:39:00 | admin.Reymark B. Evangelista | 0.02 | Ahead of Time
IC-1439-20 | CSR-0733-20 | Jennygene P. Toding | EDSD | HO | 2020-09-17 12:48:00 | 2020-09-28 21:00:00 | Done | Access Request | Kindly add access in \\10.49.1.97\iso\KPM\1. PET POLICY\03 EA. Thank you and have a nice day. | 2020-09-21 16:44:00 | 2020-09-18 00:00:00 | 2020-09-21 16:45:00 | admin.Reymark B. Evangelista | 0.02 | Ahead of Time
IC-1440-20 | CSR-0732-20 | Rolando Jr. C. Fernandez | JBRB | HO | 2020-09-17 12:51:00 | 2020-09-18 21:00:00 | Done | Install Software | VPN Access | 2020-09-17 19:39:00 | 2020-09-17 00:00:00 | 2020-09-17 19:39:00 | admin.Jasper Labenia | 0 | Ahead of Time
IC-1441-20 | CPR-0079-20 | Rafael S. Fontenuela | JBRB | HO | 2020-09-17 16:11:00 | 2020-09-17 16:05:00 | Done | Operating System | Blue screen occurred several times. Cannot do simulation job. | 2020-09-22 06:57:00 | 2020-09-21 00:00:00 | 2020-09-25 06:42:00 | admin.Joel Eduardo D. Ocampo | 80.62 | Delay
IC-1459-20 | QA-0366-20 | Grace A. Rivera | SCD | HO | 2020-09-18 08:28:00 | 2020-09-18 08:28:00 | Closed |  | OMS request data adjustment. | 2020-09-18 08:28:00 | 2020-09-18 08:28:00 | 2020-09-18 08:30:00 | admin.admin.Aaron Jet N. Sarreal | 0.03 | Ahead of Time
IC-1444-20 | DRR-0089-20 | Francis Benjamin C. Cagampan | JBRB | HO | 2020-09-18 09:40:00 | 2020-09-18 09:34:00 | Work in Progress | Cae | 07_JUL 08_AUG 09_SEPT;\\10.49.1.97\jbrb\01_JBRB Design\00 JOB ORDERS\ECI-23T\TOYOTA\2019;Original Directory;No;Data was deleted, no back up was made. please retrieve, thank you | 2020-09-23 09:00:00 | 2020-09-23 00:00:00 | 0000-00-00 00:00:00 | admin.Nancy O. Gendive
IC-1445-20 | CSR-0764-20 | Rosalinda P. Tayer | WHD1 | HO | 2020-09-18 13:43:00 | 2020-09-21 21:00:00 | Done | Install Software | Add Winshot application for easier and clear screenshot and editing of images. | 2020-10-12 08:28:00 | 2020-09-28 00:00:00 | 2020-10-20 13:03:00 | admin.Reymark B. Evangelista | 94.58 | Delay
IC-1448-20 | CSR-0736-20 | Marcelo Jr. P. Santillan | WHE | HO | 2020-09-18 15:40:00 | 2020-09-21 21:00:00 | Done | Transfer PC location | New PC will be used and the existing PC will be transfer inside TSE room. | 2020-09-21 19:03:00 | 2020-09-21 00:00:00 | 2020-09-21 19:03:00 | admin.Jasper Labenia | 0 | Ahead of Time
IC-1449-20 | CSR-0742-20 | Judelyn E. Rosales | EA | HO | 2020-09-18 15:48:00 | 2020-09-29 21:00:00 | Done | Access Request | Folder Access request for Saavedra, Sara Lee (User ID pet6073) | 2020-09-25 16:55:00 | 2020-09-21 00:00:00 | 2020-10-07 10:19:00 | admin.Joe Nico T. Geronimo | 113.4 | Delay
IC-1450-20 | CPR-0081-20 | Redemptor C. Batiduan | PRT | HO | 2020-09-19 14:13:00 | 2020-09-18 14:07:00 | Done | PC Harddisk | Workstation failed to boot-up due to defective hard disk. Recommended to replace immediately. | 2020-09-28 15:34:00 | 2020-09-21 00:00:00 | 2020-10-26 17:00:00 | admin.Jasper Labenia | 392.88 | Delay
IC-1458-20 | QA-0365-20 | Ma. Kristela T. Meomeo | EA | HO | 2020-09-21 06:30:00 | 2020-09-21 06:30:00 | Closed |  | Tableau change language to english | 2020-09-21 06:30:00 | 2020-09-21 06:30:00 | 2020-09-21 08:26:00 | admin.admin.Aaron Jet N. Sarreal | 1.93 | Delay
IC-1460-20 | QA-0367-20 | Johanna Marie C. Dandan | SCD | HO | 2020-09-21 06:30:00 | 2020-09-21 06:30:00 | Closed |  | OMS Return order sheet status | 2020-09-21 06:30:00 | 2020-09-21 06:30:00 | 2020-09-21 08:30:00 | admin.admin.Aaron Jet N. Sarreal | 2 | Delay
IC-1457-20 | QA-0364-20 | Ruby A. Maghilum | EA | HO | 2020-09-21 08:10:00 | 2020-09-21 08:10:00 | Closed |  | Borrow Headset | 2020-09-21 08:10:00 | 2020-09-21 08:10:00 | 2020-09-21 08:20:00 | admin.admin.Aaron Jet N. Sarreal | 0.17 | Ahead of Time
IC-1461-20 | QA-0368-20 | Marcelo Jr. P. Santillan | WHE | HO | 2020-09-21 08:20:00 | 2020-09-21 08:20:00 | Closed |  | Setup email account in outlook | 2020-09-21 08:20:00 | 2020-09-21 08:20:00 | 2020-09-21 08:40:00 | admin.admin.Aaron Jet N. Sarreal | 0.33 | Ahead of Time
IC-1451-20 | CPR-0084-20 | Zedrick Jaymes Nino C Enrile | PRT | HO | 2020-09-21 09:19:00 | 2020-09-21 09:13:00 | Done | Mouse | Right Click is loosing and hard to click. | 2020-09-29 10:21:00 | 2020-09-28 00:00:00 | 2020-09-29 11:18:00 | admin.Nancy O. Gendive | 92.08 | Delay
IC-1452-20 | CSR-0801-20 | Marcelo Jr. P. Santillan | WHE | HO | 2020-09-21 09:30:00 | 2020-09-22 21:00:00 | Done | Modify Software | Transfer Lync from 10.49.5.127 to 10.49.2.50. Existing Lync user was transfered from 10.49.5.127 to 10.49.2.50 | 2020-10-08 11:58:00 | 2020-10-06 00:00:00 | 2020-10-29 20:20:00 | admin.Reymark B. Evangelista | 233.37 | Delay
IC-1463-20 | QA-0370-20 | Axl Rose S. Landicho | WHD3 | HO | 2020-09-21 10:00:00 | 2020-09-21 10:00:00 | Closed |  | Assist in Lync Meeting | 2020-09-21 10:00:00 | 2020-09-21 10:00:00 | 2020-09-21 10:25:00 | admin.admin.Aaron Jet N. Sarreal | 0.42 | Ahead of Time
IC-1462-20 | QA-0369-20 | Anna Liza E. Ilusorio | WHD3 | HO | 2020-09-21 10:34:00 | 2020-09-21 10:34:00 | Closed |  | Assist in Lync Meeting | 2020-09-21 10:34:00 | 2020-09-21 10:34:00 | 2020-09-22 10:40:00 | admin.admin.Aaron Jet N. Sarreal | 15.1 | Delay
IC-1453-20 | CSR-0762-20 | Nelio E. Medina | EA | HO | 2020-09-21 12:05:00 | 2020-09-22 21:00:00 | Done | Modify Software | Please speed-up my present version of excel... The translation job I'm doing right now has so many pictures in the files. Editing using the present excel files is very very slow. Please expedite this request because the deadline is quite tight. Thank you. | 2020-10-05 14:43:00 | 2020-09-28 00:00:00 | 2020-10-05 15:39:00 | admin.Jasper Labenia | 0.93 | Ahead of Time
IC-1454-20 | CSR-0765-20 | Ronalyn G. Imana | SCD | HO | 2020-09-21 13:57:00 | 2020-11-02 21:00:00 | Done | Renewal License | FOR JBRB Request for CATIA license renewal Target ID : VWY-43491CB1D72C98EC Product is GPS IP Address 10.49.2.242 Budget PhP 447,433.53 (February 2021) | 2020-10-02 13:22:00 | 2020-09-28 00:00:00 | 2020-10-26 17:00:00 | admin.Jasper Labenia
IC-1455-20 | CPR-0083-20 | Rafael S. Fontenuela | JBRB | HO | 2020-09-21 14:19:00 | 2020-09-17 14:14:00 | Done | WS Video Card | Video Card problem for 10.49.5.3. Cannot handle ANSYS simulation. | 2020-09-29 07:02:00 | 2020-09-28 00:00:00 | 2020-09-29 07:02:00 | admin.Joel Eduardo D. Ocampo | 112.8 | Delay
IC-1464-20 | QA-0371-20 | Lariza R. Calara | EA | HO | 2020-09-22 08:10:00 | 2020-09-22 08:10:00 | Closed |  | shortcut to Server problem | 2020-09-22 08:10:00 | 2020-09-22 08:10:00 | 2020-09-22 08:20:00 | admin.admin.Aaron Jet N. Sarreal | 0.17 | Ahead of Time
IC-1465-20 | QA-0372-20 | Joe Nico T. Geronimo | MIS | HO | 2020-09-22 08:15:00 | 2020-09-22 08:15:00 | Closed |  | SRS problem wrong email | 2020-09-22 08:15:00 | 2020-09-22 08:15:00 | 2020-09-22 08:40:00 | admin.admin.Aaron Jet N. Sarreal | 0.42 | Ahead of Time
IC-1466-20 | CSR-0756-20 | Donn M. Carlos | WHD1 | HO | 2020-09-22 10:37:00 | 2020-11-03 21:00:00 | Closed | Renewal License | CADRA renewal 10.49.1.88 10.49.2.148 10.49.3.251 | 2020-09-28 11:04:00 | 2020-09-28 00:00:00 | 2020-12-01 08:28:00 | admin.Kiel S. Antaran | 687.4
IC-1467-20 | CSR-0766-20 | Karl Christopher G. Abanto | WHD1 | HO | 2020-09-22 15:12:00 | 2020-09-23 21:00:00 | Done | Modify Software | F2 function is unable to operate on cadra | 2020-09-29 06:41:00 | 2020-09-28 00:00:00 | 2020-09-29 06:42:00 | admin.Christ John M. Dela Cruz | 0.02 | Ahead of Time
IC-1468-20 | CSR-0745-20 | Ma. Kristela T. Meomeo | EA | HO | 2020-09-22 15:38:00 | 2020-10-01 21:00:00 | Done | Access Request | Delete windows log-in of Jeniline Trina Jamora (pet1849) | 2020-09-23 08:31:00 | 2020-09-23 00:00:00 | 2020-09-23 10:43:00 | admin.Nancy O. Gendive | 2.2 | Delay
IC-1471-20 | CSR-0771-20 | Belinda C. Cabico | WHE | HO | 2020-09-23 10:13:00 | 2020-12-23 21:00:00 | Assigned | Hardware Purchase | NX Workstation Replacement (Change to Laptop Workstation) 10.49.2.91 10.49.1.56 | 0000-00-00 00:00:00 | 2020-09-28 00:00:00 | 0000-00-00 00:00:00 | admin.Nancy O. Gendive
IC-1474-20 | CSR-0752-20 | Merry Joy Magana | WHE | HO | 2020-09-23 11:30:00 | 2020-09-24 21:00:00 | Done | Install Software | Install MTF Reader, Cabling Designer and PDF Exchange Viewer for TBU jobs | 2020-09-28 09:58:00 | 2020-09-28 00:00:00 | 2020-10-02 11:04:00 | admin.Joel Eduardo D. Ocampo | 61.1 | Delay
IC-1475-20 | CSR-0781-20 | Ann Mary Grace A Alde | SCD | HO | 2020-09-23 12:53:00 | 2020-12-23 21:00:00 | Work in Progress | Hardware Purchase | FOR JBRB INVESTMENT QUOTATION CIP NO. 2020/7-12 #15 Equipment name SolidWorks Workstation QTY 3 UNIT PRICE (PHP)174,000 TOTAL AMOUNT (PHP)522,00 IP address 10.49.1.225 10.49.7.226 10.49.2.20 | 2020-10-14 13:05:00 | 2020-09-29 00:00:00 | 0000-00-00 00:00:00 | admin.Jasper Labenia
IC-1476-20 | CSR-0780-20 | Ann Mary Grace A Alde | SCD | HO | 2020-09-23 12:57:00 | 2020-12-23 21:00:00 | Work in Progress | Hardware Purchase | FOR JBRB INVESTMENT QUOTATION CIP No.2020/7-12 #16 Department 204-JBRB Equipment name ANSYS Workstation QTY 1 UNIT PRICE (PHP) 293,000 TOTAL AMOUNT (PHP) 293,000 IP ADDRESS 10.49.1.186 | 2020-10-14 13:05:00 | 2020-09-29 00:00:00 | 0000-00-00 00:00:00 | admin.Jasper Labenia
IC-1478-20 | CSR-0812-20 | Charmaine D.C. Dadua | WHD3 | HO | 2020-09-24 07:27:00 | 2020-09-25 21:00:00 | Done | Transfer Software location | Transfer Extes Application from 10.49.3.149 to 10.49.1.111. Advised by superior to use 10.49.1.111, so the software needed must be transfer. | 2020-10-29 10:21:00 | 2020-10-08 00:00:00 | 2020-10-29 10:21:00 | admin.Greg Daniel E. Mojica | 0 | Ahead of Time
IC-1479-20 | CSR-0814-20 | Merry Joy Magana | WHE | HO | 2020-09-24 09:01:00 | 2020-09-25 21:00:00 | Done | Install Software | Install MTF Reader, PDF Exchange Viewer and PDF Creator for TBU jobs | 2020-10-08 11:18:00 | 2020-10-08 00:00:00 | 2020-10-08 11:20:00 | admin.Joel Eduardo D. Ocampo | 0.03 | Ahead of Time
IC-1481-20 | CSR-0815-20 | Valerie Meg G. Marcelo | WHD3 | HO | 2020-09-24 13:32:00 | 2020-09-25 21:00:00 | Closed | Transfer Software location | Transfer of Extes application from 10.49.2.187 to 10.49.2.152. | 2020-10-28 08:09:00 | 2020-10-08 00:00:00 | 2020-10-28 10:49:00 | admin.Greg Daniel E. Mojica | 2.67 | Delay
IC-1485-20 | CSR-0758-20 | Mary Joy L. De Belen | EDSD | HO | 2020-09-24 14:37:00 | 2020-12-11 21:00:00 | Work in Progress | Renewal License | CAE Server Maintenance Agreement Renewal Date: November 2020 – November 2021 IP address: 10.49.0.233 Serial No.: MA6C201981 Site: Head Office Budget Category: Software Usage-Others | 2020-12-21 12:42:00 | 2020-09-28 00:00:00 | 0000-00-00 00:00:00 | admin.Kaiser Ralph H. Roca
IC-1483-20 | CSR-0750-20 | Franz Myka M. Dumlao | WHD1 | HO | 2020-09-24 15:25:00 | 2020-09-25 21:00:00 | Work in Progress | Backup to CD/DVD | For CD transfer due to reduce files in server. (\\10.49.1.97\wh\GMT\8. HARNESS RELATED FILES\1. E-MOCHIKIN\2015-2018 MOCHIKIN- for CD transfer) | 2020-09-28 08:32:00 | 2020-09-28 00:00:00 | 0000-00-00 00:00:00 | admin.Nancy O. Gendive
IC-1484-20 | CSR-0749-20 | Annabelle L. Malonda | EI | HO | 2020-09-24 15:36:00 | 2020-09-25 21:00:00 | Done | Laptop Configuration | Configure the laptop PC for WFH arrangement for Louie Sablay (ID no. pet1872). | 2020-09-28 07:46:00 | 2020-09-25 00:00:00 | 2020-09-28 09:09:00 | admin.Joel Eduardo D. Ocampo | 1.38 | Delay
IC-1486-20 | CSR-0757-20 | Mary Joy L. De Belen | EDSD | HO | 2020-09-24 16:03:00 | 2020-11-05 21:00:00 | Done | Renewal License | KD Converter Renewal Subscription Date: November 2020 – November 2021 IP address: 10.49.1.50 Host ID: C7TOPST Site: Head Office Budget Category: Software Usage-YC | 2020-10-02 10:54:00 | 2020-09-28 00:00:00 | 2020-11-10 10:14:00 | admin.Kiel S. Antaran
IC-1490-20 | CSR-0755-20 | Jennygene P. Toding | EDSD | HO | 2020-09-25 10:04:00 | 2020-12-25 21:00:00 | Work in Progress | Hardware Purchase | CAE Server & SAN Switch Replacement 2020/7-12#11 | 2020-09-28 11:04:00 | 2020-09-28 00:00:00 | 0000-00-00 00:00:00 | admin.Kiel S. Antaran
IC-1491-20 | CSR-0754-20 | Ma. Reina Monserrat A. Abalos | WHD2 | HO | 2020-09-25 10:53:00 | 2020-10-06 21:00:00 | Done | Access Request | add temporary access | 2020-09-28 13:08:00 | 2020-09-28 00:00:00 | 2020-10-01 13:08:00 | admin.Joel Eduardo D. Ocampo | 45 | Delay
IC-1494-20 | CSR-0759-20 | Rafael O. Pangilinan | EA | HO | 2020-09-28 08:24:00 | 2020-10-07 21:00:00 | Done | Access Request | Request for Kazuyasu Hiyoshi (ID No.Y038522) to have a Removal access Location: \\10.49.1.97\emd\PET-RC SHARED FOLDER\YC_Material \\10.49.1.97\emd\PET-RC SHARED FOLDER\YC_Parts \\10.49.1.97\emd\PET-RC SHARED FOLDER\MC_Parts Request for Hiromi Kishioka (ID No.Y042531) to have a Removal of access Location: \\10.49.1.97\emd\PET-RC SHARED FOLDER\YC_Material \\10.49.1.97\emd\PET-RC SHARED FOLDER\YC_Parts \\10.49.1.97\emd\PET-RC SHARED FOLDER\MC_Parts Request for shigeaki Yagi (ID No.Y041241) to have a Read/Write access Location: \\10.49.1.97\emd\PET-RC SHARED FOLDER\YC_Material \\10.49.1.97\emd\PET-RC SHARED FOLDER\YC_Parts \\10.49.1.97\emd\PET-RC SHARED FOLDER\MC_Parts Request for Kana Matsushita (ID No.Z026112) to have a Read/Write access Location: \\10.49.1.97\emd\PET-RC SHARED FOLDER\YC_Material \\10.49.1.97\emd\PET-RC SHARED FOLDER\YC_Parts \\10.49.1.97\emd\PET-RC SHARED FOLDER\MC_Parts | 2020-10-05 14:44:00 | 2020-09-28 00:00:00 | 2020-10-05 15:18:00 | admin.Reymark B. Evangelista | 0.57 | Ahead of Time
IC-1495-20 | CSR-0753-20 | Tohru Ozaki | SPTF | HO | 2020-09-28 09:28:00 | 2020-09-29 21:00:00 | Done | PC Configuration | Request for Dual monitor. | 2020-10-01 14:54:00 | 2020-09-28 00:00:00 | 2020-10-07 10:14:00 | admin.Joe Nico T. Geronimo | 55.33 | Delay
IC-1497-20 | DRR-0116-20 | Abigail E. Salas | WHD2 | HO | 2020-09-28 12:01:00 | 2020-08-24 10:30:00 | Done | Windows | PWSMS-035-YG20(D21E2UB760_D-D00);\\10.49.1.97\wh\GMT\5. FORMS\5. ORIGINAL SOFT COPIES\PWSMS\YYA\2020;Original Directory;No;Overwrite file | 2020-12-04 08:03:00 | 2020-12-04 00:00:00 | 2020-12-10 12:52:00 | admin.Reymark B. Evangelista | 64.82 | Delay
IC-1498-20 | CSR-0816-20 | Maria Karen L. De Guia | WHD1 | HO | 2020-09-28 13:33:00 | 2020-09-29 21:00:00 | Done | Transfer Software location | transfer extes from 10.49.1.110 to 10.49.3.57. Checker need this software. | 2020-10-08 20:17:00 | 2020-10-08 00:00:00 | 2020-10-09 16:36:00 | admin.John Christian Lovitos | 11.32 | Delay
IC-1499-20 | DRR-0096-20 | Jayson R. Bontigao | CON | HO | 2020-09-28 14:30:00 | 2020-09-28 14:24:00 | Done | Windows | (04)2.3Ⅱ4P-M端子拾い (下方向);\\10.49.1.97\cdd\CDE\01CDC Start 16 June\SCT\202010\SCT20-PK-C042(200908)\⑧WORKING DATA\2.3Ⅱ 4P-M;Original Directory;Yes;accidentally deleted file while transfering to other folder | 2020-10-08 12:01:00 | 2020-10-08 00:00:00 | 2020-10-08 12:01:00 | admin.Reymark B. Evangelista | 0 | Ahead of Time
IC-1505-20 | CSR-0772-20 | Ma. Reina Monserrat A. Abalos | WHD2 | HO | 2020-09-29 07:09:00 | 2020-10-08 21:00:00 | Done | Access Request | please grant temporary access. access request form is attached thank you | 2020-10-01 06:39:00 | 2020-09-29 00:00:00 | 2020-10-01 14:33:00 | admin.Joel Eduardo D. Ocampo | 7.9 | Delay
IC-1506-20 | DRR-0095-20 | Bryan Mar R. Alvarez | WHD1 | HO | 2020-09-29 08:11:00 | 2020-09-29 08:06:00 | Closed | Cae | 81400cc000-080-k1;/export/home/cadra/DRAW/CAE/PET/FUJIJU/SUB_ASSY/MS2;Original Directory;;deleted accidentally | 2020-10-08 11:26:00 | 2020-10-08 00:00:00 | 2020-10-08 12:47:00 | admin.Kiel S. Antaran | 1.35 | Delay
IC-1508-20 | QA-0373-20 | Donn M. Carlos | WHD1 | HO | 2020-09-29 10:50:00 | 2020-09-29 10:50:00 | Closed |  | cannot join to lync meeting and always logout map server | 2020-09-29 10:50:00 | 2020-09-29 10:50:00 | 2020-09-29 11:01:00 | admin.Willem R. Leonardo | 0.18 | Ahead of Time
IC-1510-20 | CSR-0785-20 | Annabelle L. Malonda | EI | HO | 2020-09-29 11:25:00 | 2020-09-30 21:00:00 | Done | Install Software | Install viewer for MSVisio files in the following PCs. 10.49.1.129 10.49.3.151 10.49.1.172 10.49.3.14 10.49.3.81 10.49.3.13 10.49.1.145 10.49.3.163 10.49.3.153 10.49.1.152 10.49.3.155 | 2020-10-12 06:57:00 | 2020-09-30 00:00:00 | 2020-10-17 08:55:00 | admin.Reymark B. Evangelista | 76.97 | Delay
IC-1509-20 | CSR-0783-20 | Joan M. Rivera | EDSD | HO | 2020-09-29 11:27:00 | 2020-10-08 21:00:00 | Done | Access Request | Need access for new in charge person \\10.49.1.97\common\★★YC EVP Mr. Watanabe Project★★\000.KPI\80th term Vehicle Program KPIs | 2020-10-01 06:53:00 | 2020-09-30 00:00:00 | 2020-10-01 13:09:00 | admin.Joel Eduardo D. Ocampo | 6.27 | Delay
IC-1511-20 | CSR-0782-20 | Vicente Z. Nieto | WHE | HO | 2020-09-29 11:51:00 | 2020-10-08 21:00:00 | Done | Access Request | Please allow Ma'am Liezel to access the TBU PM ASSISTANT folder | 2020-09-30 17:38:00 | 2020-09-30 00:00:00 | 2020-09-30 17:39:00 | admin.Reymark B. Evangelista | 0.02 | Ahead of Time
IC-1513-20 | CSR-0820-20 | Ma. Kristela T. Meomeo | EA | HO | 2020-09-29 14:36:00 | 2020-10-08 21:00:00 | Done | Access Request | request access to \\10.49.1.97\iso\KPM\1. PET POLICY\03 EA\80th\TQM | 2020-10-23 07:37:00 | 2020-10-08 00:00:00 | 2020-12-01 15:06:00 | admin.Joe Nico T. Geronimo | 412.48 | Delay
IC-1514-20 | CSR-0793-20 | Annabelle L. Malonda | EI | HO | 2020-09-29 14:45:00 | 2020-09-30 21:00:00 | Done | Laptop Configuration | Configure Laptop PC for work-from-home arrangement for Louie Sablay (ID no. pet1872) Laptop of meeting room 5A (HP Probook 440 G6) Needed Software VPN MSOffice Notepad++ | 2020-10-02 15:56:00 | 2020-10-02 00:00:00 | 2020-10-05 16:14:00 | admin.Reymark B. Evangelista | 15.3 | Delay
IC-1515-20 | CSR-0788-20 | Ronalyn G. Imana | SCD | HO | 2020-09-29 15:01:00 | 2020-10-08 21:00:00 | Done | Account Request | FOR SOFTWARE - connection to CSR-0773-20 folder access Request for windows access and folder access in Manabu Ohki Y051984- Leader of ECI-Software 13T in the following folders \\10.49.1.97\ei\31 ECI→PET\(SOFTWARE)\SW1 \\10.49.1.97\ei\32 PET→ECI\(SOFTWARE)\SW1 | 2020-10-01 14:45:00 | 2020-10-01 00:00:00 | 2020-10-06 06:41:00 | admin.Reymark B. Evangelista | 36.93 | Delay
IC-1516-20 | CSR-0819-20 | Acer Chael R. Dupaya | PRT | HO | 2020-09-29 15:34:00 | 2020-10-02 21:00:00 | Done | Transfer Software location | Transfer of Microsoft LYNC from 10.49.2.194 PC to 10.49.1.165 PC. | 2020-10-22 13:45:00 | 2020-10-08 00:00:00 | 2020-10-22 13:48:00 | admin.Reymark B. Evangelista | 0.05 | Ahead of Time
IC-1517-20 | CPR-0085-20 | Reymark B. Evangelista | MIS | HO | 2020-09-29 20:13:00 | 2020-09-29 16:30:00 | Done | Server | servers down due aircon malfunction. 4.45 to 5.45pm Time Resolve 6.15 | 2020-10-06 07:40:00 | 2020-10-05 00:00:00 | 2020-10-06 08:11:00 | admin.Joel Eduardo D. Ocampo | 66.68 | Delay
IC-1518-20 | CSR-0817-20 | Donn M. Carlos | WHD1 | HO | 2020-09-30 08:36:00 | 2021-03-31 08:27:00 | Work in Progress | Software Purchase | CADRA w/ DXF license CADRA license | 2020-10-08 12:01:00 | 2020-10-08 00:00:00 | 0000-00-00 00:00:00 | admin.Kiel S. Antaran
IC-1519-20 | CSR-0789-20 | Jennygene P. Toding | EDSD | HO | 2020-09-30 08:45:00 | 2020-10-01 21:00:00 | Done | Printer Configuration | Please set-up printers for Mr. Asada to have his scanned files directly in his email. | 2020-10-02 09:17:00 | 2020-10-01 00:00:00 | 2020-10-02 16:28:00 | admin.Reymark B. Evangelista | 7.18 | Delay
IC-1521-20 | CSR-0803-20 | Cecil T. Morales | WHD3 | HO | 2020-09-30 09:00:00 | 2020-10-01 21:00:00 | Done | Transfer Software location | I would like to request transfer of MICROSOFT LYNC from 10.49.5.241 to 10.49.2.89 | 2020-10-06 12:51:00 | 2020-10-06 00:00:00 | 2020-10-06 12:51:00 | admin.Joel Eduardo D. Ocampo | 0 | Ahead of Time
IC-1525-20 | CSR-0798-20 | Rafael S. Fontenuela | JBRB | HO | 2020-09-30 17:04:00 | 2020-10-09 21:00:00 | Done | Account Request | ECI J3T Member Terada-san need to access PET server to view Low Voltage Simulation group weekly schedule. | 2020-10-05 14:33:00 | 2020-10-05 00:00:00 | 2020-10-05 14:33:00 | admin.Reymark B. Evangelista | 0 | Ahead of Time
IC-1526-20 | CSR-0802-20 | Donn M. Carlos | WHD1 | HO | 2020-10-01 08:38:00 | 2020-11-16 14:47:00 | Done | Access Request | Request for SSN folder access of the following members. 1. Albert Mangabay 2. Alfie Villamor 3. Irene Durana 4. Kevin Diwa Please check attachment for their User ID and password | 2020-10-06 14:22:00 | 2020-10-06 00:00:00 | 2020-12-15 15:59:00 | admin.Reymark B. Evangelista | 751.62 | Delay
IC-1527-20 | CSR-0790-20 | Ronalyn G. Imana | SCD | HO | 2020-10-01 09:25:00 | 2020-10-12 21:00:00 | Done | Account Request | FOR EI-SOFTWARE Request of windows login and folder access for ECI Software MBD counterpart. Folders need to be accessed are as follows. \\10.49.1.97\ei\31 ECI→PET\ECI→PET(SOFTWARE) \\10.49.1.97\ei\32 PET→ECI\PET→ECI(SOFTWARE) ID NO. NAME TEAM 1 Y054760 Kentaro Murai EEDS Soft 2 | 2020-10-05 09:18:00 | 2020-10-02 00:00:00 | 2020-10-05 09:22:00 | admin.Reymark B. Evangelista | 0.07 | Ahead of Time
IC-1528-20 | CSR-0787-20 | Rhiessa Sarah Z. Tuyor | EV-CE | HO | 2020-10-01 09:39:00 | 2020-10-02 21:00:00 | Done | PC Configuration | request mouse | 2020-10-01 15:07:00 | 2020-10-01 00:00:00 | 2020-10-01 15:08:00 | admin.Nancy O. Gendive | 0.02 | Ahead of Time
IC-1529-20 | CSR-0818-20 | Bryan Mar R. Alvarez | WHD1 | HO | 2020-10-01 10:33:00 | 2020-10-02 21:00:00 | Closed | Backup CAE file/s | We added folder named "EM6" in directory, "export/home/eucoodb/model/work/SBR" Please add this folder to the backup list, thank you. | 2020-10-08 12:38:00 | 2020-10-08 00:00:00 | 2020-10-08 12:46:00 | admin.Kiel S. Antaran | 0.13 | Ahead of Time
IC-1530-20 | CSR-0990-20 | Rommel E. Aguilon | ADM | HO | 2020-10-01 11:41:00 | 2020-12-31 21:00:00 | Assigned | Hardware Purchase | Please replace PC with IP 10.49.2.215 (Marissa's PC) | 0000-00-00 00:00:00 | 2020-12-04 00:00:00 | 0000-00-00 00:00:00 | admin.Reymark B. Evangelista
IC-1532-20 | CSR-0792-20 | April D. Dayapan | EI | HO | 2020-10-01 15:01:00 | 2020-12-10 21:00:00 | Work in Progress | Renewal License | CATIA Annual License Charge- Php 150,544.00 Software Usage Others Budget (EI_MEC) Target ID - FTI-42861065F32A4BB4 December 2020 Budget | 2020-10-15 19:34:00 | 2020-10-02 00:00:00 | 0000-00-00 00:00:00 | admin.Jasper Labenia
IC-1533-20 | DRR-0093-20 | Edvin B. Pantoni | EV | HO | 2020-10-01 15:09:00 | 2020-10-01 14:56:00 | Done | Windows | COU -067-LC20_BOX.xlsm;\\10.49.1.97\ev\⑮ HOME\(6)COU;Original Directory;Yes;Accidental deletion of data. | 2020-10-01 15:28:00 | 2020-10-01 00:00:00 | 2020-10-01 15:28:00 | admin.Nancy O. Gendive | 0 | Ahead of Time
IC-1535-20 | CSR-0795-20 | Sharlon J. Gatchalian | WHD2 | HO | 2020-10-02 13:00:00 | 2020-10-05 21:00:00 | Done | Backup CAE file/s | Request for additional CAE files in monthly backup | 2020-10-03 10:16:00 | 2020-10-03 00:00:00 | 2020-10-05 07:14:00 | admin.Greg Daniel E. Mojica | -3.03 | Ahead of Time
IC-1536-20 | CSR-0797-20 | Marie Rose A. Farala | EI | HO | 2020-10-02 15:41:00 | 2020-10-05 21:00:00 | Done | PC Configuration | We would like to request for Remote Desktop Connection. Name - Louie Sablay ID No - 1872 Kindly add him in the following IP addresses, so he can access MATLAB in these PCs. 10.49.3.15 10.49.3.151 10.49.1.152 Thank you. | 2020-10-05 13:04:00 | 2020-10-05 00:00:00 | 2020-10-05 15:06:00 | admin.Nancy O. Gendive | 2.03 | Delay
IC-1537-20 | CSR-0829-20 | John Elly C. Javier | EV-CE | HO | 2020-10-02 17:12:00 | 2021-01-01 21:00:00 | Work in Progress | Hardware Purchase | Requesting to purchase 2 CPU, CE have budget for 2 for the month of July Requirements. Intel R Core i5-9500, 1TB SSD M.2 NVME PCIe, 12GB DDR4 2666DIMM, Win 10 Pro 64 and with MS Office. | 2020-10-29 13:01:00 | 2020-10-12 00:00:00 | 0000-00-00 00:00:00 | admin.Reymark B. Evangelista
IC-1538-20 | CSR-0831-20 | Ernesto L. Basbas | SCD | HO | 2020-10-04 10:26:00 | 2020-10-06 21:00:00 | Assigned | Borrow | May I request for update of my laptop (10.49.2.81) from windows 7 to windows 10. thank you | 0000-00-00 00:00:00 | 2020-10-12 00:00:00 | 0000-00-00 00:00:00 | admin.Emiliano P. Mendoza
IC-1539-20 | CSR-0821-20 | Ronalyn G. Imana | SCD | HO | 2020-10-05 09:33:00 | 2020-10-14 21:00:00 | Done | Access Request | FOR SOFTWARE Request of Temporary Access for Noime Balleser (pet19484) in Software Evaluation same access as Jessa Juarez (pet1964) FOLDERS \\10.49.1.97\ei\25 MBD \\10.49.1.97\ei\31 ECI→PET\ECI→PET(SOFTWARE) \\10.49.1.97\ei\32 PET→ECI\PET→ECI(SOFTWARE) | 2020-10-09 07:25:00 | 2020-10-08 00:00:00 | 2020-10-09 07:26:00 | admin.Reymark B. Evangelista | 0.02 | Ahead of Time
IC-1541-20 | CSR-0796-20 | Emerson Simon V. Prado | CON | HO | 2020-10-05 09:43:00 | 2020-10-14 21:00:00 | Done | Account Request | Reset Password for E-mail | 2020-10-05 12:41:00 | 2020-10-05 00:00:00 | 2020-10-06 15:51:00 | admin.Nancy O. Gendive | 18.17 | Delay
IC-1542-20 | CSR-0843-20 | Samuel F. Samson | PRT | HO | 2020-10-05 16:04:00 | 2020-10-12 15:50:00 | Done | Access Request | To use while WFH. (Remote Desktop connection for 10.49.2.146) | 2020-10-15 07:17:00 | 2020-10-12 00:00:00 | 2020-10-15 07:17:00 | admin.Reymark B. Evangelista | 0 | Ahead of Time
IC-1543-20 | CSR-0809-20 | Reymark B. Evangelista | MIS | HO | 2020-10-05 17:01:00 | 2021-01-04 21:00:00 | Work in Progress | Hardware Purchase | ORICO 6629US3-C-V1-US-BK USB3.0 to SATA Dual Bay External Hard Drive Docking Station for 2.5 or 3.5 inch HDD, SSD with Hard Drive. For Troubleshooting Purposes and for file transfer peer to peer HDD/SSD | 2020-10-12 11:16:00 | 2020-10-08 00:00:00 | 0000-00-00 00:00:00 | admin.Reymark B. Evangelista
IC-1545-20 | DRR-0099-20 | Roda A. Dela Pena | WHD2 | HO | 2020-10-06 07:37:00 | 2020-10-06 07:23:00 | Done | Cae | PD_82171-12W70K-00000;/export/home/eucoodb/model/work/TBU/02_A2/840W/82171/8217112W70K/00000 ;Original Directory;Yes;It was deleted unintentionally. | 2020-10-19 08:10:00 | 2020-10-10 00:00:00 | 2020-10-19 08:11:00 | admin.Greg Daniel E. Mojica | 0.02 | Ahead of Time
IC-1546-20 | DRR-0098-20 | Czarina D. Soliven | WHD2 | HO | 2020-10-06 08:05:00 | 2020-10-06 07:52:00 | Done | Cae | AP_3606961L00-40000 or AP_PET-3606961L00-40000 AP_3605965JA1-70000 or AP_PET-3605965JA1-70000;/export/home/eucoodb/model/repository/SZK/SZK-WSZ OR /export/home/eucoodb/model/work/SZK/SZK-WSZ ;/export/home/eucoodb/model/repository/SZK/SZK-WSZ/PETDWG/recovered;;Customer request | 2020-10-19 08:07:00 | 2020-10-10 00:00:00 | 2020-10-19 08:09:00 | admin.Greg Daniel E. Mojica | 0.03 | Ahead of Time
IC-1547-20 | DRR-0097-20 | Ayen G Panganiban | EV | HO | 2020-10-06 08:20:00 | 2020-10-06 08:07:00 | Done | Windows | 1_PUSH PULL JIG;Z:\⑤ JOB ORDERS\EV CONN\⑩OCTOBER 2020\XXX\EVTC-2009008_TCE_WAKATSUKI SAN_JIG\5 WORKING DATA\20200930_PUSH PULL JIG FULL ASSY;Original Directory;Yes;corrupted file | 2020-10-09 12:21:00 | 2020-10-08 00:00:00 | 2020-10-09 12:52:00 | admin.Reymark B. Evangelista | 0.52 | Ahead of Time
IC-1548-20 | CSR-0813-20 | John Paul P. Fabro | EV-CE | HO | 2020-10-06 08:51:00 | 2020-10-15 21:00:00 | Done | Access Request | Need to reset password user log in pet1750 | 2020-10-08 11:22:00 | 2020-10-08 00:00:00 | 2020-10-08 11:23:00 | admin.Nancy O. Gendive | 0.02 | Ahead of Time
IC-1550-20 | CSR-0833-20 | Danevie Alvarez | ADM | HO | 2020-10-06 10:30:00 | 2020-10-07 21:00:00 | Work in Progress | Download | No report generated on call accounting system | 2020-10-15 12:23:00 | 2020-10-12 00:00:00 | 0000-00-00 00:00:00 | admin.Joel Eduardo D. Ocampo
IC-1552-20 | CSR-0824-20 | Jennifer Joy D. Naputo | WHD3 | HO | 2020-10-06 11:50:00 | 2020-10-07 21:00:00 | Done | Install Software | Please install sharing EXTES. ( 3 computers ) 1. IP Address - 10.49.1.67 - 10.49.2.245 (Note) Host EXTES - 10.49.5.217 2. IP Address - 10.49.2.187 (Note) Host EXTES - 10.49.5.234 | 2020-10-12 11:17:00 | 2020-10-09 00:00:00 | 2020-10-12 11:18:00 | admin.Kiel S. Antaran | 0.02 | Ahead of Time
IC-1551-20 | CSR-0804-20 | Vicente Z. Nieto | WHE | HO | 2020-10-06 12:06:00 | 2020-10-15 21:00:00 | Done | Access Request | VPN access for Troy George dela Cruz (pet1334) | 2020-10-06 12:45:00 | 2020-10-06 00:00:00 | 2020-10-06 12:46:00 | admin.Emiliano P. Mendoza | 0.02 | Ahead of Time
IC-1553-20 | CSR-0823-20 | Lariza R. Calara | EA | HO | 2020-10-06 12:09:00 | 2020-10-09 21:00:00 | Done | Backup to CD/DVD | transfer files of 77th folder only from server \\10.49.1.97\iso\KPM\1. PET POLICY\ and 76-77th folder only from Local D (\\10.49.5.7) to DVD | 2020-10-10 09:02:00 | 2020-10-09 00:00:00 | 2020-10-10 15:05:00 | admin.Nancy O. Gendive | 6.05 | Delay
IC-1556-20 | CPR-0092-20 | Brandon Alan N. Docdocil | WHD1 | HO | 2020-10-06 15:26:00 | 2020-10-06 15:12:00 | Work in Progress | Operating System | Unable to start windows 10 due to maybe power supply problem or others. countermeasure reformat or replace CPU(if defective) | 2020-11-19 16:28:00 | 2020-10-12 00:00:00 | 0000-00-00 00:00:00 | admin.Reymark B. Evangelista
IC-1557-20 | CSR-0811-20 | Efleda T. Medina | FIN | HO | 2020-10-06 15:33:00 | 2020-10-15 21:00:00 | Done | Account Request | Request for Windows Log-In and E-mail address for newly hired employee Ms. Leny G. Maleno - Fin Specialist | 2020-10-08 10:45:00 | 2020-10-08 00:00:00 | 2020-10-10 10:51:00 | admin.Nancy O. Gendive | 30.1 | Delay
IC-1558-20 | CSR-0822-20 | Efleda T. Medina | FIN | HO | 2020-10-06 15:39:00 | 2020-10-15 21:00:00 | Done | Access Request | Access Request for our newly hired employee Ms. Leny G. Maleno-Fin Specialist (Same access right with Ms. Efleda Medina) | 2020-10-23 07:32:00 | 2020-10-08 00:00:00 | 2020-10-23 07:33:00 | admin.Joe Nico T. Geronimo | 0.02 | Ahead of Time
IC-1559-20 | CPR-0087-20 | Dominic O. Meomeo | WHD3 | HO | 2020-10-06 15:41:00 | 2020-10-06 15:28:00 | Done | IP Phone | Please change the Name of Telephone Number 705 from Arlie Pida to Dominic Meomeo | 2020-10-09 07:02:00 | 2020-10-08 00:00:00 | 2020-10-14 13:30:00 | admin.Joel Eduardo D. Ocampo | 88.03 | Delay
IC-1563-20 | CSR-0827-20 | Dominic O. Meomeo | WHD3 | HO | 2020-10-07 08:42:00 | 2020-10-08 21:00:00 | Done | Modify Software | We cannot use the Foxit software since our computers were upgraded to Windows 10. Foxit was installed in following IP address 10.49.2.207 10.49.2.124 10.49.3.17 10.49.2.140 10.49.1.149 | 2020-10-12 06:42:00 | 2020-10-10 00:00:00 | 2020-10-14 13:30:00 | admin.Joel Eduardo D. Ocampo | 36.8 | Delay
IC-1564-20 | CSR-0810-20 | Ruby A. Maghilum | EA | HO | 2020-10-07 09:25:00 | 2020-10-09 21:00:00 | Done | Backup to CD/DVD | Request to delete/dispose COACH Data back-up files including other Yazaki Affiliates from DVD # 48,49,50 & 51 (June 15, 2017 - December 27, 2017). see attached approved documented information disposal approval form | 2020-10-08 10:37:00 | 2020-10-08 00:00:00 | 2020-10-08 10:38:00 | admin.Nancy O. Gendive | 0.02 | Ahead of Time
IC-1569-20 | QA-0374-20 | Ernesto L. Basbas | SCD | HO | 2020-10-07 12:10:00 | 2020-10-07 12:10:00 | Closed |  | unable to print on printer, printer cannot detect changes on paper | 2020-10-07 12:10:00 | 2020-10-07 12:10:00 | 2020-10-07 12:16:00 | admin.Willem R. Leonardo | 0.1 | Ahead of Time
IC-1571-20 | CSR-0853-20 | Jovielet B. Caintoy | EDSD | HO | 2020-10-07 13:21:00 | 2020-10-16 21:00:00 | Done | Account Request | Request for deletion of windows log-in and Seine 2 account of resigned employee | 2020-10-16 09:14:00 | 2020-10-16 00:00:00 | 2020-10-22 13:19:00 | admin.Nancy O. Gendive | 64.08 | Delay
IC-1572-20 | CSR-0826-20 | Redemptor C. Batiduan | PRT | HO | 2020-10-07 17:10:00 | 2020-11-18 21:00:00 | Closed | Renewal License | Cadra License w/ Raster Option Renewal Date: November 2020 – November 2021 IP address: 10.49.5.125 Host ID: 9-7E6B2689 | 2020-10-12 11:17:00 | 2020-10-10 00:00:00 | 2020-12-03 14:36:00 | admin.Kiel S. Antaran | 573.32
IC-1573-20 | CSR-0840-20 | Donn M. Carlos | WHD1 | HO | 2020-10-08 08:02:00 | 2020-11-19 21:00:00 | Closed | Renewal License | CADRA renewal 10.49.2.161 (Honda) / 10.49.2.231 (Honda) / 10.49.1.83 (PTM) 10.49.1.121 (PTM) / 10.49.2.77 (PTM) | 2020-10-12 12:22:00 | 2020-10-12 00:00:00 | 2020-12-01 08:28:00 | admin.Kiel S. Antaran | 536.1
IC-1574-20 | CSR-0839-20 | Ronalyn G. Imana | SCD | HO | 2020-10-08 08:49:00 | 2020-10-12 08:36:00 | Assigned | Laptop Configuration | FOR SIR EDWIN Request for update of Sir Edwin's Laptop (10.49.2.14) from Windows 7 to Windows 10. Thank you. | 0000-00-00 00:00:00 | 2020-10-12 00:00:00 | 0000-00-00 00:00:00 | admin.Emiliano P. Mendoza
IC-1575-20 | CPR-0107-20 | Bryan Allan B. Ching | EV | HO | 2020-10-08 08:55:00 | 2020-10-08 08:30:00 | Assigned | WS Video Card | VGA Cable loose wire.(Insufficient wire length) | 0000-00-00 00:00:00 | 2020-11-17 00:00:00 | 0000-00-00 00:00:00 | admin.Nancy O. Gendive
IC-1577-20 | CPR-0089-20 | Carmelo C. Malagayo | TCE | HO | 2020-10-08 10:17:00 | 2020-10-08 10:04:00 | Done | PC Harddisk | Need replace CPU and no lan connection. cpu already repair but still not working.. | 2020-10-09 11:59:00 | 2020-10-09 00:00:00 | 2020-10-10 15:02:00 | admin.Reymark B. Evangelista | 34.97 | Delay
IC-1579-20 | CSR-0842-20 | Aumer A. Velasquez | WHD1 | HO | 2020-10-08 13:26:00 | 2020-10-09 21:00:00 | Work in Progress | Install Software | Good day, we would like to request for an investigation on my cadra. Our customer encountered problem when they access the file. Root cause. The Cadra setting always resets. File cannot be read into older version. Please see attached video for the details. Thank you very much. | 2020-10-20 07:04:00 | 2020-10-12 00:00:00 | 0000-00-00 00:00:00 | admin.Christ John M. Dela Cruz
IC-1581-20 | CSR-0837-20 | Melissa R. Talabong | FIN | HO | 2020-10-08 14:28:00 | 2020-10-09 21:00:00 | Done | Borrow | Borrow 2 pcs desktop 21 inches monitor to replace 14 inches monitor. | 2020-10-12 08:26:00 | 2020-10-12 00:00:00 | 2020-10-12 08:27:00 | admin.Reymark B. Evangelista | 0.02 | Ahead of Time
IC-1587-20 | CSR-0835-20 | Efleda T. Medina | FIN | HO | 2020-10-08 16:08:00 | 2020-10-19 21:00:00 | Done | Account Request | Account request for Ms. Leny Moleno on Navision | 2020-10-19 11:14:00 | 2020-10-12 00:00:00 | 2020-10-19 11:14:00 | admin.Joel Eduardo D. Ocampo | 0 | Ahead of Time
IC-1588-20 | CSR-0899-20 | Karmalou Sasaki | FIN | HO | 2020-10-09 10:49:00 | 2021-01-08 21:00:00 | Work in Progress | Hardware Purchase | Purchase of Laptop HP IDS DSC MX250 2GB i5-10210U440G7BNBPC | 2020-11-09 12:57:00 | 2020-11-04 00:00:00 | 0000-00-00 00:00:00 | admin.Reymark B. Evangelista
IC-1589-20 | CPR-0090-20 | Emmanuel Jr. C. Jimenez | CON | HO | 2020-10-09 10:54:00 | 2020-10-09 10:41:00 | Work in Progress | PC Harddisk | PC running slow after upgrading from Windows 7 to Windows 10 | 2020-10-15 12:25:00 | 2020-10-12 00:00:00 | 0000-00-00 00:00:00 | admin.Joel Eduardo D. Ocampo
IC-1590-20 | CSR-0830-20 | Emmanuel Jr. C. Jimenez | CON | HO | 2020-10-09 11:36:00 | 2020-10-12 21:00:00 | Done | Borrow | Request for temporary PC unit for PC station due to defective PC Unit after upgrading from windows 7 to windows 10 | 2020-10-14 06:51:00 | 2020-10-12 00:00:00 | 2020-10-15 12:22:00 | admin.Joel Eduardo D. Ocampo | 20.52 | Delay
IC-1591-20 | CSR-0832-20 | Johanna Marie C. Dandan | SCD | HO | 2020-10-09 13:21:00 | 2020-11-20 21:00:00 | Done | Renewal License | Request for CAD, Hyper Works - Hyper Mesh Renewal IP 10.49.1.189 Budget Category = Software usage Others Budget Month = October 2020 Budget Amount = Php 701,309.70 | 2020-10-13 15:11:00 | 2020-10-12 00:00:00 | 2020-11-27 20:56:00 | admin.Jasper Labenia
IC-1592-20 | CSR-0825-20 | Johanna Marie C. Dandan | SCD | HO | 2020-10-09 13:30:00 | 2020-11-20 21:00:00 | Done | Renewal License | FOR PRT Request for Software Usage YC 1. WH Development and Design Support Tool by TBU, For PRT -July Budget PhP 51,352.83 2. TABAQ [Wire bundle Diameter Calculation Software] -July Budget PhP 110,407.50 Please note for TABAQ, PRT will only renew 3 Licenses. see below IP address for your reference. IP Address 1.) 10.49.1.234 2.) 10.49.1.189 3.) 10.49.5.119 | 2020-10-15 19:21:00 | 2020-10-10 00:00:00 | 2020-11-09 16:36:00 | admin.Jasper Labenia
IC-1593-20 | CSR-0854-20 | Jovielet B. Caintoy | EDSD | HO | 2020-10-12 07:32:00 | 2020-10-21 21:00:00 | Done | Access Request | Request for additional folder access right for Arlie Pida | 2020-10-20 13:33:00 | 2020-10-16 00:00:00 | 2020-10-20 13:33:00 | admin.Reymark B. Evangelista | 0 | Ahead of Time
IC-1594-20 | CPR-0093-20 | Harold B. Balanay | JBRB | HO | 2020-10-12 08:42:00 | 2020-10-12 08:28:00 | Assigned | Mouse | Mouse does not function properly. | 0000-00-00 00:00:00 | 2020-10-12 00:00:00 | 0000-00-00 00:00:00 | admin.Nancy O. Gendive
IC-1595-20 | CSR-0866-20 | Ma. Reina Monserrat A. Abalos | WHD2 | HO | 2020-10-12 09:06:00 | 2020-10-13 21:00:00 | Work in Progress | Install Software | transfer VCAD from 10.49.1.115 to 10.49.2.248 | 2020-10-22 13:49:00 | 2020-10-20 00:00:00 | 0000-00-00 00:00:00 | admin.Jasper Labenia
IC-1596-20 | CSR-0856-20 | Jovielet B. Caintoy | EDSD | HO | 2020-10-12 09:14:00 | 2020-10-21 21:00:00 | Done | Access Request | Request to edit folder access right of transferred members. 1. Rudy Obina 2. Raffy Ubaldo 3. Zarah Jane Garcia 4. Aprilyn Cupino | 2020-10-20 13:54:00 | 2020-10-16 00:00:00 | 2020-10-20 14:00:00 | admin.Reymark B. Evangelista | 0.1 | Ahead of Time
IC-1597-20 | CSR-0841-20 | Alfie I. Villamor | WHD1 | HO | 2020-10-12 09:58:00 | 2021-01-11 21:00:00 | Done | Hardware Purchase | Replacement for mouse, due to defective. Difficult to click (left click). | 2020-10-14 13:25:00 | 2020-10-12 00:00:00 | 2020-10-14 13:26:00 | admin.Joel Eduardo D. Ocampo
IC-1598-20 | CSR-0845-20 | Belinda C. Cabico | WHE | HO | 2020-10-12 13:45:00 | 2020-11-23 21:00:00 | Done | Renewal License | Catia License Renewal, Product: Mechanical Design 2 Target ID: ZTC-42A71C528251E78A . Budget: November | 2020-10-13 16:45:00 | 2020-10-13 00:00:00 | 2020-12-02 16:36:00 | admin.Jasper Labenia
IC-1600-20 | CSR-0868-20 | Ma. Reina Monserrat A. Abalos | WHD2 | HO | 2020-10-12 15:04:00 | 2020-11-23 21:00:00 | Closed | Renewal License | CADRA license renewal 10.49.2.156 (9-3294F113) | 2020-10-22 09:53:00 | 2020-10-21 00:00:00 | 2020-12-08 11:05:00 | admin.Kiel S. Antaran | 496.2
IC-1602-20 | CSR-0846-20 | Alvin O. Ramirez | TCE | HO | 2020-10-13 08:37:00 | 2020-10-14 21:00:00 | Work in Progress | Install Software | need to install menseki and initial cross-section camera set-up CS05W | 2020-11-19 13:42:00 | 2020-10-13 00:00:00 | 0000-00-00 00:00:00 | admin.Joel Eduardo D. Ocampo
IC-1604-20 | CSR-0848-20 | Emmanuel Jr. C. Jimenez | CON | HO | 2020-10-13 13:20:00 | 2020-10-14 21:00:00 | Done | Modify Software | Transfer of Microsoft lync from 10.49.3.239 to 10.49.5.145 | 2020-10-15 11:54:00 | 2020-10-14 00:00:00 | 2020-10-15 12:06:00 | admin.Nancy O. Gendive | 0.2 | Ahead of Time
IC-1605-20 | CSR-0850-20 | Roxyanne Grace R. Garcia | CON | HO | 2020-10-13 15:53:00 | 2020-10-15 21:00:00 | Assigned | Install Software | Install/Repair the following software 1. Total Commander 2. Microsoft Office Document Imaging(MODI) 3. The add-ons to show CMMS homepage. 4. E-drawings (SW 2018 compatible) Thank you. | 0000-00-00 00:00:00 | 2020-10-15 00:00:00 | 0000-00-00 00:00:00 | admin.Nancy O. Gendive
IC-1607-20 | CSR-0855-20 | Jovielet B. Caintoy | EDSD | HO | 2020-10-14 07:21:00 | 2020-10-23 21:00:00 | Done | Access Request | Request to edit folder access right of Jerald Dizon | 2020-10-22 14:07:00 | 2020-10-16 00:00:00 | 2020-10-22 14:08:00 | admin.Reymark B. Evangelista | 0.02 | Ahead of Time
IC-1608-20 | QA-0375-20 | Belinda C. Cabico | WHE | HO | 2020-10-14 09:00:00 | 2020-10-14 09:00:00 | Closed |  | no ms visio found on the pc, upon checking on software list software is installed | 2020-10-14 09:00:00 | 2020-10-14 09:00:00 | 2020-10-14 09:12:00 | admin.Willem R. Leonardo | 0.2 | Ahead of Time
IC-1609-20 | CPR-0094-20 | Emmanuel Jr. C. Jimenez | CON | HO | 2020-10-14 10:14:00 | 2020-10-14 10:01:00 | Done | Monitor | Black spots in the Screen of the monitor | 2020-10-15 19:52:00 | 2020-10-14 00:00:00 | 2020-10-19 14:40:00 | admin.Jasper Labenia | 49.65 | Delay
IC-1611-20 | CSR-0851-20 | Roxyanne Grace R. Garcia | CON | HO | 2020-10-14 10:39:00 | 2021-01-13 21:00:00 | Work in Progress | Hardware Purchase | Solidworks Hardware Renewal for -10.49.1.29 -10.49.1.93 Reason: Replacement of Hardware for the CAD system for parts design corresponding to the customer's CAD requirements. CIP(EP) No. 2020/7-12 #13 Thank you. | 2020-10-22 14:09:00 | 2020-10-15 00:00:00 | 0000-00-00 00:00:00 | admin.Reymark B. Evangelista
IC-1612-20 | CSR-0999-20 | Gretchen C. Magsino | WHD1 | HO | 2020-10-14 13:31:00 | 2020-10-23 21:00:00 | Done | Access Request | Access right for GL and SV only | 2020-12-09 14:38:00 | 2020-12-09 00:00:00 | 2020-12-09 14:51:00 | admin.Reymark B. Evangelista | 0.22 | Ahead of Time
IC-1613-20 | CSR-0849-20 | admin.Emiliano P. Mendoza | MIS | HO | 2020-10-14 16:48:00 | 2020-10-15 21:00:00 | Done | Install Software | Microsoft Windows Server 2016 On Call Support for File Server Migration by Phildata | 2020-10-14 16:53:00 | 2020-10-14 00:00:00 | 2020-11-16 10:05:00 | admin.Nancy O. Gendive | 338.2 | Delay