## Worksheet
HO August 2021
| New Request | Assigned | Work in Progress | Completed | Count | Complete Percentage
CSR | 0 | 3 | 5 | 94 | 102 | 92
CPR | 0 | 0 | 0 | 7 | 7 | 100
DRR | 0 | 0 | 0 | 5 | 5 | 100
QA | N/A | N/A | N/A | 20 | 20 | 100
Members with Request and Status count info
Name | Assigned | Work in Progress | Done | Closed | Total
admin.Aaron Jet N. Sarreal | 0 | 0 | 1 | 0 | 1
admin.admin.Reymark B. Evangelista | 0 | 0 | 0 | 19 | 19
admin.Bryan Mar R. Alvarez | 0 | 0 | 6 | 5 | 11
admin.Elmo A. Daquila JR. | 0 | 0 | 1 | 0 | 1
admin.Jasper Labenia | 0 | 0 | 2 | 0 | 2
admin.Joel Eduardo D. Ocampo | 1 | 0 | 0 | 0 | 1
admin.Kaiser Ralph H. Roca | 0 | 0 | 0 | 3 | 3
admin.Kevin Neil A. Mapa | 0 | 0 | 32 | 0 | 32
admin.Nancy O. Gendive | 1 | 1 | 21 | 0 | 23
admin.Reymark B. Evangelista | 0 | 0 | 13 | 1 | 14
admin.Ruby A. Maghilum | 1 | 4 | 21 | 0 | 26
admin.Shiela Marie N. Arceo | 0 | 0 | 1 | 0 | 1
Total |  |  |  |  | 134
Request Details
IC No. | Reference No. | Requestor | Department | Site | Request date | Request needed/occur | Status | Request | Details | Acknowledge Date | Date Receive | Date Done | In Charge | Man Hour | Response
IC-1397-21 | CSR-0917-21 | Sheila Mae E. Espora | WHD3 | HO | 2021-07-16 09:26:00 | 2021-07-19 21:00:00 | Closed | Install Software | share extes from 10.49.5.137 to 10.49.3.21 | 2021-07-16 13:46:00 | 2021-07-16 00:00:00 | 2021-07-19 14:26:00 | admin.Kaiser Ralph H. Roca | 15.67
IC-1398-21 | DRR-0113-21 | Anna Love A. Guevarra | TCE | HO | 2021-07-16 09:44:00 | 2021-07-16 09:44:00 | Done | Windows | ➃ ASEAN Affiliates TCSS Monitoring;\\10.49.1.97\tced\07 TCE TCSS Registration\TCSS Monitoring;Original Directory;Yes;Wrong save as document. Kindly recover file last saved July 15,2021. | 2021-07-16 11:17:00 | 2021-07-16 00:00:00 | 2021-07-20 07:39:00 | admin.Ruby A. Maghilum
IC-1399-21 | CSR-0918-21 | Jayson L. Toding | WHD2 | HO | 2021-07-16 10:15:00 | 2021-07-19 21:00:00 | Done | Borrow | Reason - Work from home (Michelle Marasigan) HP (CPU) Model Name - HPPRODESKG4SFF Serial No.- SGH737R45H HP (Monitor) Model Name - HPPRODESKG4SFF Serial No. - CNK7321PXO | 2021-07-16 16:44:00 | 2021-07-16 00:00:00 | 2021-07-16 16:48:00 | admin.Kevin Neil A. Mapa
IC-1400-21 | CSR-0916-21 | Jayson L. Toding | WHD2 | HO | 2021-07-16 10:23:00 | 2021-07-19 21:00:00 | Done | Borrow | Reason - Work from home (Clarice Jandayan) HP (CPU) Model Name - HPPRODESKG3SFF Serial No. - SGH822TVRY HP (Monitor) Model Name - HPPRODISPLAY Serial No. - CNK81829FS | 2021-07-16 14:32:00 | 2021-07-16 00:00:00 | 2021-07-16 15:23:00 | admin.Kevin Neil A. Mapa
IC-1401-21 | CSR-0941-21 | Norberto Jr. N. Bustarga | WHE | HO | 2021-07-16 11:56:00 | 2021-07-19 21:00:00 | Done | Borrow | Borrow PC for Nikee Ibarrientos. HP Pro desk 400 CPU (IP 10.49.2.63) HP Monitor and HP Mouse | 2021-07-28 13:06:00 | 2021-07-28 00:00:00 | 2021-07-28 13:06:00 | admin.Kevin Neil A. Mapa
IC-1407-21 | CSR-0926-21 | Joan M. Fortuna | EV-CE | HO | 2021-07-19 09:38:00 | 2021-07-28 21:00:00 | Done | Account Request | Request Email for Jeffrey Huagan | 2021-07-23 08:20:00 | 2021-07-23 00:00:00 | 2021-07-23 11:44:00 | admin.Nancy O. Gendive
IC-1409-21 | CSR-0924-21 | admin.Emiliano P. Mendoza | MIS | HO | 2021-07-19 11:54:00 | 2021-07-20 21:00:00 | Done | Hardware Purchase | Jabra headset purchase for MIS - replacement of defective and for other department borrowing | 2021-07-19 12:00:00 | 2021-07-19 00:00:00 | 2021-10-15 07:57:00 | admin.Nancy O. Gendive
IC-1410-21 | CSR-0947-21 | Michael Angelo H. Escalona | WHE | HO | 2021-07-19 15:15:00 | 2021-07-28 21:00:00 | Work in Progress | Account Request | 1 TBU member resigned | 2021-11-02 11:46:00 | 2021-07-28 00:00:00 | 0000-00-00 00:00:00 | admin.Ruby A. Maghilum
IC-1412-21 | CSR-0930-21 | Redemptor C. Batiduan | PRT | HO | 2021-07-19 16:26:00 | 2021-07-20 21:00:00 | Done | Borrow | Request of VPN activation on PC 10.49.5.125 for WFH of Jairo Ruben Perez (pet2015). | 2021-07-26 17:32:00 | 2021-07-26 00:00:00 | 2021-07-26 18:12:00 | admin.Kevin Neil A. Mapa
IC-1413-21 | CSR-0939-21 | Evangeline T. Quilloy | WHD3 | HO | 2021-07-21 07:42:00 | 2021-07-22 21:00:00 | Done | Folder Creation | RENAME FOLDER FORD-YTMI-CHRYSLER to FORD-YTMI-STELLANTIS in 10.49.1.97 WH. | 2021-07-28 13:45:00 | 2021-07-28 00:00:00 | 2021-07-28 15:14:00 | admin.Kevin Neil A. Mapa
IC-1414-21 | CSR-0940-21 | Mary Kathleen D. Brotonel | WHD3 | HO | 2021-07-21 14:29:00 | 2021-07-22 21:00:00 | Done | Borrow | Request for VPN access for Cecil Morales to be used during Work from Home | 2021-07-28 13:05:00 | 2021-07-28 00:00:00 | 2021-07-28 13:06:00 | admin.Kevin Neil A. Mapa
IC-1415-21 | CSR-0988-21 | Mary Joy L. De Belen | EDSD | HO | 2021-07-22 08:34:00 | 2021-09-02 21:00:00 | Done | Renewal License | KD Converter Renewal Subscription BUDGET MONTH DEPARTMENT GROUP IP ADDRESS Host ID September WHDS WHDS 10.49.1.50 HPTOPST September WHDS WHDS 10.49.1.50 C73RS | 2021-08-04 11:15:00 | 2021-08-04 00:00:00 | 2021-09-01 14:41:00 | admin.Jasper Labenia
IC-1416-21 | CSR-0935-21 | Anna Liza E. Ilusorio | WHD3 | HO | 2021-07-22 08:43:00 | 2021-08-02 21:00:00 | Done | Account Request | E-mail account for Jerome Tamayo (whd3 Designer) Hino Group | 2021-07-27 12:57:00 | 2021-07-27 00:00:00 | 2021-07-28 11:52:00 | admin.Nancy O. Gendive
IC-1419-21 | CSR-0958-21 | Edvin B. Pantoni | EV | HO | 2021-07-22 10:06:00 | 2021-07-23 21:00:00 | Done | No Connection | Disconnection of Teams during meeting. Many member experienced this problem, so please investigate. | 2021-08-10 10:34:00 | 2021-07-29 00:00:00 | 2021-08-10 10:35:00 | admin.Ruby A. Maghilum
IC-1418-21 | CSR-0928-21 | Sharlon J. Gatchalian | WHD2 | HO | 2021-07-22 10:34:00 | 2021-08-02 21:00:00 | Done | Install Software | install PHP for HTML function. | 2021-07-30 12:07:00 | 2021-07-23 00:00:00 | 2021-07-30 12:09:00 | admin.Aaron Jet N. Sarreal
IC-1420-21 | CSR-0927-21 | April D. Dayapan | EI | HO | 2021-07-22 13:35:00 | 2021-09-02 21:00:00 | Done | Renewal License | (1) Adobe Photoshop Renewal - Php 25,000 FY81P_HO_SOFTWAREUSAGEOTHERS_MT_rev1 August 2021 Budget | 2021-07-28 06:51:00 | 2021-07-23 00:00:00 | 2021-11-05 10:55:00 | admin.Nancy O. Gendive
IC-1422-21 | CSR-0929-21 | April D. Dayapan | EI | HO | 2021-07-23 07:05:00 | 2021-07-26 21:00:00 | Done | Access Request | Request for remote access of 10.49.5.112 | 2021-07-23 10:37:00 | 2021-07-23 00:00:00 | 2021-07-23 10:37:00 | admin.Nancy O. Gendive
IC-1423-21 | CSR-0957-21 | Danevie Alvarez | ADM | HO | 2021-07-23 07:48:00 | 2021-10-22 21:00:00 | Done | Borrow | Replacement of Monitor | 2021-08-06 08:45:00 | 2021-07-29 00:00:00 | 2021-08-06 08:45:00 | admin.Nancy O. Gendive
IC-1424-21 | CSR-1118-21 | Judelyn E. Rosales | EA-TQM | HO | 2021-07-23 09:32:00 | 2021-07-30 21:00:00 | Assigned | Backup to CD/DVD | Transfer to DVD due to full storage capacity of ISO folder. 1. \\10.49.1.97\common\Common_Data\TQM_share\QMS_share data\For transfer to DVD\ 2. \\10.49.1.97\iso\KPM\1. PET POLICY\77th & 78th | 0000-00-00 00:00:00 | 2021-08-27 00:00:00 | 0000-00-00 00:00:00 | admin.Nancy O. Gendive
IC-1425-21 | CSR-0943-21 | Jonh Rolan D.R. Lucida | WHD3 | HO | 2021-07-23 09:43:00 | 2021-07-26 21:00:00 | Closed | Install Software | Transfer application from 10.49.5.13 to 10.49.3.191 Notepad++ Foxit Shared extes | 2021-07-28 08:45:00 | 2021-07-28 00:00:00 | 2021-09-27 09:32:00 | admin.Kaiser Ralph H. Roca | 630.78
IC-1426-21 | CSR-0953-21 | Arlie F. Pida | WHD2 | HO | 2021-07-23 15:27:00 | 2021-07-26 21:00:00 | Done | PC Configuration | Phone transfer from Yolanda Cinco to Arlie Pida (10.49.2.127) | 2021-08-06 08:08:00 | 2021-07-28 00:00:00 | 2021-08-06 08:17:00 | admin.Nancy O. Gendive
IC-1430-21 | DRR-0114-21 | Ma. Kristela T. Meomeo | EA-TQM | HO | 2021-07-26 10:32:00 | 2021-07-26 10:32:00 | Done | Windows | F-RAI-015 (Risk Register ( TQM ));\\10.49.1.97\common\Common_Data\Risk and Opportunity Management\Risk Register\Total Quality Management;Original Directory;No;edited unintentionally the file. recover file dated June 29, 2021 | 2021-07-26 15:22:00 | 2021-07-26 00:00:00 | 2021-07-26 15:52:00 | admin.Ruby A. Maghilum
IC-1432-21 | CSR-0944-21 | Norberto Jr. N. Bustarga | WHE | HO | 2021-07-26 12:15:00 | 2021-08-04 21:00:00 | Assigned | Access Request | Delete Access of Resigned members (WHE-IVS/MSC) (Please see attached file) 1. PET1823 - May Angeli Ramos 2. PET 2004- Neslie Borgonia Also, please please deactivated MHT account of May and Neslie. Thank you. | 0000-00-00 00:00:00 | 2021-07-28 00:00:00 | 0000-00-00 00:00:00 | admin.Ruby A. Maghilum
IC-1431-21 | CSR-0933-21 | Jovielet B. Caintoy | EDSD | HO | 2021-07-26 12:20:00 | 2021-08-04 21:00:00 | Done | Access Request | Request to add/delete folder access right. 1. Hare Krish Amaro 2. Roner Paguirigan 3. Belinda Cabico | 2021-07-26 17:21:00 | 2021-07-26 00:00:00 | 2021-08-20 13:16:00 | admin.Kevin Neil A. Mapa
IC-1452-21 | QA-0050-21 | Brad Randolph L. Litrero | JBRB | HO | 2021-07-27 02:04:00 | 2021-07-27 02:04:00 | Closed |  | Catia macro concern | 2021-07-27 02:04:00 | 2021-07-27 02:04:00 | 2021-07-27 02:30:00 | admin.admin.Reymark B. Evangelista | 0.43
IC-1433-21 | DRR-0117-21 | Catherine U. Bulalacao | WHD3 | HO | 2021-07-27 07:52:00 | 2021-07-27 07:52:00 | Closed | Cae | PD_24011TBC01JIS-00000.ModelRoot MD_24011TBC01JIS-00000.ModelRoot;/export/home/eucoodb/model/work/NSN/NSN_RNBU/NSN_SSN/2021/08_AUGUST/P13C_MEX_JISHUKEN/24011TBC01JISCHECKING/FINAL;Original Directory;No;for sending to RNBU | 2021-07-28 08:17:00 | 2021-07-27 00:00:00 | 2021-07-28 08:24:00 | admin.Kaiser Ralph H. Roca | 0.12
IC-1434-21 | CSR-0934-21 | Sharlon J. Gatchalian | WHD2 | HO | 2021-07-27 08:46:00 | 2021-07-28 21:00:00 | Done | Transfer PC location | 1. Transfer of PC location. 2. Transfer of Telephone location and change name (714, Yolanda cinco to Arlie Pida) Please refer attached. (Yellow part) | 2021-07-27 12:57:00 | 2021-07-27 00:00:00 | 2021-07-27 17:51:00 | admin.Kevin Neil A. Mapa
IC-1435-21 | CPR-0085-21 | Kean John M. Nanteza | CON | HO | 2021-07-27 10:26:00 | 2021-07-27 10:26:00 | Done | Monitor | Computer problem | 2021-07-27 12:01:00 | 2021-07-27 00:00:00 | 2021-07-30 07:31:00 | admin.Reymark B. Evangelista
IC-1437-21 | CSR-0999-21 | Emmanuel Jr. C. Jimenez | CON | HO | 2021-07-27 11:45:00 | 2021-07-28 21:00:00 | Done | Borrow | Lenovo G40-70(Laptop) 10.49.3.253 with installed VPN for WFH User Name Judy Ann Lagamson (PET1808) | 2021-08-10 09:43:00 | 2021-08-04 00:00:00 | 2021-08-10 09:46:00 | admin.Ruby A. Maghilum
IC-1438-21 | CSR-0948-21 | Annabelle L. Malonda | EI | HO | 2021-07-27 13:03:00 | 2021-07-28 21:00:00 | Done | PC Configuration | Install RAM to the following desktop PCs 16GB 10.49.3.151 10.49.3.153 8GB 10.49.1.129 10.49.1.145 | 2021-07-29 11:15:00 | 2021-07-28 00:00:00 | 2021-10-20 09:18:00 | admin.Reymark B. Evangelista
IC-1441-21 | CPR-0089-21 | Edvin B. Pantoni | EV | HO | 2021-07-27 14:14:00 | 2021-07-27 14:13:00 | Done | Operating System | After deletion of below file, the file was come back again automatically. Please delete permanently. \\10.49.1.97\ev\④ ORDER SHEET\01 Paper Ordersheet\CE21-PK-0359_A.pdf | 2021-07-29 12:20:00 | 2021-07-29 00:00:00 | 2021-07-31 15:40:00 | admin.Reymark B. Evangelista
IC-1442-21 | CPR-0088-21 | Edvin B. Pantoni | EV | HO | 2021-07-27 14:20:00 | 2021-07-28 14:19:00 | Done | Operating System | Before I have permission to the below location. \\10.49.1.97\ev\④ ORDER SHEET\01 Paper Ordersheet But now my access was lost. Please return my access. Please refer yo the attached sheet. | 2021-07-29 20:07:00 | 2021-07-29 00:00:00 | 2021-07-30 14:19:00 | admin.Kevin Neil A. Mapa
IC-1449-21 | CSR-0951-21 | Ronalyn G. Imana | SCD | HO | 2021-07-28 07:17:00 | 2021-08-06 21:00:00 | Work in Progress | Account Request | FOR HARDWARE Request for Windows account of new Hardware member Mr. Christopher N. Nova - pet2079 | 2021-07-28 11:20:00 | 2021-07-28 00:00:00 | 0000-00-00 00:00:00 | admin.Ruby A. Maghilum
IC-1450-21 | CSR-0950-21 | Ronalyn G. Imana | SCD | HO | 2021-07-28 07:22:00 | 2021-08-06 21:00:00 | Done | Access Request | FOR HARDWARE Request for folder access for Mr. Christopher N. Nova- pet2079. Please see attachment. | 2021-07-28 15:14:00 | 2021-07-28 00:00:00 | 2021-08-18 13:06:00 | admin.Kevin Neil A. Mapa
IC-1451-21 | CPR-0090-21 | Patrick B. Martinez | EV | HO | 2021-07-28 07:35:00 | 2021-07-28 07:34:00 | Done | Mouse | Mouse not working | 2021-08-09 23:42:00 | 2021-07-29 00:00:00 | 2021-08-09 23:42:00 | admin.Nancy O. Gendive
IC-1453-21 | CSR-0945-21 | admin.Emiliano P. Mendoza | MIS | HO | 2021-07-28 08:46:00 | 2021-07-29 21:00:00 | Done | Account Request | Uniform purchase for new regular employee - Kevin Mapa | 2021-07-28 09:08:00 | 2021-07-28 00:00:00 | 2021-08-10 16:33:00 | admin.Ruby A. Maghilum
IC-1457-21 | CSR-0954-21 | Benito H. Pitas | SCD | HO | 2021-07-28 13:02:00 | 2021-09-08 21:00:00 | Done | Renewal License | Request to renew tableau license in PC 10.49.2.185 | 2021-08-21 08:36:00 | 2021-07-28 00:00:00 | 2021-10-08 07:12:00 | admin.Nancy O. Gendive
IC-1458-21 | CSR-0959-21 | Princess Ellaine C. Malanao | ADM | HO | 2021-07-28 14:03:00 | 2021-08-20 21:00:00 | Done | Increase Capacity | PRIF preparation for Jabra Speak, 1 unit Budget Month - July 2021 Amount - P 8,000.00 | 2021-07-30 07:04:00 | 2021-07-29 00:00:00 | 2021-08-06 08:28:00 | admin.Nancy O. Gendive
IC-1459-21 | CSR-0956-21 | Princess Ellaine C. Malanao | ADM | HO | 2021-07-28 14:07:00 | 2021-08-20 21:00:00 | Done | Increase Capacity | PRIF preparation for DOT Matrix Printer, 1 unit Budget Month - July 2021 Amount - P 25000 | 2021-08-02 11:15:00 | 2021-07-29 00:00:00 | 2021-08-06 08:32:00 | admin.Nancy O. Gendive
IC-1460-21 | CSR-0972-21 | Robel P. Ganzon | WHD2 | HO | 2021-07-28 16:02:00 | 2021-07-29 21:00:00 | Done | Download | Please recover my personal file (my monitoring excel file) \\10.49.1.97\wh\TOYOTA\★CAE Related Documents\JOB RELATED FILES\MEMBERS FOLDER\BEBEL\Monitoring ok filename 2021 filename Tape checking Please recover latest / last save file | 2021-08-02 12:50:00 | 2021-08-02 00:00:00 | 2021-08-02 12:51:00 | admin.Kevin Neil A. Mapa
IC-1463-21 | CPR-0092-21 | Angelic M. Ong | CON | HO | 2021-07-29 08:20:00 | 2021-07-29 08:20:00 | Done | Mouse | The scroll wheel, left and right buttons is not functioning properly. | 2021-08-04 17:26:00 | 2021-08-04 00:00:00 | 2021-08-04 17:59:00 | admin.Kevin Neil A. Mapa
IC-1466-21 | CSR-0970-21 | Jovielet B. Caintoy | EDSD | HO | 2021-07-29 08:30:00 | 2021-08-09 21:00:00 | Closed | Access Request | Request for additional folder access right of Czarina Soliven in Toyota folder. | 2021-08-03 11:41:00 | 2021-08-02 00:00:00 | 2021-08-05 12:52:00 | admin.Bryan Mar R. Alvarez | 31.18
IC-1472-21 | CSR-0961-21 | Sharmaine T. Ingles | SCD | HO | 2021-07-29 09:26:00 | 2021-08-09 21:00:00 | Closed | Access Request | Access request for HO TCE Transferred Employees Testing Machine Operator 1. Anzu de Vera (ID No. 1866) & 2. Wendy Lyn Agnote (ID No. 2025) | 2021-07-29 13:06:00 | 2021-07-29 00:00:00 | 2021-08-24 07:41:00 | admin.Bryan Mar R. Alvarez | 264.58
IC-1473-21 | CSR-0962-21 | Sharmaine T. Ingles | SCD | HO | 2021-07-29 09:27:00 | 2021-08-09 21:00:00 | Closed | Account Request | Account & Access request for HO TCE New & Transferred Employees Maintenance and Facilities Engineer 1. Alexander C. Inocencio (ID No. 2075) Jr. Testing Evaluator 1. Paquito I. Conde Jr. (ID No. 2076) Testing Machine Operator 1. Joshua James Q. Aguilar (ID No. 2077), 2. Jobelle V. Lazaro (ID No. 2078) | 2021-07-29 11:51:00 | 2021-07-29 00:00:00 | 2021-08-24 07:42:00 | admin.Bryan Mar R. Alvarez | 265.85
IC-1477-21 | CSR-1000-21 | Emmanuel Jr. C. Jimenez | CON | HO | 2021-07-29 11:58:00 | 2021-07-30 21:00:00 | Done | PC Configuration | Configuration for Remote PC Set up for BO user. IP Address 10.49.2.177 User to add: Ariel Altamira(PET6104) | 2021-08-09 09:39:00 | 2021-08-04 00:00:00 | 2021-08-09 09:44:00 | admin.Elmo A. Daquila JR.
IC-1479-21 | CSR-0998-21 | Roxyanne Grace R. Garcia | CON | HO | 2021-07-29 16:50:00 | 2021-07-30 21:00:00 | Done | Borrow | Borrow PC and VPN installation for 1 Connector Member (PET0643 Melanie Crispino) HP Prodesk G4 SFF (SN. SGH822TVQS) (IP 10.49.2.67) | 2021-08-04 18:01:00 | 2021-08-04 00:00:00 | 2021-08-06 15:56:00 | admin.Kevin Neil A. Mapa
IC-1496-21 | QA-0059-21 | Jose V. Samson | EV | HO | 2021-07-30 06:43:00 | 2021-07-30 06:43:00 | Closed |  | Network/firewall connection inquiry | 2021-07-30 06:43:00 | 2021-07-30 06:43:00 | 2021-07-30 06:59:00 | admin.admin.Reymark B. Evangelista | 0.27
IC-1498-21 | QA-0060-21 | Jan Ruwiltton N. Tropicales | WHE | HO | 2021-07-30 07:15:00 | 2021-07-30 07:15:00 | Closed |  | CPU Check for Bring in form. | 2021-07-30 07:15:00 | 2021-07-30 07:15:00 | 2021-07-30 09:45:00 | admin.Reymark B. Evangelista | 2.5
IC-1480-21 | CSR-1210-21 | Romil S. Corminal | WHD1 | HO | 2021-07-30 07:39:00 | 2021-08-02 21:00:00 | Done | Install Software | 10.49.3.138 - MS Professional (Marylla Alvarez) transfer of microsoft LYNC | 2021-10-02 08:52:00 | 2021-09-17 00:00:00 | 2021-10-02 08:52:00 | admin.Ruby A. Maghilum
IC-1481-21 | CSR-0968-21 | Kristiel Joy B. Diaz | WHD2 | HO | 2021-07-30 07:58:00 | 2021-08-10 21:00:00 | Assigned | Access Request | Temporary or Permanent request for external DVD access for sending and checking back up files thru CD/ DVD | 0000-00-00 00:00:00 | 2021-08-02 00:00:00 | 0000-00-00 00:00:00 | admin.Joel Eduardo D. Ocampo
IC-1482-21 | CSR-0963-21 | Jorem R Alfredo | ADM | HO | 2021-07-30 08:02:00 | 2021-08-02 21:00:00 | Done | Install Software | FUJI XEROX SCANNER FILE READER | 2021-07-30 10:02:00 | 2021-07-30 00:00:00 | 2021-07-30 10:03:00 | admin.Reymark B. Evangelista
IC-1485-21 | CSR-0983-21 | Karmalou Sasaki | FIN | HO | 2021-07-30 08:28:00 | 2021-08-02 21:00:00 | Done | Borrow | One (1) Monitor for PC Set-up for Ms. Millie on 6th Floor Meeting Room 6A. | 2021-08-03 14:14:00 | 2021-08-03 00:00:00 | 2021-08-31 15:24:00 | admin.Kevin Neil A. Mapa
IC-1484-21 | CSR-0969-21 | Ma. Kristela T. Meomeo | EA-TQM | HO | 2021-07-30 08:38:00 | 2021-08-02 21:00:00 | Done | Backup to CD/DVD | transfer files from \\10.49.1.97\tqm\006 Training\003 EEDS\Reference Files (Batch 4 Files, Batch 5 Files & Batch 6 Files) to DVD. | 2021-08-09 16:06:00 | 2021-08-02 00:00:00 | 2021-08-09 16:18:00 | admin.Ruby A. Maghilum
IC-1500-21 | QA-0062-21 | Kristiel Joy B. Diaz | WHD2 | HO | 2021-07-30 09:20:00 | 2021-07-30 09:20:00 | Closed |  | .Lync/skype Concern transfer from pro to standard | 2021-07-30 09:20:00 | 2021-07-30 09:20:00 | 2021-07-30 09:31:00 | admin.admin.Reymark B. Evangelista | 0.18
IC-1487-21 | CSR-0967-21 | Maria Teresa C. Valentin | WHD2 | HO | 2021-07-30 09:40:00 | 2021-10-29 21:00:00 | Done | Hardware Purchase | We would like to request for the quotation of the below. 1) Jabra headset 2) Panasonic Telephone (for replacement) | 2021-07-31 14:22:00 | 2021-07-31 00:00:00 | 2021-08-11 06:27:00 | admin.Nancy O. Gendive
IC-1499-21 | QA-0061-21 | Kristiel Joy B. Diaz | WHD2 | HO | 2021-07-30 09:59:00 | 2021-07-30 09:59:00 | Closed |  | add remote access 10.49.2.98 | 2021-07-30 09:59:00 | 2021-07-30 09:59:00 | 2021-07-30 10:15:00 | admin.admin.Reymark B. Evangelista | 0.27
IC-1501-21 | QA-0063-21 | Jorem R Alfredo | ADM | HO | 2021-07-30 10:01:00 | 2021-07-30 10:01:00 | Closed |  | Fuji Xerox file reader inquiry and request to install | 2021-07-30 10:01:00 | 2021-07-30 10:01:00 | 2021-07-30 10:15:00 | admin.admin.Reymark B. Evangelista | 0.23
IC-1502-21 | QA-0064-21 | Jorem R Alfredo | ADM | HO | 2021-07-30 10:01:00 | 2021-07-30 10:01:00 | Closed |  | Fuji Xerox file reader inquiry and request to install | 2021-07-30 10:01:00 | 2021-07-30 10:01:00 | 2021-07-30 10:15:00 | admin.admin.Reymark B. Evangelista | 0.23
IC-1503-21 | QA-0065-21 | Marie Rose A. Farala | EI | HO | 2021-07-30 10:43:00 | 2021-07-30 10:43:00 | Closed |  | . Folder Access request Check | 2021-07-30 10:43:00 | 2021-07-30 10:43:00 | 2021-07-30 10:59:00 | admin.admin.Reymark B. Evangelista | 0.27
IC-1489-21 | CSR-0978-21 | Maria Teresa C. Valentin | WHD2 | HO | 2021-07-30 11:24:00 | 2021-09-10 21:00:00 | Work in Progress | Software Purchase | We would like to request for the quotation of KD viewer for WHD2 August budget(Suzuki). | 2021-08-03 08:29:00 | 2021-08-03 00:00:00 | 0000-00-00 00:00:00 | admin.Nancy O. Gendive
IC-1490-21 | CSR-0996-21 | Belinda C. Cabico | WHE | HO | 2021-07-30 12:26:00 | 2021-08-02 21:00:00 | Done | PC Configuration | Configure PC for WFH | 2021-08-04 18:01:00 | 2021-08-04 00:00:00 | 2021-08-06 15:56:00 | admin.Kevin Neil A. Mapa
IC-1491-21 | CSR-1022-21 | John Kendryl O. Fernandez | WHD2 | HO | 2021-07-30 12:52:00 | 2021-08-02 21:00:00 | Done | Install Software | please install MS Office 365, requirement for TBU's Macro tool | 2021-09-01 07:46:00 | 2021-08-07 00:00:00 | 2021-09-01 07:47:00 | admin.Bryan Mar R. Alvarez
IC-1504-21 | QA-0066-21 | Redemptor C. Batiduan | PRT | HO | 2021-07-30 14:03:00 | 2021-07-30 14:03:00 | Closed |  | Office 365 inquiry via call | 2021-07-30 14:03:00 | 2021-07-30 14:03:00 | 2021-07-30 14:20:00 | admin.admin.Reymark B. Evangelista | 0.28
IC-1505-21 | QA-0067-21 | Redemptor C. Batiduan | PRT | HO | 2021-07-30 14:03:00 | 2021-07-30 14:03:00 | Closed |  | Office 365 inquiry via call | 2021-07-30 14:03:00 | 2021-07-30 14:03:00 | 2021-07-30 14:20:00 | admin.admin.Reymark B. Evangelista | 0.28
IC-1492-21 | CSR-1019-21 | Jathniel I. Lopez | PRT | HO | 2021-07-30 14:13:00 | 2021-08-10 21:00:00 | Done | Access Request | Access and Account deletion for pet1953, Jason Odtuhan. Resigned employee. | 2021-08-06 14:03:00 | 2021-08-06 00:00:00 | 2021-10-08 07:12:00 | admin.Nancy O. Gendive
IC-1494-21 | CSR-0971-21 | Kristel Anne D. Villanueva | SCD | HO | 2021-07-30 14:58:00 | 2021-08-02 21:00:00 | Done | Folder Deletion | Delete old Meter/Mechanical Group Folders in HO and BO Server (since there is new Folder for Meter Dept.) \\10.49.1.97\ei\21 METER \\10.49.1.97\ei\22 SENSOR \\10.49.1.97\EI Archive\MECHANICAL \\10.49.128.7\ei_(branch)\21 METER GROUP \\10.49.128.7\ei_(branch)\22 SENSOR \\10.49.128.7\ei_(branch)_archive\MECHANICAL | 2021-08-02 12:49:00 | 2021-08-02 00:00:00 | 2021-08-03 20:49:00 | admin.Kevin Neil A. Mapa
IC-1507-21 | CSR-1212-21 | Merry Rose Chavez | WHD1 | HO | 2021-08-02 07:33:00 | 2021-08-03 21:00:00 | Done | Borrow | request for mouse replacement | 2021-09-17 16:39:00 | 2021-09-17 00:00:00 | 2021-09-17 16:40:00 | admin.Kevin Neil A. Mapa
IC-1508-21 | CSR-1016-21 | Kristiel Joy B. Diaz | WHD2 | HO | 2021-08-02 07:43:00 | 2021-08-04 07:42:00 | Done | Backup to CD/DVD | Please back up this link below for storage. IP desktop file - 10.49.3.121 (pet1109) Filename- moch | 2021-10-11 16:28:00 | 2021-08-06 00:00:00 | 2021-11-02 16:01:00 | admin.Ruby A. Maghilum
IC-1509-21 | CSR-0989-21 | Marcelo Jr. P. Santillan | WHE | HO | 2021-08-02 08:16:00 | 2021-08-03 21:00:00 | Done | Install Software | Install Microsoft Teams for online meetings with client | 2021-08-09 12:13:00 | 2021-08-04 00:00:00 | 2021-08-09 15:27:00 | admin.Ruby A. Maghilum
IC-1510-21 | DRR-0119-21 | Gerald Peter O. Rivera | WHD2 | HO | 2021-08-02 08:32:00 | 2021-08-02 08:32:00 | Done | Cae | DP_821611EU80-00000.ModelRoot MD_821611EU80-00000.ModelRoot;/export/home/eucoodb/model/work/TBU/02_A2/892W/82161/821611EU80/00000;Original Directory;Yes;ACCIDENTALLY OVEWRITE ORIGINAL DATA | 2021-08-03 09:06:00 | 2021-08-03 00:00:00 | 2021-08-03 09:07:00 | admin.Bryan Mar R. Alvarez
IC-1512-21 | CSR-1010-21 | Marie Rose A. Farala | EI | HO | 2021-08-02 09:23:00 | 2021-08-06 21:00:00 | Done | Install Software | May we request to download newly purchased MATLAB Licenses from Mathworks account (Reymark Evangelista) and install it in the corresponding IP addresses. MATLAB Licenses 1. 41024689(Matlab05) install in 10.49.131.113 and 10.49.131.114 with log-in matlab01 for both PC 2. 41024690(Matlab06) install in 10.49.1.145 with log-in pet1103 Should you have any concern, feel free to contact me. | 2021-08-09 08:38:00 | 2021-08-05 00:00:00 | 2021-09-27 11:21:00 | admin.Shiela Marie N. Arceo
IC-1516-21 | CSR-0975-21 | Redemptor C. Batiduan | PRT | HO | 2021-08-02 10:09:00 | 2021-08-03 21:00:00 | Done | Borrow | 1) Set VPN on 10.49.2.146 for WFH of Dary Asuncion (pet1529). 2) Set remote connection on the following workstations. a) 10.49.1.211 b) 10.49.1.165 c) 10.49.1.135 d) 10.49.1.250 e) 10.49.1.181 f) 10.49.1.182 g) 10.49.2.193 | 2021-08-02 21:35:00 | 2021-08-02 00:00:00 | 2021-08-03 12:57:00 | admin.Kevin Neil A. Mapa
IC-1513-21 | CSR-0990-21 | Cecil T. Morales | WHD3 | HO | 2021-08-02 10:50:00 | 2021-08-02 10:50:00 | Done | Borrow | Request of VPN for WFH. IP 10.49.3.18 | 2021-08-04 12:55:00 | 2021-08-04 00:00:00 | 2021-08-04 12:56:00 | admin.Kevin Neil A. Mapa
IC-1514-21 | CSR-0995-21 | Alanah Marie C. Mandawe | WHD3 | HO | 2021-08-02 10:50:00 | 2021-08-03 21:00:00 | Done | Borrow | REQUEST FOR VPN FOR WORK FROM HOME | 2021-08-04 18:01:00 | 2021-08-04 00:00:00 | 2021-08-04 18:02:00 | admin.Kevin Neil A. Mapa
IC-1515-21 | CSR-0994-21 | Jenneth M. Luna | WHD3 | HO | 2021-08-02 10:50:00 | 2021-08-03 21:00:00 | Done | Borrow | request of VPN for WFH IP 10.49.2.140 | 2021-08-04 17:18:00 | 2021-08-04 00:00:00 | 2021-08-04 17:19:00 | admin.Kevin Neil A. Mapa
IC-1517-21 | CSR-0987-21 | Lorenie M. Maullon | EA-DM | HO | 2021-08-02 11:48:00 | 2021-08-03 21:00:00 | Done | Borrow | NAME Mary Grace,Sore PET ID Pet1723 IP ADDRESS 10.49.5.15 BORROW 1 Laptop, charger and mouse. bag NAME Ann mary grace,Alde PET ID Pet 2051 IP ADDRESS 10.49.1.116 BORROW 1 Laptop, charger and mouse. bag | 2021-08-06 08:05:00 | 2021-08-04 00:00:00 | 2021-08-06 08:05:00 | admin.Nancy O. Gendive
IC-1519-21 | CSR-0976-21 | Jayson L. Toding | WHD2 | HO | 2021-08-02 13:21:00 | 2021-08-03 13:20:00 | Done | Borrow | Request to borrow PC for work from home. Owner - Daniel Movido HP (CPU) Model - HP ProDesk 400 G4 SFF PC S/N - SGH822TVRR HP (Monitor) Model - HP ProDisplay P240va Monitor S/N - CNK81829FC | 2021-08-02 21:34:00 | 2021-08-02 00:00:00 | 2021-08-04 18:01:00 | admin.Kevin Neil A. Mapa
IC-1520-21 | CSR-0974-21 | Jayson L. Toding | WHD2 | HO | 2021-08-02 13:23:00 | 2021-08-03 21:00:00 | Done | Borrow | Request to borrow PC for work from home. Owner - Carlyn Mae Vera HP (CPU) Model - HP ProDesk 400 G3 SFF S/N - 6CR7234M9H HP (Monitor 1) Model - HPPRODESKG4SFF S/N - CNK713lVPF HP (Monitor 2) Model - HP ProDisplay P240va Monitor S/N - CNK9152QRF | 2021-08-02 21:34:00 | 2021-08-02 00:00:00 | 2021-08-04 18:00:00 | admin.Kevin Neil A. Mapa
IC-1521-21 | CSR-0973-21 | Jayson L. Toding | WHD2 | HO | 2021-08-02 13:30:00 | 2021-08-03 21:00:00 | Done | Borrow | Request to borrow PC for work from home. Owner - Raiven Argete HP (CPU) Model - HP Pro Desk 400 G4 SFF PC S/N - SGH737R45R HP (Monitor 1) Model - HP ProDisplay P240va Monitor S/N - CNK7321PXD | 2021-08-02 21:34:00 | 2021-08-02 00:00:00 | 2021-08-03 20:49:00 | admin.Kevin Neil A. Mapa
IC-1522-21 | CSR-0993-21 | Williard D. Go | TCE | HO | 2021-08-02 15:32:00 | 2021-08-03 21:00:00 | Done | Borrow | We would like to borrow Big PC Monitor for the laptop below this is for better viewing of test results and reports. ( including cross section photo and appearance photo ) IP Address 10.49.1.229 | 2021-08-06 21:40:00 | 2021-08-04 00:00:00 | 2021-08-09 15:24:00 | admin.Kevin Neil A. Mapa
IC-1534-21 | QA-0068-21 | Melissa R. Talabong | FIN | HO | 2021-08-03 06:49:00 | 2021-08-03 06:49:00 | Closed |  | network problem laptop connecting to 6A | 2021-08-03 06:49:00 | 2021-08-03 06:49:00 | 2021-08-03 07:15:00 | admin.admin.Reymark B. Evangelista | 0.43
IC-1535-21 | QA-0069-21 | Sharmaine T. Ingles | SCD | HO | 2021-08-03 07:19:00 | 2021-08-03 07:19:00 | Closed |  | Folder access concern CSR-0838-19 yan po New folder created for TCE Members. Z:\TCE_OPERATION\7. TCE_Dashboard Per log in folder access for members. Manager, Supervisor & Staff can create, access & modify all files inside the folder | 2021-08-03 07:19:00 | 2021-08-03 07:19:00 | 2021-08-04 07:29:00 | admin.admin.Reymark B. Evangelista | 15.17
IC-1536-21 | QA-0070-21 | Marie Rose A. Farala | EI | HO | 2021-08-03 07:58:00 | 2021-08-03 07:58:00 | Closed |  | Check ram to 4 PC and confirm additional ram | 2021-08-03 07:58:00 | 2021-08-03 07:58:00 | 2021-08-03 08:10:00 | admin.admin.Reymark B. Evangelista | 0.2
IC-1524-21 | CSR-1009-21 | Annabelle L. Malonda | EI | HO | 2021-08-03 07:59:00 | 2021-11-02 21:00:00 | Done | Hardware Purchase | October Budget Change Jabra Headset (1 unit) to A4Tech HU-7P USB Headset (2 units) Reference \\10.49.1.97\Budget Control\FY81_BUDGET\1. ENGINEERING REDUCED 3\HO\FY81P_HO_ENGINEERING_SW.xlsx | 2021-08-06 13:15:00 | 2021-08-05 00:00:00 | 2021-10-15 07:56:00 | admin.Nancy O. Gendive
IC-1526-21 | CSR-0992-21 | Mariel R. Santos | WHD3 | HO | 2021-08-03 08:57:00 | 2021-08-12 21:00:00 | Done | Account Request | change my email surname from mariel.santos@ph.yazaki.com to mariel.param@ph.yazaki.com | 2021-08-05 08:21:00 | 2021-08-04 00:00:00 | 2021-08-09 12:12:00 | admin.Ruby A. Maghilum
IC-1537-21 | QA-0071-21 | Marie Rose A. Farala | EI | HO | 2021-08-03 09:00:00 | 2021-08-03 09:00:00 | Closed |  | 515 assist Ozaki san/ mam ruby on data center | 2021-08-03 09:00:00 | 2021-08-03 09:00:00 | 2021-08-03 09:29:00 | admin.admin.Reymark B. Evangelista | 0.48
IC-1538-21 | QA-0072-21 | Marie Rose A. Farala | EI | HO | 2021-08-03 09:00:00 | 2021-08-03 09:00:00 | Closed |  | 515 assist Ozaki san/ mam ruby on data center | 2021-08-03 09:00:00 | 2021-08-03 09:00:00 | 2021-08-03 09:29:00 | admin.admin.Reymark B. Evangelista | 0.48
IC-1525-21 | CPR-0093-21 | Rhiessa Sarah Z. Tuyor | EV-CE | HO | 2021-08-03 09:02:00 | 2021-08-03 09:02:00 | Done | IP Phone | wire of the handset of loc.510 is broken. Please repair. | 2021-08-27 13:35:00 | 2021-08-06 00:00:00 | 2021-10-07 15:48:00 | admin.Reymark B. Evangelista
IC-1542-21 | QA-0076-21 | Emiliano P. Mendoza | MIS | HO | 2021-08-03 09:47:00 | 2021-08-03 09:47:00 | Closed |  | A company sir emil to deploy repaired OCE machine in WH | 2021-08-03 09:47:00 | 2021-08-03 09:47:00 | 2021-08-03 10:11:00 | admin.admin.Reymark B. Evangelista | 0.4
IC-1527-21 | CSR-1018-21 | Angelo I. Tajonera | EI | HO | 2021-08-03 10:01:00 | 2021-08-04 21:00:00 | Closed | Modify Software | Need to fix excel. Problem - Excel is freezing when copying inside the cell | 2021-09-01 07:36:00 | 2021-08-06 00:00:00 | 2021-09-01 08:17:00 | admin.Bryan Mar R. Alvarez | 0.68
IC-1539-21 | QA-0073-21 | April D. Dayapan | EI | HO | 2021-08-03 11:00:00 | 2021-08-03 11:00:00 | Closed |  | Remote connection concern, BO try to connect PC in pet but she accidentally click the connect VPN in forticlient | 2021-08-03 11:00:00 | 2021-08-03 11:00:00 | 2021-08-03 11:14:00 | admin.admin.Reymark B. Evangelista | 0.23
IC-1540-21 | QA-0074-21 | April D. Dayapan | EI | HO | 2021-08-03 11:00:00 | 2021-08-03 11:00:00 | Closed |  | Remote connection concern, BO try to connect PC in pet but she accidentally click the connect VPN in forticlient | 2021-08-03 11:00:00 | 2021-08-03 11:00:00 | 2021-08-03 11:14:00 | admin.admin.Reymark B. Evangelista | 0.23
IC-1529-21 | CSR-1125-21 | Carlyn Mae T. Vera | WHD2 | HO | 2021-08-03 11:35:00 | 2021-08-12 21:00:00 | Done | PC Configuration | Remote Access Request for WFH purposes. pet1788 10.49.2.228 Request to install Lync for WFH purposes. | 2021-08-31 14:31:00 | 2021-08-31 00:00:00 | 2021-08-31 14:32:00 | admin.Kevin Neil A. Mapa
IC-1531-21 | CSR-0984-21 | Lei C. Malabanan | JBRB | HO | 2021-08-03 12:36:00 | 2021-08-04 21:00:00 | Done | PC Configuration | LYNC, OUTLOOK, MICROSOFT EXCEL still not working properly. (Windows 365 installation confirmation if completed) problem occurs yesterday 08/02/2021 and requested for support. Other PC of JBRB has this problem. 10.49.1.33, 10.49.3.237 Thank you in advance. | 2021-08-03 16:10:00 | 2021-08-03 00:00:00 | 2021-08-04 12:55:00 | admin.Kevin Neil A. Mapa
IC-1532-21 | CSR-0991-21 | Sharmaine T. Ingles | SCD | HO | 2021-08-03 13:10:00 | 2021-08-12 21:00:00 | Done | Account Request | Email Request for 1. Alexander C. Inocencio (ID No. 2075_MFE ) 2. Paquito I. Conde Jr. (ID No. 2076_JTE_Test Method Expert) 3. Christian Ian Mikko M. Magyaya ( ID No. 2073_JTE_Test Method Expert ) | 2021-08-06 06:44:00 | 2021-08-04 00:00:00 | 2021-08-09 23:20:00 | admin.Nancy O. Gendive
IC-1533-21 | CSR-0986-21 | Jayson L. Toding | WHD2 | HO | 2021-08-03 17:06:00 | 2021-08-04 21:00:00 | Done | Borrow | Request to borrow PC for work from home. Owner - Elijah Marco HP (CPU) Model - HP ProDesk 400 G3 SFF S/N - SGH737R45H HP (Monitor 1) Model - HP ProDisplay P240va Monitor S/N - CNK7321PX0 | 2021-08-04 11:58:00 | 2021-08-04 00:00:00 | 2021-10-20 09:18:00 | admin.Reymark B. Evangelista
IC-1543-21 | CSR-1061-21 | Edvin B. Pantoni | EV | HO | 2021-08-04 08:38:00 | 2021-08-05 21:00:00 | Done | Borrow | Borrow Monitor for PET expat (Kengo Machida). | 2021-09-02 19:48:00 | 2021-08-17 00:00:00 | 2021-09-02 19:57:00 | admin.Kevin Neil A. Mapa
IC-1544-21 | CSR-1142-21 | Carolyn B. EspeÃ±a | WHD1 | HO | 2021-08-04 09:30:00 | 2021-08-05 21:00:00 | Done | Transfer Software location | Request to transfer Microsoft Lync from PET1PC1222 (10.49.1.222) to PET5PC5038 (10.49.5.3 8) due to no one using the PC PETPC1222 and to prevent transferring to other table and using other PC for online meeting. | 2021-09-03 09:06:00 | 2021-09-02 00:00:00 | 2021-09-03 09:07:00 | admin.Bryan Mar R. Alvarez
IC-1545-21 | CSR-1231-21 | Johanna D. Santos | HR | HO | 2021-08-04 10:20:00 | 2021-11-03 21:00:00 | Done | Hardware Purchase | Epson LQ 310 (printer) (PRIF for processing) | 2021-10-02 15:37:00 | 2021-09-23 00:00:00 | 2021-10-02 15:37:00 | admin.Nancy O. Gendive
IC-1548-21 | CSR-1140-21 | Ma. Cecilia B. Bermejo | EDSD | HO | 2021-08-04 12:48:00 | 2021-08-11 12:48:00 | Done | Backup to CD/DVD | Back up file located at \\10.49.1.97\wh\COMMON\QUALITY\COUNTERMEASURE CPAP-EXTERNAL- 76TH TERM CPAP-EXTERNAL- 77TH TERM CPAP-EXTERNAL-2015 CPAP-EXTERNAL-2016 | 2021-10-02 08:50:00 | 2021-09-02 00:00:00 | 2021-10-02 08:51:00 | admin.Ruby A. Maghilum
IC-1541-21 | QA-0075-21 | April D. Dayapan | EI | HO | 2021-08-04 14:30:00 | 2021-08-04 14:30:00 | Closed |  | SRS follow-up request CPR 0077-21 | 2021-08-04 14:30:00 | 2021-08-04 14:30:00 | 2021-08-04 14:49:00 | admin.admin.Reymark B. Evangelista | 0.32
IC-1550-21 | CSR-1175-21 | Belinda C. Cabico | WHE | HO | 2021-08-04 16:28:00 | 2021-08-13 21:00:00 | Work in Progress | Access Request | Delete Windows Login, Email, Seine2, and deactivate MHT of Resigned Employee PET1885 | 2021-10-19 07:36:00 | 2021-09-10 00:00:00 | 0000-00-00 00:00:00 | admin.Ruby A. Maghilum
IC-1553-21 | CSR-1066-21 | Jovielet B. Caintoy | EDSD | HO | 2021-08-05 07:30:00 | 2021-08-16 21:00:00 | Closed | Access Request | Request for additional access right of WHD2 members. See attached documents, | 2021-08-18 12:30:00 | 2021-08-18 00:00:00 | 2021-09-02 08:51:00 | admin.Bryan Mar R. Alvarez | 146.35
IC-1557-21 | CSR-1006-21 | Ruby A. Maghilum | MIS | HO | 2021-08-05 08:41:00 | 2021-08-06 21:00:00 | Done | Hardware Purchase | request quotation of POLY 67500 for ASEANA1 and ASEANA 2 | 2021-08-09 12:11:00 | 2021-08-05 00:00:00 | 2021-08-10 15:09:00 | admin.Ruby A. Maghilum
IC-1558-21 | CSR-1001-21 | Ruby A. Maghilum | MIS | HO | 2021-08-05 08:41:00 | 2021-08-06 21:00:00 | Done | Hardware Purchase | request quotation of POLY 67500 for ASEANA1 and ASEANA 2 | 2021-08-09 12:07:00 | 2021-08-05 00:00:00 | 2021-08-09 12:08:00 | admin.Ruby A. Maghilum
IC-1559-21 | CSR-1013-21 | Reymark B. Evangelista | MIS | HO | 2021-08-05 08:46:00 | 2021-11-04 21:00:00 | Done | Hardware Purchase | Engineering works, HDMI Cable installation for Aseana One and Two FY81P_HO_ENGINEERING_MIS July Budget | 2021-08-10 08:17:00 | 2021-08-06 00:00:00 | 2021-09-18 14:55:00 | admin.Reymark B. Evangelista
IC-1561-21 | CSR-1053-21 | John Kendryl O. Fernandez | WHD2 | HO | 2021-08-05 08:57:00 | 2021-08-16 21:00:00 | Done | Account Request | Request to update email and name john kendryll, fernandez john kendryl, fernandez johnkendryll.fernandez@ph.yazaki.com to johnkendryll.fernandez@ph.yazaki.com | 2021-08-31 07:54:00 | 2021-08-17 00:00:00 | 2021-08-31 08:01:00 | admin.Ruby A. Maghilum
IC-1560-21 | CSR-1005-21 | Johanna Marie C. Dandan | SCD | HO | 2021-08-05 09:00:00 | 2021-08-16 21:00:00 | Done | Access Request | Request for Folder Access in EED server (WHE) [add, SAVE, delete] Location_ \\10.49.1.97\eed\EED_Hardisk 5S\EED | 2021-08-06 16:06:00 | 2021-08-05 00:00:00 | 2021-08-09 13:32:00 | admin.Kevin Neil A. Mapa
IC-1562-21 | CSR-1041-21 | Rafael S. Fontenuela | JBRB | HO | 2021-08-05 09:01:00 | 2021-08-06 21:00:00 | Done | PC Configuration | Request to add ANSYS version 2021 (to use Workbench version 2021). Please keep the old version. | 2021-09-02 19:48:00 | 2021-08-13 00:00:00 | 2021-09-06 14:26:00 | admin.Kevin Neil A. Mapa
IC-1563-21 | CSR-1059-21 | John Kendryl O. Fernandez | WHD2 | HO | 2021-08-05 09:06:00 | 2021-08-06 21:00:00 | Done | Install Software | skype for business for my nihonggo class | 2021-08-17 11:42:00 | 2021-08-17 00:00:00 | 2021-08-17 11:42:00 | admin.Bryan Mar R. Alvarez
IC-1565-21 | QA-0079-21 | Rommel E. Aguilon | ADM | HO | 2021-08-05 09:40:00 | 2021-08-05 09:40:00 | Closed |  | Internet Connection concern | 2021-08-05 09:40:00 | 2021-08-05 09:40:00 | 2021-08-05 10:05:00 | admin.admin.Reymark B. Evangelista | 0.42
IC-1564-21 | CSR-1020-21 | Angelica Gentica | EDSD | HO | 2021-08-05 11:17:00 | 2021-08-06 21:00:00 | Done | PC Configuration | For work from home set up IP address 10.49.2.245 | 2021-08-09 12:05:00 | 2021-08-07 00:00:00 | 2021-08-09 12:06:00 | admin.Ruby A. Maghilum
IC-1568-21 | CSR-1014-21 | Rafael O. Pangilinan | EA-DM | HO | 2021-08-06 08:14:00 | 2021-08-09 21:00:00 | Done | Install Software | Installation of Mozilla Firefox to the following PC with IP Address - 10.49.2.200 (Rafael Pangilinan) - 10.49.1.173 (Charito Canonizado) - 10.49.5.5 (Juvy Ann Nava) - 10.49.3.199 (Rodney Estacion) | 2021-08-06 08:50:00 | 2021-08-06 00:00:00 | 2021-08-09 12:04:00 | admin.Ruby A. Maghilum
IC-1572-21 | CSR-1031-21 | Sharmaine T. Ingles | SCD | HO | 2021-08-09 09:15:00 | 2021-08-10 09:15:00 | Work in Progress | Transfer PC location | Request for PC & Telephone location. Please see attached file. Y:\01. TED Common_Management\002_ISMS Related\Reference Files\Computer Layout\20210809_TCE & CE Common_Monitoring of Account and PC Layout | 2021-11-02 11:38:00 | 2021-08-10 00:00:00 | 0000-00-00 00:00:00 | admin.Ruby A. Maghilum
IC-1574-21 | CSR-1030-21 | Mark Joseph D. Asis | WHE | HO | 2021-08-09 13:06:00 | 2021-08-10 08:00:00 | Done | Access Request | Access to files at 1.\\10.49.1.97\common\Common_Data\Risk and Opportunity Management\Risk Register\System and Component\WHE 2.\\10.49.1.97\common\Common_Data\Risk and Opportunity Management\Opportunity Register\System and Component\WHE was change to Read Only As one of department QRs, Request to return to Read and Write | 2021-08-11 06:40:00 | 2021-08-09 00:00:00 | 2021-08-11 06:40:00 | admin.Bryan Mar R. Alvarez
IC-1575-21 | CSR-1060-21 | Kristiel Joy B. Diaz | WHD2 | HO | 2021-08-10 07:52:00 | 2021-09-21 21:00:00 | Done | Renewal License | CADRA LICENSE FOR RENEWAL | 2021-08-17 13:08:00 | 2021-08-17 00:00:00 | 2021-10-19 16:20:00 | admin.Jasper Labenia
IC-1576-21 | DRR-0122-21 | Catherine U. Bulalacao | WHD3 | HO | 2021-08-10 08:10:00 | 2021-08-10 08:10:00 | Done | Windows | JOB REQUEST CONTROL LIST 2019_UPDATED.xls;\\10.49.1.97\wh\NISSAN\NISSAN_SSN\SCHEDULE_OF_INCHRGE\JOB REQUEST CONTROL LIST 2019_UPDATED.xls;Original Directory;No;file corrupted | 2021-08-31 07:52:00 | 2021-08-17 00:00:00 | 2021-08-31 07:53:00 | admin.Ruby A. Maghilum
IC-1577-21 | CSR-1032-21 | Roxyanne Grace R. Garcia | CON | HO | 2021-08-10 09:46:00 | 2021-08-11 21:00:00 | Done | Borrow | Borrow PC for 1 Connector Member (PET0315 Mario Carlo Dizon) HP ProDesk 400 G4 SFF (SN. SGH822TVQJ) (IP 10.49.1.156) | 2021-08-10 14:34:00 | 2021-08-10 00:00:00 | 2021-08-10 14:35:00 | admin.Ruby A. Maghilum
IC-1578-21 | CSR-1139-21 | Sheena C. Cagape | WHD1 | HO | 2021-08-10 12:27:00 | 2021-08-11 21:00:00 | Done | PC Configuration | for WFH purposes KD viewer | 2021-09-02 15:27:00 | 2021-09-02 00:00:00 | 2021-09-02 15:28:00 | admin.Bryan Mar R. Alvarez
IC-1579-21 | CSR-1033-21 | Sharmaine T. Ingles | SCD | HO | 2021-08-10 13:19:00 | 2021-08-11 21:00:00 | Done | Borrow | Borrow 1 monitor for Documentation Area Sharmaine Ingles 10.49.2.22 until Dec 2022 | 2021-08-10 16:12:00 | 2021-08-10 00:00:00 | 2021-08-24 08:48:00 | admin.Kevin Neil A. Mapa
IC-1580-21 | CSR-1040-21 | Ranilyn Rose M. Mernilo | WHE | HO | 2021-08-10 15:38:00 | 2021-08-11 21:00:00 | Done | PC Configuration | WFH set-up | 2021-08-31 07:47:00 | 2021-08-13 00:00:00 | 2021-08-31 07:50:00 | admin.Ruby A. Maghilum
IC-1581-21 | CSR-1034-21 | Karmalou Sasaki | FIN | HO | 2021-08-11 07:16:00 | 2021-11-10 21:00:00 | Done | Hardware Purchase | Purchase of Scanner and Printer | 2021-08-11 07:27:00 | 2021-08-11 00:00:00 | 2021-10-02 15:35:00 | admin.Nancy O. Gendive
IC-1583-21 | CSR-1035-21 | Lorenie M. Maullon | EA-DM | HO | 2021-08-11 11:45:00 | 2021-08-12 21:00:00 | Done | Borrow | NAME Cheryl Gaa PET ID Pet0849 IP ADDRESS 10.49.3.53 BORROW 1 Laptop, charger and mouse. bag REASON WFH | 2021-08-17 06:39:00 | 2021-08-11 00:00:00 | 2021-08-17 07:20:00 | admin.Reymark B. Evangelista
IC-1584-21 | CSR-1095-21 | Johanna Marie C. Dandan | SCD | HO | 2021-08-11 11:57:00 | 2021-09-22 21:00:00 | Done | Renewal License | PRT CATIA RENEWAL LICENSE 1. Mechanical Design 2 (MD2) TARGET ID MEU-41D31C4A3E8C03AB IP ADDRESS 10.49.1.89 SEPTEMBER BUDGET (FY1P_HO_SOFTWAREUSAGEOTHERS_PRT) P 149,570.38 | 2021-10-02 08:45:00 | 2021-08-24 00:00:00 | 2021-10-02 08:47:00 | admin.Ruby A. Maghilum
IC-1585-21 | CSR-1232-21 | Lalaine L. Adriano | HR | HO | 2021-08-11 13:31:00 | 2021-09-22 21:00:00 | Done | Renewal License | Request for renewal of license of Robotic Process Automation (covering period from Oct. 1, 2020 to Sept. 30, 2022 | 2021-10-02 15:33:00 | 2021-09-23 00:00:00 | 2021-10-02 15:34:00 | admin.Nancy O. Gendive
IC-1586-21 | CSR-1039-21 | John Erick A. Nombrefia | WHD3 | HO | 2021-08-11 15:36:00 | 2021-08-12 21:00:00 | Done | Transfer PC location | Configuration of PC for WFH. Please check this. \\10.49.1.97\wh\COMMON\SV-MANAGER\WHD3\4 Monitoring\Gate Passing\Erick, yhel, Tin Gate passing and taking out.xlsx | 2021-08-13 12:40:00 | 2021-08-13 00:00:00 | 2021-08-31 17:21:00 | admin.Kevin Neil A. Mapa
IC-1587-21 | CSR-1037-21 | Ronalyn G. Imana | SCD | HO | 2021-08-12 06:48:00 | 2021-09-23 21:00:00 | Done | Renewal License | FOR JBRB Catia License Renewal- August Budget Target ID IP Address Planned Amount FVI-42481C4A3E999383 10.49.2.150 149,570.38 MBN-42A4108CFDC51B36 10.49.2.33 52,466.29 MTA-41F41C44FD2E3F35 10.49.1.184 149,570.38 TMT-429A10A8F04D1799 10.49.1.70 46,258.21 VWY-43491CB1D72C98EC 10.49.2.242 145,778.58 ZTQ-432E10A8F063DB53 10.49.3.66- Php149570.38 | 2021-10-02 08:34:00 | 2021-08-12 00:00:00 | 2021-10-02 08:41:00 | admin.Ruby A. Maghilum
IC-1588-21 | CSR-1097-21 | Rolando Jr. C. Miguel | CON | HO | 2021-08-12 06:52:00 | 2021-08-13 21:00:00 | Done | Endurance Test | PC hangs up after 10 to 30 minutess of use. | 2021-09-03 09:12:00 | 2021-08-24 00:00:00 | 2021-09-03 10:27:00 | admin.Reymark B. Evangelista
IC-1590-21 | CSR-1036-21 | Marron C. De Guzman | JBRB | HO | 2021-08-12 09:24:00 | 2021-08-13 21:00:00 | Done | Transfer Software location | Need to temporarily transfer solidworks simulation license because of hardware failure. Urgent request. | 2021-08-12 15:32:00 | 2021-08-12 00:00:00 | 2021-08-16 07:04:00 | admin.Reymark B. Evangelista
IC-1597-21 | CSR-1048-21 | Santiago III DC. Lagrimas | WHE | HO | 2021-08-12 15:26:00 | 2021-08-23 21:00:00 | Done | Account Request | E-mail account request(Migration), please inform if there is one already created. | 2021-08-17 08:50:00 | 2021-08-17 00:00:00 | 2021-08-17 10:45:00 | admin.Nancy O. Gendive
IC-1599-21 | CSR-1181-21 | Nazarine John P. Gesalan | WHD1 | HO | 2021-08-13 06:52:00 | 2021-08-16 21:00:00 | Done | Folder Creation | increase storage capacity of FUJIJU (temporary until 8/13/21) | 2021-09-17 10:27:00 | 2021-09-14 00:00:00 | 2021-09-17 10:28:00 | admin.Reymark B. Evangelista
IC-1604-21 | CSR-1050-21 | Norberto Jr. N. Bustarga | WHE | HO | 2021-08-13 07:56:00 | 2021-08-24 21:00:00 | Done | Access Request | Request a email address for Noel Sonny Sosa (PET1548) | 2021-08-17 07:03:00 | 2021-08-17 00:00:00 | 2021-08-17 09:56:00 | admin.Nancy O. Gendive
IC-1614-21 | CPR-0095-21 | Lucky Bien M. De Vera | JBRB | HO | 2021-08-13 13:55:00 | 2021-08-12 13:55:00 | Done | WS Ram | solidworks workstation become stuck up.( screen froze, no light on mouse, keyboard not working). we reset the workstation and after some time, the screen just went blue (fatal error). Sir Reymark have witnessed the event. | 2021-08-18 15:22:00 | 2021-08-18 00:00:00 | 2021-08-19 14:04:00 | admin.Reymark B. Evangelista
IC-1615-21 | CSR-1177-21 | Nazarine John P. Gesalan | WHD1 | HO | 2021-08-13 14:56:00 | 2021-08-16 21:00:00 | Done | PC Configuration | increase storage capacity of FUJIJU (temporary until 8/13/21) | 2021-09-14 07:01:00 | 2021-09-13 00:00:00 | 2021-09-14 07:02:00 | admin.Reymark B. Evangelista