## Worksheet
HO January 2021
| New Request | Assigned | Work in Progress | Completed | Count | Complete Percentage
CSR | 0 | 4 | 5 | 41 | 50 | 82
CPR | 0 | 1 | 1 | 6 | 8 | 75
DRR | 0 | 1 | 0 | 3 | 4 | 75
QA | N/A | N/A | N/A | 7 | 7 | 100
Members with Request and Status count info
Name | Assigned | Work in Progress | Done | Closed | Total
admin.Donald Kerby L. Manejero | 0 | 0 | 0 | 1 | 1
admin.Emiliano P. Mendoza | 0 | 0 | 1 | 0 | 1
admin.Jasper Labenia | 0 | 0 | 1 | 1 | 2
admin.Joe Nico T. Geronimo | 1 | 0 | 3 | 0 | 4
admin.Joel Eduardo D. Ocampo | 2 | 3 | 5 | 0 | 10
admin.John Christian Lovitos | 0 | 0 | 0 | 3 | 3
admin.Kaiser Ralph H. Roca | 0 | 1 | 0 | 2 | 3
admin.Kevin Neil A. Mapa | 1 | 0 | 0 | 0 | 1
admin.Nancy O. Gendive | 2 | 1 | 9 | 0 | 12
admin.Reymark B. Evangelista | 0 | 0 | 13 | 0 | 13
admin.Ruby A. Maghilum | 0 | 1 | 10 | 0 | 11
admin.Shiela Marie N. Arceo | 0 | 0 | 1 | 0 | 1
admin.Willem R. Leonardo | 0 | 0 | 0 | 7 | 7
Total |  |  |  |  | 69
Request Details
IC No. | Reference No. | Requestor | Department | Site | Request date | Request needed/occur | Status | Request | Details | Acknowledge Date | Date Receive | Date Done | In Charge | Man Hour | Response
IC-2182-20 | CSR-0017-21 | Jenny Lyn A. Pangilinan | WHD1 | HO | 2020-12-16 08:38:00 | 2020-12-17 21:00:00 | Closed | Backup CAE file/s | /export/home/eucoodb/model/work/HONDA/XY6E | 2021-01-06 14:09:00 | 2021-01-06 00:00:00 | 2021-03-08 14:06:00 | admin.John Christian Lovitos | 614.95 | Ahead of Time
IC-2186-20 | CSR-1040-20 | Mary Ann N. Javier | TCE | HO | 2020-12-16 09:02:00 | 2020-12-17 21:00:00 | Done | Install Software | Sorry for the short notice, We would like to request for installation of SKYPE, For the audit this afternoon via Skype Meeting. Williard Go (IP Address 10.49.2.82) Mary Ann Javier (IP Address 10.49.2.11) | 2021-01-15 09:09:00 | 2020-12-22 00:00:00 | 2021-01-15 10:29:00 | admin.Nancy O. Gendive | 1.33 | Ahead of Time
IC-2188-20 | QA-0657-20 | Czarina D. Soliven | WHD2 | HO | 2020-12-17 08:20:00 | 2020-12-17 08:20:00 | Closed |  | Ms office is not activated | 2020-12-17 08:20:00 | 2020-12-17 08:20:00 | 2020-12-17 08:35:00 | admin.Willem R. Leonardo | 0.25 | Ahead of Time
IC-2192-20 | QA-0660-20 | John Christian Lovitos | MIS | HO | 2020-12-17 10:00:00 | 2020-12-17 10:00:00 | Closed |  | riccoh printer paper jam | 2020-12-17 10:00:00 | 2020-12-17 10:00:00 | 2020-12-17 10:23:00 | admin.Willem R. Leonardo | 0.38 | Ahead of Time
IC-2190-20 | QA-0658-20 | Marissa M. Santiagudo | ADM | HO | 2020-12-17 10:20:00 | 2020-12-17 10:20:00 | Closed |  | Printer problem unable to print | 2020-12-17 10:20:00 | 2020-12-17 10:20:00 | 2020-12-17 11:00:00 | admin.Willem R. Leonardo | 0.67 | Ahead of Time
IC-2189-20 | CSR-0006-21 | Gene Rigor Quintos | EA-TQM | HO | 2020-12-17 10:31:00 | 2020-12-18 21:00:00 | Done | Plotter Configuration | What need - Identify user ID "Pet123" from what division and department he/she belongs. Why need - To improve work productivity on monthly paper consumption report. | 2021-01-05 13:41:00 | 2021-01-04 00:00:00 | 2021-01-13 15:46:00 | admin.Reymark B. Evangelista | 92.08 | Delay
IC-2191-20 | QA-0659-20 | Analy B. Babatio | HR | HO | 2020-12-17 11:00:00 | 2020-12-17 11:00:00 | Closed |  | configuration of new id to the printer | 2020-12-17 11:00:00 | 2020-12-17 11:00:00 | 2020-12-17 11:22:00 | admin.Willem R. Leonardo | 0.37 | Ahead of Time
IC-2193-20 | CPR-0117-20 | Mary Joy L. De Belen | EDSD | HO | 2020-12-18 09:28:00 | 2020-12-18 09:28:00 | Assigned | Mouse | Defective Mouse | 0000-00-00 00:00:00 | 2020-12-22 00:00:00 | 0000-00-00 00:00:00 | admin.Nancy O. Gendive
IC-2194-20 | DRR-0123-20 | Anna Marie D. Rirao | WHD2 | HO | 2020-12-18 10:51:00 | 2020-12-18 10:51:00 | Closed | Cae | PD_PET-3662073S00-36000;/export/home/eucoodb/model/work/SZK/SZK-WSZ/YJA/INSTPN/3662073S00/36000;Original Directory;No;No need to implement in data the received information from the customer. | 2020-12-21 13:27:00 | 2020-12-21 00:00:00 | 2020-12-21 15:08:00 | admin.John Christian Lovitos | 1.68 | Down Time
IC-2195-20 | CSR-1041-20 | Rommel E. Aguilon | ADM | HO | 2020-12-18 11:30:00 | 2020-12-21 21:00:00 | Assigned | Install Software | We would like to make a request to have the powerpoint file in the link below to be converted into a screensaver that will be installed to all computers in PET. This is one way to keep all PET employees reminded of their safety during these pandemic season specially in the coming holidays. \\Petsvr1097\common\ADMIN\for MIS\From_ADM_COVID-19\COVID-19 PRESENTATION.pptx\ | 0000-00-00 00:00:00 | 2020-12-22 00:00:00 | 0000-00-00 00:00:00 | admin.Joel Eduardo D. Ocampo
IC-2196-20 | CSR-1038-20 | Anna Marie D. Rirao | WHD2 | HO | 2020-12-18 13:25:00 | 2020-12-21 21:00:00 | Closed | Backup CAE file/s | Request for back up CAE FILES /export/home/eucoodb/model/work/SZK/SZK-WSZ/YEA /export/home/eucoodb/model/work/SZK/SZK-WSZ/YEB | 2020-12-21 14:55:00 | 2020-12-21 00:00:00 | 2020-12-21 15:13:00 | admin.Kaiser Ralph H. Roca | 0.3 | Ahead of Time
IC-2197-20 | DRR-0004-21 | Josie M. Gabatino | WHD2 | HO | 2020-12-18 13:40:00 | 2020-12-18 13:40:00 | Assigned | Windows | 82114-050D1;\\10.49.1.97\wh\TOYOTA\★CAE Related Documents\01. PROGRESS LIST\97=J7\050D\82114;Original Directory;No;file corrupted cannot be opened | 0000-00-00 00:00:00 | 2021-01-06 00:00:00 | 0000-00-00 00:00:00 | admin.Nancy O. Gendive
IC-2200-20 | CSR-1047-20 | Kristiel Joy B. Diaz | WHD2 | HO | 2020-12-18 14:22:00 | 2020-12-22 21:00:00 | Done | Backup to CD/DVD | FOR FILING AND ARCHIVING OF FILES | 2020-12-22 14:28:00 | 2020-12-22 00:00:00 | 2021-01-04 17:09:00 | admin.Reymark B. Evangelista | 47.68 | Delay
IC-2201-20 | CSR-0008-21 | Rhiessa Sarah Z. Tuyor | EV-CE | HO | 2020-12-18 14:54:00 | 2021-01-15 14:54:00 | Assigned | PC Configuration | I need to remotely access the Data Logger in PC. Can you help me configure TCP/IP of data logger to connect in network? | 0000-00-00 00:00:00 | 2021-01-04 00:00:00 | 0000-00-00 00:00:00 | admin.Joe Nico T. Geronimo
IC-2202-20 | CSR-0031-21 | Sharmaine T. Ingles | SCD | HO | 2020-12-18 15:18:00 | 2021-01-29 15:18:00 | Work in Progress | Backup to CD/DVD | transfer file to dvd from Z:\TCE Old Data\For Archive\2017 TCE file for Archive | 2021-01-19 17:07:00 | 2021-01-08 00:00:00 | 0000-00-00 00:00:00 | admin.Nancy O. Gendive
IC-2203-20 | CSR-1048-20 | Marilou P. De Luna | WHD3 | HO | 2020-12-18 16:05:00 | 2020-12-29 21:00:00 | Done | Access Request | Request VPN access for Dioza Mula Cruz to support work from home. | 2021-01-05 17:32:00 | 2020-12-22 00:00:00 | 2021-01-05 17:32:00 | admin.Reymark B. Evangelista | 0 | Ahead of Time
IC-2205-20 | CSR-0014-21 | Jovielet B. Caintoy | EDSD | HO | 2020-12-21 07:32:00 | 2020-12-30 21:00:00 | Done | Access Request | Request of folder access right for Mark John Castro ( transferred member from TCE to WHD2-Toyota) | 2021-01-06 14:00:00 | 2021-01-05 00:00:00 | 2021-01-06 16:36:00 | admin.Reymark B. Evangelista | 2.6 | Ahead of Time
IC-2206-20 | CPR-0116-20 | Rosano A. Buerano | EI | HO | 2020-12-21 07:41:00 | 2020-12-21 07:41:00 | Done | Operating System | There is no antivirus in my PC | 2020-12-22 13:49:00 | 2020-12-22 00:00:00 | 2020-12-22 13:50:00 | admin.Reymark B. Evangelista | 21.15 | Down Time
IC-2208-20 | CSR-1039-20 | Maria Josefa G. Samson | EA-DM | HO | 2020-12-21 14:56:00 | 2020-12-30 21:00:00 | Done | Access Request | Access to this folder \\10.49.1.97\emd\EMD1102\Data\Policy | 2020-12-22 09:10:00 | 2020-12-22 00:00:00 | 2021-01-04 09:26:00 | admin.Joe Nico T. Geronimo | 45.27 | Delay
IC-2209-20 | DRR-0125-20 | Wennie Rose C. Camus | SCD | HO | 2020-12-22 07:17:00 | 2020-12-22 07:17:00 | Done | Windows | File name - CE20-PK-0325.pdf;Location - \\Petsvr1097\cdd\Common\④ORDER SHEET\1_OS For Approval\BO\(1) B for Approval(GL)\FOR SENDING;Original Directory;;unintentionally delete the data | 2021-01-04 09:28:00 | 2020-12-22 00:00:00 | 2021-01-08 07:26:00 | admin.Joe Nico T. Geronimo | 57.97 | Down Time
IC-2210-20 | CSR-0015-21 | Ma. Cecilia B. Bermejo | EDSD | HO | 2020-12-22 16:30:00 | 2020-12-31 21:00:00 | Done | Access Request | Request for access right due to policy report requirement- \\Petsvr1097\iso\KPM\1. PET POLICY\03 EA\80th\TQM | 2021-01-07 14:08:00 | 2021-01-05 00:00:00 | 2021-01-13 16:43:00 | admin.Reymark B. Evangelista | 62.58 | Delay
IC-0001-21 | CSR-0032-21 | Maria Josefa G. Samson | EA-DM | HO | 2021-01-02 16:14:00 | 2021-01-04 21:00:00 | Done | Install Software | Update lync to skype | 2021-01-14 07:42:00 | 2021-01-08 00:00:00 | 2021-01-27 15:39:00 | admin.Joel Eduardo D. Ocampo | 142.95 | Delay
IC-0005-21 | CSR-0012-21 | Jennifer Joy D. Naputo | WHD3 | HO | 2021-01-04 11:42:00 | 2021-01-05 21:00:00 | Done | Backup to CD/DVD | Please back-up our files in CD/DVD. | 2021-01-05 14:16:00 | 2021-01-05 00:00:00 | 2021-01-06 13:29:00 | admin.Reymark B. Evangelista | 14.22 | Ahead of Time
IC-0007-21 | CSR-0035-21 | Jovielet B. Caintoy | EDSD | HO | 2021-01-04 13:57:00 | 2021-01-13 21:00:00 | Done | Access Request | Request for additional folder access right of Mary Kathlene Brotonel in Hino Folder. | 2021-01-15 11:12:00 | 2021-01-11 00:00:00 | 2021-02-04 11:37:00 | admin.Joel Eduardo D. Ocampo | 210.42 | Delay
IC-0012-21 | CSR-0011-21 | Glenn L. Fabian | EI | HO | 2021-01-04 15:39:00 | 2021-01-15 12:00:00 | Work in Progress | Increase Capacity | Add additional 100GB capacity to \\10.49.1.97\EI Archive\Hardware | 2021-01-14 07:39:00 | 2021-01-05 00:00:00 | 0000-00-00 00:00:00 | admin.Joel Eduardo D. Ocampo
IC-0014-21 | CSR-0016-21 | Sharmaine T. Ingles | SCD | HO | 2021-01-05 10:09:00 | 2021-01-14 21:00:00 | Done | Access Request | Request access of pet 1462 Rein Abalos in \\10.49.1.97\common\★★YC EVP Mr. Watanabe Project★★\000.KPI\80th term Vehicle Program KPIs | 2021-01-06 07:02:00 | 2021-01-06 00:00:00 | 2021-01-08 07:26:00 | admin.Joe Nico T. Geronimo | 30.4 | Delay
IC-0015-21 | CSR-0045-21 | Belinda C. Cabico | WHE | HO | 2021-01-05 10:18:00 | 2021-01-14 21:00:00 | Done | Access Request | Access and Account Deletion of the following Resigned employee 1290 Eurie Bandian Windows Login Email Seine2 MHT | 2021-01-18 15:28:00 | 2021-01-13 00:00:00 | 2021-04-05 09:50:00 | admin.Nancy O. Gendive
IC-0016-21 | CSR-0023-21 | Jovielet B. Caintoy | EDSD | HO | 2021-01-05 11:23:00 | 2021-01-14 21:00:00 | Done | Account Request | Request Seine 2 account for new & transferred members. Raiven Argete Elijah Marco Gerald Rivera Maribeth Bobo Charlie Fernandez Jeric Segurola Arizza Deres Kenneth Navales Catherine Balabo Mark John Castro | 2021-01-06 15:17:00 | 2021-01-06 00:00:00 | 2021-01-11 15:55:00 | admin.Nancy O. Gendive | 45.63 | Delay
IC-0017-21 | CSR-0010-21 | admin.Emiliano P. Mendoza | MIS | HO | 2021-01-05 11:44:00 | 2021-01-06 21:00:00 | Done | Access Request | Folder access request for new MIS member - Ms Ruby Maghilum MIS folder ( \\10.49.1.97\mis ) MIS Utilities folder ( \\10.49.1.97\MIS Utilities ) | 2021-01-15 11:17:00 | 2021-01-05 00:00:00 | 2021-02-07 11:44:00 | admin.Joel Eduardo D. Ocampo | 240.45 | Delay
IC-0018-21 | CSR-0028-21 | Johanna Marie C. Dandan | SCD | HO | 2021-01-05 14:15:00 | 2021-02-16 21:00:00 | Done | Renewal License | PRT CATIA RENEWAL LICENSE 1. CATIA-V5-6R2013-HD2-KWA ST1 TARGET ID DDX-41681C4A3E7D2131 IP ADDRESS 10.49.2.193 2. CATIA / ENOVIA DMU-V5-6R2017-DM1 (CONFIGURATION) TARGET ID DPX-4269105A3A58DC9C IP ADDRESS 10.49.5.138 3. CATIA V5 -V5-6R2013-MD2 (CONFIGURATION) TARGET ID ZAF-41F710481C79F421 IP ADDRESS 10.49.1.182 FEBRUARY BUDGET P 438,262.54 | 2021-01-07 15:54:00 | 2021-01-07 00:00:00 | 2021-03-25 16:14:00 | admin.Ruby A. Maghilum
IC-0020-21 | CSR-0024-21 | Rosano A. Buerano | EI | HO | 2021-01-05 15:35:00 | 2021-01-08 21:00:00 | Assigned | Install Software | Install Mentor Graphic Softwares and LP Wizard on Laptops with the following IP addresses -10.49.2.91 -10.49.5.250 -10.49.3.42 | 2021-01-14 12:54:00 | 2021-01-07 00:00:00 | 0000-00-00 00:00:00 | admin.Kevin Neil A. Mapa
IC-0021-21 | CSR-0025-21 | Ann Mary Grace A Alde | SCD | HO | 2021-01-05 16:49:00 | 2021-02-16 21:00:00 | Done | Renewal License | Request for license renewal for JBRB Target ID: CEM-41CB1CAE8B220D52 IP: 10.49.1.233 Product: PLM Budget: February Dept.: JBRB Site: HO | 2021-01-07 15:53:00 | 2021-01-07 00:00:00 | 2021-04-14 11:18:00 | admin.Ruby A. Maghilum
IC-0022-21 | CSR-0026-21 | Ann Mary Grace A Alde | SCD | HO | 2021-01-05 17:10:00 | 2021-02-16 21:00:00 | Done | Renewal License | Request for Catia license renewal for JBRB Target ID: MBD-441E108CFDDBECC9 IP: 10.49.2.227 Product: Catia V5-V5-6R2013-MD2 Budget: February Dept.: JBRB Site: HO | 2021-01-07 15:51:00 | 2021-01-07 00:00:00 | 2021-04-14 10:41:00 | admin.Ruby A. Maghilum
IC-0023-21 | CSR-0027-21 | Ann Mary Grace A Alde | SCD | HO | 2021-01-05 17:13:00 | 2021-02-16 21:00:00 | Done | Renewal License | Request for Catia license renewal for JBRB Target ID: VWY-43491CB1D72C98EC IP: 10.49.2.242 Product: CATIA V5 - V5-6R2013 - MD2 + GPS Budget: February Dept.: JBRB Site: HO | 2021-01-07 15:46:00 | 2021-01-07 00:00:00 | 2021-04-14 10:41:00 | admin.Ruby A. Maghilum
IC-0025-21 | CSR-0022-21 | Joan M. Fortuna | EV-CE | HO | 2021-01-06 08:46:00 | 2021-01-15 08:34:00 | Done | Backup to CD/DVD | To free up space in CTD server. Back up of old files. Location CTD/CE Requesting Affiliate/03 Low Voltage/0A FOR DVD/ | 2021-01-07 08:24:00 | 2021-01-06 00:00:00 | 2021-01-15 15:55:00 | admin.Nancy O. Gendive | 97.52 | Delay
IC-0026-21 | CSR-0033-21 | John Elly C. Javier | EV-CE | HO | 2021-01-06 09:57:00 | 2021-01-07 21:00:00 | Done | Install Software | Requesting to install the imaging software of newly purchase stereo microscope. | 2021-02-02 15:08:00 | 2021-01-08 00:00:00 | 2021-02-07 11:41:00 | admin.Joel Eduardo D. Ocampo | 56.55 | Delay
IC-0027-21 | CPR-0005-21 | Ramona Chariz A. Amon | CON | HO | 2021-01-06 11:14:00 | 2021-01-06 11:00:00 | Done | Mouse | Right pointer of mouse could not click properly. | 2021-01-15 10:32:00 | 2021-01-15 00:00:00 | 2021-01-15 10:34:00 | admin.Nancy O. Gendive | 104.57 | Down Time
IC-0028-21 | CPR-0006-21 | Mark Joseph S. Quion | CON | HO | 2021-01-06 14:41:00 | 2021-01-06 14:26:00 | Done | Monitor | monitor cannot be open | 2021-01-15 09:54:00 | 2021-01-15 00:00:00 | 2021-01-15 09:55:00 | admin.Ruby A. Maghilum | 100.48 | Down Time
IC-0036-21 | QA-0003-21 | Princess Ellaine C. Malanao | ADM | HO | 2021-01-07 07:00:00 | 2021-01-07 07:00:00 | Closed |  | internet access to online shopping | 2021-01-07 07:00:00 | 2021-01-07 07:00:00 | 2021-01-07 07:30:00 | admin.Willem R. Leonardo | 0.5 | Ahead of Time
IC-0032-21 | CSR-0044-21 | Marie Rose A. Farala | EI | HO | 2021-01-07 09:23:00 | 2021-01-08 21:00:00 | Done | Transfer Software location | Transfer MATLAB License R2019b and switch location of PC. - from 10.49.3.151 (8GB RAM) to 10.49.3.81 (16GB RAM) - from 10.49.3.153 (8GB RAM) to 10.49.3.13 (16GB RAM) | 2021-01-18 15:48:00 | 2021-01-13 00:00:00 | 2021-01-18 16:58:00 | admin.Reymark B. Evangelista | 1.17 | Ahead of Time
IC-0033-21 | CPR-0003-21 | Ronalyn G. Imana | SCD | HO | 2021-01-07 09:48:00 | 2021-01-07 09:33:00 | Done | MS Office | FOR TQM-SCDS Any Powerpoint files located in Server cannot open, always in error. (Started January 4 until current date) | 2021-01-14 13:00:00 | 2021-01-13 00:00:00 | 2021-01-15 19:44:00 | admin.Reymark B. Evangelista | 100.18 | Down Time
IC-0034-21 | CSR-0043-21 | Gelli A. Merene | EA-DM | HO | 2021-01-07 10:02:00 | 2021-01-18 21:00:00 | Done | Account Request | Update of information (Name) in LYNC and Email from Gelli Merene to Gelli Takahashi. | 2021-01-14 08:17:00 | 2021-01-13 00:00:00 | 2021-01-15 14:38:00 | admin.Nancy O. Gendive | 21.35 | Ahead of Time
IC-0035-21 | QA-0002-21 | Edwin F. Fulgar | ADM | HO | 2021-01-07 10:30:00 | 2021-01-07 10:30:00 | Closed |  | set up scan folder | 2021-01-07 10:30:00 | 2021-01-07 10:30:00 | 2021-01-07 10:40:00 | admin.Willem R. Leonardo | 0.17 | Ahead of Time
IC-0038-21 | CSR-0042-21 | Emiliano P. Mendoza | MIS | HO | 2021-01-07 14:14:00 | 2021-01-18 21:00:00 | Assigned | Account Request | Account Creation for new MIS member - Ms Ruby A. Maghilum ( local / Admin ) | 0000-00-00 00:00:00 | 2021-01-13 00:00:00 | 0000-00-00 00:00:00 | admin.Joel Eduardo D. Ocampo
IC-0039-21 | CSR-0029-21 | Ann Mary Grace A Alde | SCD | HO | 2021-01-07 15:16:00 | 2021-01-18 21:00:00 | Done | Account Request | Additional (CMMS) account request for Ms. Franzette Sola (1889) and Mr. Kennon Monleon (1888) | 2021-01-07 16:58:00 | 2021-01-07 00:00:00 | 2021-01-15 14:38:00 | admin.Nancy O. Gendive | 87.67 | Delay
IC-0040-21 | CSR-0047-21 | Michael Angelo H. Escalona | WHE | HO | 2021-01-08 06:59:00 | 2021-01-11 21:00:00 | Done | Access Request | 2 new TBU member 1 TBU member resigned | 2021-01-13 20:56:00 | 2021-01-13 00:00:00 | 2021-01-13 20:58:00 | admin.Reymark B. Evangelista | 0.03 | Ahead of Time
IC-0041-21 | CPR-0001-21 | Ayen G Panganiban | EV | HO | 2021-01-08 09:11:00 | 2021-01-08 06:30:00 | Done | Mouse | Left button defect. Request for replacement | 2021-01-08 15:10:00 | 2021-01-08 00:00:00 | 2021-01-08 15:10:00 | admin.Nancy O. Gendive | 8.67 | Down Time
IC-0044-21 | CSR-0059-21 | Juvy Ann G. Nava | EA-DM | HO | 2021-01-08 14:57:00 | 2021-01-12 08:00:00 | Done | Backup to CD/DVD | Transfer of scanned docs Location \\10.49.1.97\emd\PET-RC SHARED FOLDER\YC_Parts\DATA\DD_PI_AM\DRAWING DATA\YC Job Requests (Drawing Data Scanned Check Sheets) \\10.49.1.97\emd\EMD1102\Resource Center\MC-Parts\Temporary Folder\SCANNED | 2021-01-22 16:51:00 | 2021-01-15 00:00:00 | 2021-01-22 16:52:00 | admin.Ruby A. Maghilum | 0.02 | Ahead of Time
IC-0045-21 | CSR-0070-21 | Donn M. Carlos | WHD1 | HO | 2021-01-08 15:31:00 | 2021-02-19 21:00:00 | Closed | Renewal License | Renewal Cadra Software (V22) Support [10.49.1.86] | 2021-01-18 19:42:00 | 2021-01-15 00:00:00 | 2021-03-19 20:53:00 | admin.Jasper Labenia | 631.18
IC-0046-21 | CSR-0065-21 | Donn M. Carlos | WHD1 | HO | 2021-01-08 15:33:00 | 2021-04-09 21:00:00 | Done | Hardware Purchase | PC for replacement [10.49.3.94 (Subaru)] | 2021-04-30 10:19:00 | 2021-01-15 00:00:00 | 2021-05-11 10:18:00 | admin.Reymark B. Evangelista
IC-0047-21 | QA-0004-21 | Vicente Z. Nieto | WHE | HO | 2021-01-11 07:50:00 | 2021-01-11 07:50:00 | Closed |  | OMS change estimated time from 30 to 20hrs | 2021-01-11 07:50:00 | 2021-01-11 07:50:00 | 2021-01-11 07:56:00 | admin.Willem R. Leonardo | 0.1 | Ahead of Time
IC-0049-21 | CSR-0049-21 | Mark Joseph H. Nocon | TCE | HO | 2021-01-11 09:29:00 | 2021-01-12 21:00:00 | Work in Progress | Install Software | moritex shott application msx-500di viewer | 2021-02-02 15:11:00 | 2021-01-13 00:00:00 | 0000-00-00 00:00:00 | admin.Joel Eduardo D. Ocampo
IC-0050-21 | CSR-0064-21 | Donn M. Carlos | WHD1 | HO | 2021-01-11 09:37:00 | 2021-01-29 07:43:00 | Work in Progress | Transfer PC location | WHD1 relocation of computer layout due to transfer of members to other group. | 2021-01-15 16:21:00 | 2021-01-15 00:00:00 | 0000-00-00 00:00:00 | admin.Ruby A. Maghilum
IC-0051-21 | CSR-0038-21 | Mary Joy L. De Belen | EDSD | HO | 2021-01-11 13:48:00 | 2021-02-22 21:00:00 | Work in Progress | Renewal License | CAE SERVER MAINTENANCE RENEWAL Date: February 2021 - February 2022 Host Name: pet1ws1042 Serial No.: PZ31648024 Site: Head Office | 2021-01-18 09:08:00 | 2021-01-13 00:00:00 | 0000-00-00 00:00:00 | admin.Kaiser Ralph H. Roca
IC-0052-21 | CSR-0069-21 | Alfie I. Villamor | WHD1 | HO | 2021-01-12 08:10:00 | 2021-01-21 21:00:00 | Closed | Access Request | Access request to remote cadra Ip address 10.49.1.88 for the following Jig members Albert Mangabay - 10.49.5.194 Irene Durana - 10.49.2.158 | 2021-01-18 07:13:00 | 2021-01-15 00:00:00 | 2021-01-18 15:28:00 | admin.Kaiser Ralph H. Roca | 8.25 | Ahead of Time
IC-0053-21 | CSR-0048-21 | Belinda C. Cabico | WHE | HO | 2021-01-12 09:24:00 | 2021-01-13 21:00:00 | Done | Modify Software | NX cannot be opened in the newly installed PC. Email has already been made since 1/05/2021 and no action from MIS yet. | 2021-02-01 16:26:00 | 2021-01-13 00:00:00 | 2021-02-01 16:27:00 | admin.Emiliano P. Mendoza | 0.02 | Ahead of Time
IC-0054-21 | CSR-0058-21 | Roner B. Paguirigan | WHE | HO | 2021-01-12 09:28:00 | 2021-01-18 21:00:00 | Done | Borrow | Loptop for work from home of assignee. he will be quarantined for 14 days after arrival in Iloilo. he need to work from home. | 2021-01-15 13:46:00 | 2021-01-15 00:00:00 | 2021-01-18 09:21:00 | admin.Shiela Marie N. Arceo | 10.58 | Ahead of Time
IC-0055-21 | CSR-0052-21 | Troy George II G. Dela Cruz | WHE | HO | 2021-01-12 09:43:00 | 2021-01-13 21:00:00 | Done | Backup to CD/DVD | For data archive "\\10.49.1.97\eed\EED_Hardisk 5S\TBU-JPN\06_TBU-DJJ2\DJJ2_Jig_Simulation_November_2019-February_2020.zip" | 2021-01-18 10:04:00 | 2021-01-13 00:00:00 | 2021-01-18 15:27:00 | admin.Ruby A. Maghilum | 5.38 | Ahead of Time
IC-0057-21 | CPR-0004-21 | Ernesto L. Basbas | SCD | HO | 2021-01-12 14:49:00 | 2021-01-11 14:34:00 | Work in Progress | Monitor | Alert popped up on my screen whenever I open my PC. | 2021-01-15 12:49:00 | 2021-01-13 00:00:00 | 0000-00-00 00:00:00 | admin.Joel Eduardo D. Ocampo
IC-0058-21 | CSR-0053-21 | Belinda C. Cabico | WHE | HO | 2021-01-12 14:50:00 | 2021-01-21 21:00:00 | Done | Account Request | Delete Access and Account of Resigned Employee pet1974 Marc Carlo Vendivil Windows Login | 2021-01-14 16:27:00 | 2021-01-13 00:00:00 | 2021-01-14 17:10:00 | admin.Nancy O. Gendive | 0.72 | Ahead of Time
IC-0059-21 | CSR-0055-21 | Belinda C. Cabico | WHE | HO | 2021-01-12 15:05:00 | 2021-01-13 21:00:00 | Done | Modify Software | Exchange MS Office between PC. Lync needed for the Online training and Meeting. See attached file for the concerned IP. | 2021-01-25 12:56:00 | 2021-01-14 00:00:00 | 2021-02-01 13:04:00 | admin.Reymark B. Evangelista | 75.13 | Delay
IC-0060-21 | DRR-0009-21 | Wennie Rose C. Camus | SCD | HO | 2021-01-12 17:11:00 | 2021-01-12 16:57:00 | Closed | Windows | JBRB Folder Access Right;\\Petsvr1097\jbrb\00_Home\(9) ISMS\JBRB Members Access List\02-JBRB Members Folder Access Rights;Original Directory;;Unintentionally saved. | 2021-01-25 09:05:00 | 2021-01-19 00:00:00 | 2021-01-25 10:16:00 | admin.Donald Kerby L. Manejero | 1.18 | Down Time
IC-0067-21 | CSR-0057-21 | Maria Josefa G. Samson | EA-DM | HO | 2021-01-13 15:56:00 | 2021-01-15 09:49:00 | Done | Access Request | Additional & deletion of member to access this location \\10.49.1.97\emd\EMD1102\Data\★ES Management\002. Profile | 2021-01-15 09:21:00 | 2021-01-15 00:00:00 | 2021-01-15 12:56:00 | admin.Ruby A. Maghilum | 3.58 | Ahead of Time
IC-0068-21 | CSR-0068-21 | Donn M. Carlos | WHD1 | HO | 2021-01-14 08:11:00 | 2021-01-25 21:00:00 | Closed | Outsources Request | Change of VNC password of the following WHD1 members. Please see attachment. | 2021-01-15 21:28:00 | 2021-01-15 00:00:00 | 2021-01-27 12:56:00 | admin.John Christian Lovitos | 111.47 | Delay
IC-0070-21 | CSR-0067-21 | Jovielet B. Caintoy | EDSD | HO | 2021-01-14 09:00:00 | 2021-01-25 21:00:00 | Done | Access Request | Request for additional access right of Joshua De los Santos in PTM folder. | 2021-01-18 10:03:00 | 2021-01-15 00:00:00 | 2021-02-04 10:07:00 | admin.Ruby A. Maghilum | 195.07 | Delay
IC-0074-21 | CSR-0056-21 | Cindy S. Antonillas | EA-TQM | HO | 2021-01-14 12:11:00 | 2021-01-25 21:00:00 | Done | Access Request | To have full access on ISMS folder \\10.49.1.97\isms for ISMS activities. for pet user id 6098 | 2021-01-15 09:19:00 | 2021-01-15 00:00:00 | 2021-01-18 09:59:00 | admin.Ruby A. Maghilum | 15.67 | Ahead of Time
IC-0075-21 | CPR-0007-21 | Clarice L. Jandayan | WHD2 | HO | 2021-01-14 13:03:00 | 2021-01-04 12:49:00 | Done | No Connection | Problem encountered on LAN outlet.(no connection) | 2021-02-07 11:36:00 | 2021-01-15 00:00:00 | 2021-02-07 11:37:00 | admin.Joel Eduardo D. Ocampo | 373.8 | Down Time
IC-0076-21 | CSR-0066-21 | Demark M. Simborio | WHD1 | HO | 2021-01-14 13:50:00 | 2021-01-15 21:00:00 | Done | Printer Configuration | scan location in desktop (10.49.3.25) due heavy load in server. | 2021-01-15 20:35:00 | 2021-01-15 00:00:00 | 2021-01-15 20:35:00 | admin.Reymark B. Evangelista | 0 | Ahead of Time
IC-0077-21 | CSR-0081-21 | Ann Mary Grace A Alde | SCD | HO | 2021-01-14 15:32:00 | 2021-02-25 21:00:00 | Done | Renewal License | PRIF Request for CADRA License renewal HOST ID : 9-76E65CD1 Department : JBRB | 2021-01-19 18:36:00 | 2021-01-19 00:00:00 | 2021-04-13 16:54:00 | admin.Jasper Labenia