## Worksheet
BO July 2021
| New Request | Assigned | Work in Progress | Completed | Count | Complete Percentage
CSR | 0 | 1 | 2 | 34 | 37 | 92
CPR | 0 | 0 | 0 | 4 | 4 | 100
DRR | 0 | 0 | 0 | 6 | 6 | 100
QA | N/A | N/A | N/A | 0 | 0 | 0
Members with Request and Status count info
Name | Assigned | Work in Progress | Done | Closed | Total
admin.Donald Kerby L. Manejero | 0 | 0 | 6 | 0 | 6
admin.Elmo A. Daquila JR. | 0 | 0 | 8 | 0 | 8
admin.Kevin Neil A. Mapa | 0 | 0 | 2 | 0 | 2
admin.Nancy O. Gendive | 0 | 0 | 1 | 0 | 1
admin.Ruby A. Maghilum | 0 | 0 | 1 | 0 | 1
admin.Shiela Marie N. Arceo | 0 | 2 | 25 | 1 | 28
Total |  |  |  |  | 46
Request Details
IC No. | Reference No. | Requestor | Department | Site | Request date | Request needed/occur | Status | Request | Details | Acknowledge Date | Date Receive | Date Done | In Charge | Man Hour | Response
IC-1124-21 | CSR-0751-21 | April D. Dayapan | EI | BO | 2021-06-16 10:18:00 | 2021-07-28 21:00:00 | Work in Progress | Renewal License | 2 CATIA Annual License Charge- Php 299,140.77 FY81P_BO_Software Usage Others Budget_MT_rev1 Target ID - FLU-41F31C4A3E8C03CB (10.49.130.161) July 2021 Budget Target ID - NDU-42071C4A3E8C03DF (10.49.130.162) August 2021 Budget | 2021-08-20 10:07:00 | 2021-06-18 00:00:00 | 0000-00-00 00:00:00 | admin.Shiela Marie N. Arceo
IC-1123-21 | DRR-0091-21 | Kayzelle Shyne S. Magarse | EV | BO | 2021-06-16 10:37:00 | 2021-06-16 10:37:00 | Done | Windows | 1. X42154-MC07M01#00# and X42154-MC07M02#00# 2. X42154-MC06M01#00# and X42154-MC06M02#00# ;1. Z:\③ JOB_ORDERS\EV_BOX\2021\6月\EVXX-XX-XXXX (OISHI SAN)\OUTPUT\2D DWG\210615\2\X42154-MC07M#05#MdSwMd\X42154-MC07M#05#MdSwMd 2. Z:\③ JOB_ORDERS\EV_BOX\2021\6月\EVXX-XX-XXXX (OISHI SAN)\OUTPUT\2D DWG\besh\1\X42154-MC06M#05#MdSwMd\X42154-MC06M#00#MdSwMd ;save time 1. before 845 to 9am 2. 9amto 915am;No;restore drawing | 2021-06-18 10:10:00 | 2021-06-16 00:00:00 | 2021-06-18 10:12:00 | admin.Shiela Marie N. Arceo
IC-1141-21 | DRR-0092-21 | Kristel Anne D. Villanueva | SCD | BO | 2021-06-18 07:17:00 | 2021-06-18 07:17:00 | Done | Windows | 81st Paper Monitoring.xlsm;\\10.49.128.7\tqm_(branch)\001 KPI DATA MANAGEMENT\(4) INVENTORY\81st Term\Paper Consumption;Original Directory;Yes;cannot open file / corrupt file | 2021-06-22 11:15:00 | 2021-06-18 00:00:00 | 2021-07-30 20:33:00 | admin.Shiela Marie N. Arceo
IC-1145-21 | CSR-0745-21 | Shiela Marie N. Arceo | MIS | BO | 2021-06-18 08:23:00 | 2021-07-30 21:00:00 | Done | Renewal License | -VS7-STD-G-SSS-C Basic Support CoverageVMware vSphere 7 Standardfor 1 processor 4 -VCS7-STD-G-SSS-C Basic Support CoverageVMware vCenter Server 7Standard for vSphere 7 (PerInstance) -NET911 | 2021-06-18 11:00:00 | 2021-06-18 00:00:00 | 2021-09-24 10:54:00 | admin.Shiela Marie N. Arceo
IC-1148-21 | CSR-0746-21 | Johanna Marie C. Dandan | SCD | BO | 2021-06-18 08:44:00 | 2021-07-30 21:00:00 | Work in Progress | Renewal License | Request for CATIA LICENSE RENEWAL (81st Term _PRT BO) AUGUST BUDGET_SOFTWARE USAGE OTHERS Php 234,733.97 Mechanical Design 2 (MD2) Target ID: EWU-420E1C4A3E8C03E6 Date Covered: September 16, 2021 to September 15, 2022 IP 10.49.130.131 Budget Php 149,570.38 CATIA - DRAWING PRODUCTIION 2 CONFIGURATION (DP2) Target ID: CEM-41CB1CAE8B220D52 Date Covered: September 16, 2021 to September 15, 2022 IP 10.49.130.230 Budget Php 85,163.59 | 2021-08-11 10:37:00 | 2021-06-18 00:00:00 | 0000-00-00 00:00:00 | admin.Shiela Marie N. Arceo
IC-1157-21 | CSR-0810-21 | Jesrel F. Casabuena | CON | BO | 2021-06-21 11:17:00 | 2021-06-30 21:00:00 | Done | Access Request | Delete Access List Records of Resign CON member. Please see attach file for details. | 2021-06-29 07:42:00 | 2021-06-28 00:00:00 | 2021-07-05 14:11:00 | admin.Shiela Marie N. Arceo
IC-1163-21 | CSR-0768-21 | Kayzelle Shyne S. Magarse | EV | BO | 2021-06-22 06:36:00 | 2021-06-23 21:00:00 | Done | Add Internet Connection | full access of internet needed for the research/survey of trends as Costumer's request. | 2021-06-22 11:52:00 | 2021-06-22 00:00:00 | 2021-06-30 17:14:00 | admin.Donald Kerby L. Manejero
IC-1165-21 | CSR-0769-21 | Mark B. Sucaldito | EV | BO | 2021-06-22 07:20:00 | 2021-06-23 21:00:00 | Done | Add Internet Connection | Internet access to yasuda-san request on documentation. need to full access internet topic. | 2021-06-22 12:18:00 | 2021-06-22 00:00:00 | 2021-06-30 17:13:00 | admin.Donald Kerby L. Manejero
IC-1166-21 | CSR-0785-21 | Annie C. Palo | WHD1 | BO | 2021-06-22 08:54:00 | 2021-06-23 21:00:00 | Done | Backup CAE file/s | Please include in monthly back-up /export/home/eucoodb/model/work/HONDA -33FA -3A0A -3K2A -3K6 -3N0 -TVA -TYA -TZAV -TZBH -XT1E /export/home/eucoodb/model/repository/HONDA -3K6 | 2021-06-25 16:24:00 | 2021-06-24 00:00:00 | 2021-07-05 13:52:00 | admin.Shiela Marie N. Arceo
IC-1170-21 | CSR-0845-21 | Ann Jennet J. Hitones | PRT | BO | 2021-06-22 13:49:00 | 2021-06-22 13:49:00 | Done | PC Configuration | allow usage of web cam | 2021-07-06 09:31:00 | 2021-07-06 00:00:00 | 2021-07-06 09:37:00 | admin.Shiela Marie N. Arceo
IC-1180-21 | CSR-0797-21 | Ian Gabriel P. Tranco | EV | BO | 2021-06-23 09:30:00 | 2021-06-25 21:00:00 | Done | Install Software | Install MS Office(Standby from 10.49.130.209) in 10.49.130.194. | 2021-06-25 13:17:00 | 2021-06-25 00:00:00 | 2021-07-16 15:20:00 | admin.Shiela Marie N. Arceo
IC-1181-21 | CSR-0777-21 | Ariel L. Lachica | EV | BO | 2021-06-23 09:54:00 | 2021-06-25 21:00:00 | Done | Add Internet Connection | I would like to request full internet access for EEDDSHVB-2106007(Yasuda san) research job request. | 2021-06-23 10:34:00 | 2021-06-23 00:00:00 | 2021-06-23 10:35:00 | admin.Shiela Marie N. Arceo
IC-1183-21 | CSR-0790-21 | Rommel E. Aguilon | ADM | BO | 2021-06-23 11:54:00 | 2021-07-02 21:00:00 | Done | Access Request | We would like to request for Ms. Eileen Sorongon to access the scanned RFP of Admin on the following folder location \\10.49.1.97\admin\ARCHIVE\Supplier Conditions. 1. Read Only 2. No delete See her details below. Name: Eileen Sorongon Department: Finance ID Number: 6212 | 2021-06-25 16:40:00 | 2021-06-24 00:00:00 | 2021-06-25 16:47:00 | admin.Ruby A. Maghilum
IC-1189-21 | CSR-0800-21 | Ian Gabriel P. Tranco | EV | BO | 2021-06-24 08:16:00 | 2021-06-25 21:00:00 | Done | Printer Configuration | Reimplementation of CSR-1331-19 and CSR-1488-19(scanning configuration). Background - scan files do not appear in the scan location and e-mail. Need to fix scan issue. | 2021-06-25 14:19:00 | 2021-06-25 00:00:00 | 2021-07-19 08:07:00 | admin.Elmo A. Daquila JR.
IC-1194-21 | CSR-0808-21 | Ruzzel R. Ambrocio | CON | BO | 2021-06-24 10:19:00 | 2021-07-05 21:00:00 | Done | Account Request | New Email Request (See Attachment for Details). For Job Coordination Purposes (Team Leader). | 2021-07-02 08:06:00 | 2021-06-28 00:00:00 | 2021-07-06 11:47:00 | admin.Nancy O. Gendive
IC-1200-21 | CSR-0781-21 | Kerby Joy S. Yu | EA-DM | BO | 2021-06-24 13:58:00 | 2021-06-25 21:00:00 | Done | Install Software | SOFTWARE - POWER BI desktop New set of database use by our counterpart for 81st term. i would like to request to install power bi to PET YGP members. | 2021-06-25 14:45:00 | 2021-06-24 00:00:00 | 2021-07-09 10:48:00 | admin.Shiela Marie N. Arceo
IC-1215-21 | CPR-0072-21 | Mark B. Sucaldito | EV | BO | 2021-06-28 07:13:00 | 2021-06-28 07:13:00 | Done | Mouse | replacement of mouse | 2021-06-29 08:18:00 | 2021-06-28 00:00:00 | 2021-06-29 08:20:00 | admin.Elmo A. Daquila JR.
IC-1229-21 | CSR-0827-21 | Wennie Rose C. Camus | SCD | BO | 2021-06-28 15:50:00 | 2021-08-09 21:00:00 | Done | Software Purchase | Please Prepare PRIF for the item below (81st Term, CON Department) , Thank You!: ITEM: English PloComp Ver.10.12 QTY: 2 BUDGET (july): 11,466.77 | 2021-07-06 07:56:00 | 2021-06-30 00:00:00 | 2021-09-01 07:45:00 | admin.Shiela Marie N. Arceo
IC-1230-21 | CSR-0822-21 | Kristel Anne D. Villanueva | SCD | BO | 2021-06-28 17:23:00 | 2021-06-29 21:00:00 | Done | Account Request | Delete Windows Log-In Account, and email of resigned member, Carag, Phincy Roy T. (ID No. 6059). Delete User Tap Card access in ED1_ApeosPort-V 5070, ED2_ApeosPort-V 5070, ED_DocuCentre-V C5576. | 2021-06-30 17:08:00 | 2021-06-29 00:00:00 | 2021-07-28 09:50:00 | admin.Donald Kerby L. Manejero
IC-1232-21 | CSR-0820-21 | Annabelle L. Malonda | EI | BO | 2021-06-29 06:47:00 | 2021-10-05 21:00:00 | Closed | Hardware Purchase | Laptop PC for incoming BO SW manager using August budget (Php 60,000) \\10.49.1.97\Budget Control\FY81_BUDGET\1. ENGINEERING REDUCED 3\BO\FY81P_BO_ENGINEERING_SW.xlsx Please prioritize. | 2021-06-29 14:34:00 | 2021-06-29 00:00:00 | 2021-09-23 07:06:00 | admin.Shiela Marie N. Arceo | 907.53
IC-1233-21 | CSR-0819-21 | Annabelle L. Malonda | EI | BO | 2021-06-29 06:55:00 | 2021-10-05 21:00:00 | Done | Hardware Purchase | Laptop PC for Software Evaluation using September budget (PhP 60,000) \\10.49.1.97\Budget Control\FY81_BUDGET\1. ENGINEERING REDUCED 3\BO\FY81P_BO_ENGINEERING_SW.xlsx This will be in replacement of 10.49.130.166 (poorly performing laptop PC with RAM expansion maxed out). | 2021-06-29 14:34:00 | 2021-06-29 00:00:00 | 2021-09-23 07:06:00 | admin.Shiela Marie N. Arceo
IC-1236-21 | DRR-0101-21 | Kayzelle Shyne S. Magarse | EV | BO | 2021-06-29 08:18:00 | 2021-06-29 08:18:00 | Done | Windows | MA32_SHIN;Z:\③ JOB_ORDERS\EV_BOX\2021\7月\EVB1-2106014 (SUZUKI SAN)\OUTPUT\3D MODEL\10mdl\JIG MODEL;Original Directory;No;accidentally deleted | 2021-07-05 08:34:00 | 2021-06-30 00:00:00 | 2021-07-05 08:41:00 | admin.Shiela Marie N. Arceo
IC-1237-21 | DRR-0104-21 | Nikko Matthew L. Eulatic | PRT | BO | 2021-06-29 10:47:00 | 2021-06-29 10:47:00 | Done | Windows | 7276-6639-50 7176-6640-50;Z:\ILOILO PARTS\03-W.I.P\06-JUN'21\21-30\FUTORI\SWEDEN\0629\13.7276-6639-50\E_DWG;Original Directory;No;file was deleted | 2021-07-06 09:31:00 | 2021-07-06 00:00:00 | 2021-07-06 09:37:00 | admin.Shiela Marie N. Arceo
IC-1242-21 | CSR-0825-21 | Wennie Rose C. Camus | SCD | BO | 2021-06-29 13:13:00 | 2021-07-08 21:00:00 | Done | Access Request | Please kindly give folder access to the New members of CON BO. Please kindly refer to attached file. | 2021-07-05 13:30:00 | 2021-06-30 00:00:00 | 2021-07-06 17:08:00 | admin.Kevin Neil A. Mapa
IC-1243-21 | CSR-0824-21 | Wennie Rose C. Camus | SCD | BO | 2021-06-29 15:44:00 | 2021-07-08 21:00:00 | Done | Account Request | Please kindly give SEINE2 and CMMS account access to New member of CON BO. Please kindly refer to attached file. | 2021-07-05 15:33:00 | 2021-06-30 00:00:00 | 2021-07-28 09:43:00 | admin.Donald Kerby L. Manejero
IC-1248-21 | CSR-0833-21 | Lennil P Castañares | EI | BO | 2021-06-30 09:25:00 | 2021-07-01 21:00:00 | Done | Install Software | Install notepad++ for laptop (IP address 10.49.130.183 & 10.49.131.116) | 2021-07-02 13:49:00 | 2021-07-01 00:00:00 | 2021-07-02 14:05:00 | admin.Elmo A. Daquila JR.
IC-1250-21 | DRR-0100-21 | Ian Gabriel P. Tranco | EV | BO | 2021-06-30 10:27:00 | 2021-06-30 10:27:00 | Done | Windows | DPA;\\10.49.128.7\ev_(branch)\COMMON FILES\COMMON\ISMS;Original Directory;Yes;Accidental deletion | 2021-07-05 08:35:00 | 2021-06-30 00:00:00 | 2021-07-16 15:20:00 | admin.Shiela Marie N. Arceo
IC-1260-21 | CSR-0851-21 | Wennie Rose C. Camus | SCD | BO | 2021-06-30 16:45:00 | 2021-08-11 21:00:00 | Done | Renewal License | Please Prepare PRIF for the item below (81st Term, CON Department) , Thank You!: ITEM: MicroCadam QTY: 2 - [I.P. Address : 10.49.130.115 & 10.49.130.116] BUDGET (September & January): 65,851.32 | 2021-07-06 15:25:00 | 2021-07-06 00:00:00 | 2021-09-01 09:04:00 | admin.Shiela Marie N. Arceo
IC-1269-21 | CSR-0877-21 | Annie C. Palo | WHD1 | BO | 2021-07-01 11:50:00 | 2021-07-02 21:00:00 | Done | Backup CAE file/s | /export/home/eucoodb/model/repository/HONDA -3K6 -TG4 | 2021-07-08 13:21:00 | 2021-07-08 00:00:00 | 2021-07-08 13:21:00 | admin.Elmo A. Daquila JR.
IC-1280-21 | CSR-0836-21 | Belinda C. Cabico | WHE | BO | 2021-07-02 08:41:00 | 2021-08-13 21:00:00 | Done | Renewal License | Brava IXL Renewal License for BO (3) | 2021-07-06 07:11:00 | 2021-07-02 00:00:00 | 2021-09-13 10:05:00 | admin.Shiela Marie N. Arceo
IC-1281-21 | CSR-0844-21 | Shenie Lou G Besa | EDSD | BO | 2021-07-02 08:52:00 | 2021-07-13 21:00:00 | Done | Access Request | Request for folder access rights of new TYT member. 1. pet6196 | 2021-07-05 13:30:00 | 2021-07-05 00:00:00 | 2021-07-14 06:58:00 | admin.Shiela Marie N. Arceo
IC-1284-21 | CSR-0843-21 | Shenie Lou G Besa | EDSD | BO | 2021-07-02 09:50:00 | 2021-07-13 21:00:00 | Done | Account Request | Request for deletion of all accounts and folder access rights of resigned member. 1. pet6209 | 2021-07-05 15:28:00 | 2021-07-05 00:00:00 | 2021-07-26 17:51:00 | admin.Donald Kerby L. Manejero
IC-1285-21 | CSR-0853-21 | Johansson L. Binalla | CON | BO | 2021-07-02 10:56:00 | 2021-07-13 21:00:00 | Done | Access Request | Need to have access from this Address to add files and records for the new employee trainees. | 2021-07-07 12:57:00 | 2021-07-07 00:00:00 | 2021-07-07 13:13:00 | admin.Kevin Neil A. Mapa
IC-1288-21 | DRR-0106-21 | Jennifer D. Umali | WHD3 | BO | 2021-07-05 07:48:00 | 2021-07-05 07:48:00 | Done | Windows | ALL FILES inside (\\10.49.128.7\wh\common\nissan);\\10.49.128.7\wh\common\nissan;Original Directory;No;active files for delivery | 2021-07-07 07:09:00 | 2021-07-07 00:00:00 | 2021-07-07 07:14:00 | admin.Shiela Marie N. Arceo
IC-1296-21 | CSR-0852-21 | Jesrel F. Casabuena | CON | BO | 2021-07-05 14:39:00 | 2021-07-14 21:00:00 | Done | Access Request | Delete Access List Records of Resign CON member. Please see attach file for details. | 2021-07-07 07:09:00 | 2021-07-07 00:00:00 | 2021-07-21 10:18:00 | admin.Shiela Marie N. Arceo
IC-1309-21 | CSR-0868-21 | Wennie Rose C. Camus | SCD | BO | 2021-07-06 16:48:00 | 2021-07-07 21:00:00 | Done | Printer Configuration | Please kindly enroll CON new member User tap card in ED2_ApeosPort-V 5070,ED_DocuCentre-V C5576 KENT J. MATUNDING (6215) KIRBY D. SOLDEVILLA (6216) MARYELLE B. LOPEZ (6219) PRINCESS LHEAN O. CANTO (6214) KARL JAN A. ASUMBRA (6220) JESSA ANN Y. QUIñONERO (6217) SHIELA A. PORTILLO (6218) Thank You! | 2021-07-08 13:07:00 | 2021-07-08 00:00:00 | 2021-07-08 13:46:00 | admin.Elmo A. Daquila JR.
IC-1324-21 | CPR-0078-21 | Donald Kerby L. Manejero | MIS | BO | 2021-07-07 16:14:00 | 2021-07-07 16:14:00 | Done | Printer/Plotter | ERROR CODE: 042-325. need to shutdown machine. | 2021-07-07 16:28:00 | 2021-07-07 00:00:00 | 2021-07-22 14:29:00 | admin.Elmo A. Daquila JR.
IC-1335-21 | CSR-0901-21 | Catherine Anne D. CaÃ±onero | WHE | BO | 2021-07-08 13:54:00 | 2021-07-19 21:00:00 | Done | Account Request | Transfer from CONN to WHE | 2021-07-13 14:38:00 | 2021-07-13 00:00:00 | 2021-07-23 10:49:00 | admin.Shiela Marie N. Arceo
IC-1337-21 | CSR-0891-21 | Francis Razel R. Ybañez | EI | BO | 2021-07-09 09:46:00 | 2021-07-12 09:46:00 | Done | Install Software | Install Multi IDE for Renesas ICE test. Installer \\Petifssvr\ei_(branch)\24 SOFTWARE\COMMON\⑤EQUIPMENT SOFTWARE. File name win64_v800. | 2021-07-12 10:10:00 | 2021-07-12 00:00:00 | 2021-07-12 13:07:00 | admin.Shiela Marie N. Arceo
IC-1339-21 | CSR-0885-21 | Johanna Marie C. Dandan | SCD | BO | 2021-07-09 13:39:00 | 2021-07-12 21:00:00 | Done | Install Software | Request for Software Installation. (PRT_BO) Soft name: PloComp (English) Soft version no.: 10.12 Quantity: 1 | 2021-07-12 13:07:00 | 2021-07-10 00:00:00 | 2021-07-14 06:57:00 | admin.Shiela Marie N. Arceo
IC-1346-21 | CSR-1012-21 | Shiela Marie N. Arceo | MIS | BO | 2021-07-09 17:28:00 | 2021-08-20 21:00:00 | Done | Renewal License | Renewal of HArdware Server • VM Server Host 1 (HP DL360 Gen9 8SFF 8C E5-2630v3) ---Serial NO. SGH608XJOR • VM Server Host 2 (HP DL360 Gen9 8SFF 8C E5-2630v3) --Serial NO.SGH608XJOT • Wsus Server (Proliant DL60 Gen9 4LFF CTO Svr) -- Serial NO. SGH634YJDC • Active Directory / DNS (Proliant DL60 Gen9 4LFF CTO Svr) --Serial NO. SGH634YJDB • HP (FlexFabric 5700-32XGT-8XGT-2QSFP+ JG898A) -- Serial No. CN65GN502R --Serial No. CN65GN50CJ | 2021-08-06 07:36:00 | 2021-08-06 00:00:00 | 2021-09-24 10:54:00 | admin.Shiela Marie N. Arceo
IC-1351-21 | CSR-0955-21 | Shenie Lou G Besa | EDSD | BO | 2021-07-12 09:46:00 | 2021-07-13 21:00:00 | Done | Transfer PC location | Request for transfer of PC and telephone from EDSD area to SCD area. IP - 10.49.131.251 Local - 437 | 2021-08-09 09:06:00 | 2021-07-28 00:00:00 | 2021-08-09 09:07:00 | admin.Donald Kerby L. Manejero
IC-1369-21 | CSR-0906-21 | Nikko Matthew L. Eulatic | PRT | BO | 2021-07-13 14:04:00 | 2021-07-19 21:00:00 | Done | Modify Software | Customer request solidworks 2020 | 2021-07-19 06:50:00 | 2021-07-14 00:00:00 | 2021-07-19 06:51:00 | admin.Shiela Marie N. Arceo
IC-1378-21 | CPR-0087-21 | Vincent Danyl C. Tagaduar | CON | BO | 2021-07-14 09:56:00 | 2021-07-14 09:56:00 | Done | Mouse | DEFECTIVE MOUSE SCROLL | 2021-07-28 09:36:00 | 2021-07-27 00:00:00 | 2021-07-28 09:36:00 | admin.Elmo A. Daquila JR.
IC-1379-21 | CSR | Francis Razel R. Ybañez | EI | BO | 2021-07-14 10:00:00 | 2021-07-15 21:00:00 | Assigned | Download | Download RH850 Datasheet/ hardware manual in https://www.scribd.com/document/392601540/r01uh0451ej0220-rh850d1lm | 0000-00-00 00:00:00 | 0000-00-00 00:00:00 | 0000-00-00 00:00:00
IC-1384-21 | CPR-0084-21 | Rhonalyn S. Encarnacion | EI | BO | 2021-07-14 11:08:00 | 2021-07-09 11:08:00 | Done | Laptop | In the normal usage of laptop, the laptop should not heat up. The suspicion is that the problem comes from the fan that is not working well. Until last Friday, July 09 the fan of the laptop made noises every now and then which may cause a lot more damage if continued to be used during operations/tests. | 2021-07-26 11:16:00 | 2021-07-26 00:00:00 | 2021-07-26 11:29:00 | admin.Elmo A. Daquila JR.
IC-1385-21 | CSR-0919-21 | Shenie Lou G Besa | EDSD | BO | 2021-07-14 13:44:00 | 2021-07-23 21:00:00 | Done | Account Request | Request for deletion of all accounts of resigned member. 1. pet6037 | 2021-07-16 18:50:00 | 2021-07-16 00:00:00 | 2021-07-27 06:55:00 | admin.Shiela Marie N. Arceo